## Outage Plan EirGrid
2025 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2025 |  |  |  |  | Feb '2025 |  |  |  | Mar '2025 |  |  |  |  | Apr '2025 |  |  |  | May '2025 |  |  |  | Jun '2025 |  |  |  |  | Jul '2025 |  |  |  | Aug '2025 |  |  |  | Sep '2025 |  |  |  |  | Oct '2025 |  |  |  | Nov '2025 |  |  |  | Dec '2025
|  | Week | 1 '2025 | 2 '2025 | 3 '2025 | 4 '2025 | 5 '2025 | 6 '2025 | 7 '2025 | 8 '2025 | 9 '2025 | 10 '2025 | 11 '2025 | 12 '2025 | 13 '2025 | 14 '2025 | 15 '2025 | 16 '2025 | 17 '2025 | 18 '2025 | 19 '2025 | 20 '2025 | 21 '2025 | 22 '2025 | 23 '2025 | 24 '2025 | 25 '2025 | 26 '2025 | 27 '2025 | 28 '2025 | 29 '2025 | 30 '2025 | 31 '2025 | 32 '2025 | 33 '2025 | 34 '2025 | 35 '2025 | 36 '2025 | 37 '2025 | 38 '2025 | 39 '2025 | 40 '2025 | 41 '2025 | 42 '2025 | 43 '2025 | 44 '2025 | 45 '2025 | 46 '2025 | 47 '2025 | 48 '2025 | 49 '2025 | 50 '2025 | 51 '2025 | 52 '2025 | 53 '2025
Station | Unit | NPR
Aghada | AD2 | 449
Aghada | AT1 | 90 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Aghada | AT2 | 90
Aghada | AT4 | 90
Aghada 110kV | AD3 | 19
Ardnacrusha | AA1 | 21 | [23 empty] | S
Ardnacrusha | AA2 | 22 | [14 empty] | S
Ardnacrusha | AA3 | 19 | [17 empty] | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [34 empty] | S | S | S | S | S
Banoge 110kV | OD1 | 9
Beenanaspuck Tobertoreen | XT2 | 11
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [20 empty] | S | S | S | S | S | S | S | S | S
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | S | S | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
ENEL X | EX1 | 20
Energy Trading | ET1 | 13
Enernoc | AE1 | 95
Enernoc | AE2 | 12
Enernoc | AE3 | 14
Enernoc | AE4 | 15
Enernoc | AE5 | 15
Enernoc | EN1 | 15
Enernoc | EN2 | 16
Enernoc | EN3 | 16
Enernoc | EN4 | 16
Enernoc | EN5 | 6
Enernoc | EN6 | 11
Enernoc | EN8 | 21
Enernoc | EN9 | 16
Erne | ER1 | 10 | [16 empty] | S | S | S
Erne | ER2 | 10 | [36 empty] | S
Erne | ER3 | 22 | [23 empty] | S | S | S | S | S | S | S | S
Erne | ER4 | 22 | [38 empty] | S
EWIC | EW1 | 500
Gardnershill | GP1 | 8
Golagh 110kV | GO2 | 3
Gorman 110kV | GF1 | 50
Great Island | GI4 | 461
Huntstown | HN2 | 400
Huntstown | HNC | 342 | [13 empty] | S | S | S
Indaver | IW1 | 17
Kelwin | KZ4 | 27
Kilteel 110kV | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [20 empty] | S | S
Lee | LE2 | 4 | [12 empty] | S | S
Lee | LE3 | 8 | [16 empty] | S | S
Liffey | LI1 | 15
Liffey | LI2 | 15
Liffey | LI4 | 4
Liffey | LI5 | 4
Lumcloon | LU1 | 50
Lumcloon | LU2 | 50
Moneypoint | MP1 | 285 | [18 empty] | S | S
Moneypoint | MP2 | 285 | [19 empty] | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [37 empty] | S
Poolbeg | PB4 | 154 | [16 empty] | S | S
Poolbeg | PB5 | 146 | [19 empty] | S
Poolbeg | PB6 | 168 | [16 empty] | S
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Shannonbridge | SI1 | 50
Shannonbridge | SI2 | 50
Tarbert | TB1 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB2 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB3 | 241 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB4 | 243 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Tawnaghmore 110kV | KF2 | 11
Turlough Hill | TH1 | 73 | [9 empty] | S
Turlough Hill | TH2 | 73 | [9 empty] | S
Turlough Hill | TH3 | 73 | [9 empty] | S
Turlough Hill | TH4 | 73 | [9 empty] | S
Tynagh | TYC | 384 | [39 empty] | S
VIOTAS | EE1 | 47
VIOTAS | EE2 | 20
VIOTAS | EE3 | 8
VIOTAS | EE4 | 9
VIOTAS | EE5 | 7
VIOTAS | EE6 | 14
VIOTAS | EE7 | 9
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | [39 empty] | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Tarbert | TB4 | 243 | 2023-03-31 17:00 | 2030-12-31 00:30 | F | 2831.29
Tarbert | TB2 | 54 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Tarbert | TB1 | 54 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Aghada | AT1 | 90 | 2024-01-01 | 2025-12-31 00:30 | S | 730
Tarbert | TB3 | 241 | 2024-01-01 | 2030-12-31 00:30 | F | 2556
Edenderry | ED1 | 118 | 2024-12-26 12:00 | 2025-01-01 08:00 | S | 5.83
Turlough Hill | TH1 | 73 | 2025-03-03 | 2025-03-12 00:30 | S | 9
Turlough Hill | TH2 | 73 | 2025-03-03 | 2025-03-12 00:30 | S | 9
Turlough Hill | TH3 | 73 | 2025-03-03 | 2025-03-12 00:30 | S | 9
Turlough Hill | TH4 | 73 | 2025-03-03 | 2025-03-12 00:30 | S | 9
Lee | LE2 | 4 | 2025-03-24 | 2025-04-04 00:30 | S | 11
Huntstown | HNC | 342 | 2025-04-01 | 2025-04-22 | S | 21
Ardnacrusha | AA2 | 22 | 2025-04-07 08:00 | 2025-04-11 20:00 | S | 4.5
Edenderry | ED1 | 118 | 2025-04-17 17:00 | 2025-04-23 08:00 | S | 5.58
Lee | LE3 | 8 | 2025-04-22 | 2025-05-02 00:30 | S | 10
Erne | ER1 | 10 | 2025-04-23 08:00 | 2025-05-14 20:00 | S | 21.5
Poolbeg | PB4 | 154 | 2025-04-24 | 2025-05-04 00:30 | S | 10
Poolbeg | PB6 | 168 | 2025-04-24 | 2025-04-29 00:30 | S | 5
Ardnacrusha | AA3 | 19 | 2025-04-28 08:00 | 2025-05-30 20:00 | S | 32.5
Moneypoint | MP1 | 285 | 2025-05-03 22:00 | 2025-05-15 22:00 | S | 12
Moneypoint | MP2 | 285 | 2025-05-09 22:00 | 2025-07-04 22:00 | S | 56
Poolbeg | PB5 | 146 | 2025-05-12 | 2025-05-17 00:30 | S | 5
Dublin Bay | DB1 | 405 | 2025-05-19 | 2025-07-18 00:30 | S | 60
Lee | LE1 | 15 | 2025-05-19 | 2025-05-30 00:30 | S | 11
Erne | ER3 | 22.5 | 2025-06-09 08:00 | 2025-08-01 20:00 | S | 53.5
Ardnacrusha | AA1 | 21 | 2025-06-09 08:00 | 2025-06-13 20:00 | S | 4.5
Aghada | AT2 | 90 | 2025-06-13 | 2025-06-16 00:30 | S | 3
Aghada | AT4 | 90 | 2025-06-27 | 2025-06-30 00:30 | S | 3
Edenderry | ED1 | 118 | 2025-07-04 12:00 | 2025-09-01 08:00 | S | 58.83
Ardnacrusha | AA4 | 24 | 2025-08-25 07:30 | 2025-09-26 20:00 | S | 32.5
Edenderry | ED3 | 58 | 2025-09-05 09:00 | 2025-09-05 18:30 | S | 0.38
Erne | ER2 | 10 | 2025-09-08 08:00 | 2025-09-12 20:00 | S | 4.5
Moneypoint | MP3 | 285 | 2025-09-12 22:00 | 2025-09-24 22:30 | S | 12
Erne | ER4 | 22.5 | 2025-09-22 07:30 | 2025-09-26 20:00 | S | 4.5
Whitegate | WG1 | 444 | 2025-09-26 | 2025-10-07 | S | 11
Tynagh | TYC | 384 | 2025-09-28 20:00 | 2025-10-03 22:00 | S | 5.08
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2025 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2025 |  |  |  |  | Feb '2025 |  |  |  | Mar '2025 |  |  |  |  | Apr '2025 |  |  |  | May '2025 |  |  |  | Jun '2025 |  |  |  |  | Jul '2025 |  |  |  | Aug '2025 |  |  |  | Sep '2025 |  |  |  |  | Oct '2025 |  |  |  | Nov '2025 |  |  |  | Dec '2025
|  | Week | 1 '2025 | 2 '2025 | 3 '2025 | 4 '2025 | 5 '2025 | 6 '2025 | 7 '2025 | 8 '2025 | 9 '2025 | 10 '2025 | 11 '2025 | 12 '2025 | 13 '2025 | 14 '2025 | 15 '2025 | 16 '2025 | 17 '2025 | 18 '2025 | 19 '2025 | 20 '2025 | 21 '2025 | 22 '2025 | 23 '2025 | 24 '2025 | 25 '2025 | 26 '2025 | 27 '2025 | 28 '2025 | 29 '2025 | 30 '2025 | 31 '2025 | 32 '2025 | 33 '2025 | 34 '2025 | 35 '2025 | 36 '2025 | 37 '2025 | 38 '2025 | 39 '2025 | 40 '2025 | 41 '2025 | 42 '2025 | 43 '2025 | 44 '2025 | 45 '2025 | 46 '2025 | 47 '2025 | 48 '2025 | 49 '2025 | 50 '2025 | 51 '2025 | 52 '2025 | 53 '2025
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [37 empty] | S
Ballylumford | NIBGT2 | 58 | [11 empty] | S | [26 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [19 empty] | S | [15 empty] | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT2 | 29 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT3 | 42 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT4 | 42 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Kilroot | NIKGT1 | 29 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT2 | 29 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT3 | 42 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT4 | 42 | 2024-10-01 | 2025-10-01 | S | 365
Coolkeeragh | NIC30 | 408 | 2025-02-02 | 2025-02-03 | S | 1
Ballylumford | NIBGT2 | 58 | 2025-03-17 | 2025-03-23 | S | 6
Ballylumford | NIB31 | 249 | 2025-03-21 | 2025-03-24 | S | 3
Ballylumford | NIB32 | 249 | 2025-03-28 | 2025-03-31 | S | 3
Coolkeeragh | NIC30 | 408 | 2025-05-03 | 2025-05-05 | S | 2
Coolkeeragh | NIC30 | 408 | 2025-05-12 | 2025-05-17 | S | 5
Coolkeeragh | NICGT8 | 53 | 2025-05-12 | 2025-05-17 | S | 5
Ballylumford | NIB10 | 94 | 2025-05-23 | 2025-05-26 | S | 3
Moyle | MOYLE | 450 | 2025-06-17 | 2025-06-20 | 250 | 3
Coolkeeragh | NIC30 | 408 | 2025-07-05 | 2025-07-06 | S | 1
Ballylumford | NIB31 | 249 | 2025-08-08 | 2025-08-11 | S | 3
Ballylumford | NIB32 | 249 | 2025-08-08 | 2025-08-15 | 161 | 7
Ballylumford | NIB31 | 249 | 2025-08-11 | 2025-08-22 | 161 | 11
Ballylumford | NIB32 | 249 | 2025-08-15 | 2025-08-18 | S | 3
Coolkeeragh | NIC30 | 408 | 2025-09-01 | 2025-09-11 | S | 10
Ballylumford | NIBGT1 | 58 | 2025-09-17 | 2025-09-23 | S | 6
Ballylumford | NIBGT2 | 58 | 2025-09-23 | 2025-09-29 | S | 6
Ballylumford | NIB10 | 94 | 2025-11-13 | 2025-11-16 | S | 3
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2025 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2025 |  |  |  |  | Feb '2025 |  |  |  | Mar '2025 |  |  |  |  | Apr '2025 |  |  |  | May '2025 |  |  |  | Jun '2025 |  |  |  |  | Jul '2025 |  |  |  | Aug '2025 |  |  |  | Sep '2025 |  |  |  |  | Oct '2025 |  |  |  | Nov '2025 |  |  |  | Dec '2025
|  | Week | 1 '2025 | 2 '2025 | 3 '2025 | 4 '2025 | 5 '2025 | 6 '2025 | 7 '2025 | 8 '2025 | 9 '2025 | 10 '2025 | 11 '2025 | 12 '2025 | 13 '2025 | 14 '2025 | 15 '2025 | 16 '2025 | 17 '2025 | 18 '2025 | 19 '2025 | 20 '2025 | 21 '2025 | 22 '2025 | 23 '2025 | 24 '2025 | 25 '2025 | 26 '2025 | 27 '2025 | 28 '2025 | 29 '2025 | 30 '2025 | 31 '2025 | 32 '2025 | 33 '2025 | 34 '2025 | 35 '2025 | 36 '2025 | 37 '2025 | 38 '2025 | 39 '2025 | 40 '2025 | 41 '2025 | 42 '2025 | 43 '2025 | 44 '2025 | 45 '2025 | 46 '2025 | 47 '2025 | 48 '2025 | 49 '2025 | 50 '2025 | 51 '2025 | 52 '2025 | 53 '2025
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Aghada | AD2 | 449
Aghada | AT1 | 90 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Aghada | AT2 | 90
Aghada | AT4 | 90
Aghada 110kV | AD3 | 19
Ardnacrusha | AA1 | 21 | [23 empty] | S
Ardnacrusha | AA2 | 22 | [14 empty] | S
Ardnacrusha | AA3 | 19 | [17 empty] | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [34 empty] | S | S | S | S | S
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [37 empty] | S
Ballylumford | NIBGT2 | 58 | [11 empty] | S | [26 empty] | S
Banoge 110kV | OD1 | 9
Beenanaspuck Tobertoreen | XT2 | 11
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [19 empty] | S | [15 empty] | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
DAE Virtual Power Plant | DP1 | 19
DAE Virtual Power Plant | DP2 | 26
Dublin Bay | DB1 | 405 | [20 empty] | S | S | S | S | S | S | S | S | S
Dublin Waste To Energy | DW1 | 62
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | S | S | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 20
Empower | NIEMP | 3
Endeco Technologies | EC1 | 47
Endeco Technologies | EC2 | 11
Endeco Technologies | EC5 | 15
Endeco Technologies | NIECA | 13
ENEL X | EX1 | 20
Energy Trading | ET1 | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Enernoc | AE1 | 95
Enernoc | AE2 | 12
Enernoc | AE3 | 14
Enernoc | AE4 | 15
Enernoc | AE5 | 15
Enernoc | EN1 | 15
Enernoc | EN2 | 16
Enernoc | EN3 | 16
Enernoc | EN4 | 16
Enernoc | EN5 | 6
Enernoc | EN6 | 11
Enernoc | EN8 | 21
Enernoc | EN9 | 16
Erne | ER1 | 10 | [16 empty] | S | S | S
Erne | ER2 | 10 | [36 empty] | S
Erne | ER3 | 22 | [23 empty] | S | S | S | S | S | S | S | S
Erne | ER4 | 22 | [38 empty] | S
EWIC | EW1 | 500
Gardnershill | GP1 | 8
Golagh 110kV | GO2 | 3
Gorman 110kV | GF1 | 50
Great Island | GI4 | 461
Huntstown | HN2 | 400
Huntstown | HNC | 342 | [13 empty] | S | S | S
Indaver | IW1 | 17
iPower | NIAGU | 74
Kelwin | KZ4 | 27
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT2 | 29 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT3 | 42 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT4 | 42 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilteel 110kV | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [20 empty] | S | S
Lee | LE2 | 4 | [12 empty] | S | S
Lee | LE3 | 8 | [16 empty] | S | S
Liffey | LI1 | 15
Liffey | LI2 | 15
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisahally | NILPS | 18
Lumcloon | LU1 | 50
Lumcloon | LU2 | 50
Moneypoint | MP1 | 285 | [18 empty] | S | S
Moneypoint | MP2 | 285 | [19 empty] | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [37 empty] | S
Moyle | MOYLE | 450
Poolbeg | PB4 | 154 | [16 empty] | S | S
Poolbeg | PB5 | 146 | [19 empty] | S
Poolbeg | PB6 | 168 | [16 empty] | S
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 85
Seal Rock | SK4 | 85
Seecon | SO1 | 105
Shannonbridge | SI1 | 50
Shannonbridge | SI2 | 50
Tarbert | TB1 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB2 | 54 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB3 | 241 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tarbert | TB4 | 243 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Tawnaghmore 110kV | KF2 | 11
Turlough Hill | TH1 | 73 | [9 empty] | S
Turlough Hill | TH2 | 73 | [9 empty] | S
Turlough Hill | TH3 | 73 | [9 empty] | S
Turlough Hill | TH4 | 73 | [9 empty] | S
Tynagh | TYC | 384 | [39 empty] | S
VIOTAS | EE1 | 47
VIOTAS | EE2 | 20
VIOTAS | EE3 | 8
VIOTAS | EE4 | 9
VIOTAS | EE5 | 7
VIOTAS | EE6 | 14
VIOTAS | EE7 | 9
Viridian Energy | VE1 | 20
Viridian Energy DSU | VE2 | 13
Whitegate | WG1 | 444 | [39 empty] | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Tarbert | TB4 | 243 | 2023-03-31 17:00 | 2030-12-31 00:30 | F | 2831.29
Tarbert | TB2 | 54 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Tarbert | TB1 | 54 | 2023-09-30 | 2030-12-31 00:30 | F | 2649
Aghada | AT1 | 90 | 2024-01-01 | 2025-12-31 00:30 | S | 730
Tarbert | TB3 | 241 | 2024-01-01 | 2030-12-31 00:30 | F | 2556
Kilroot | NIKGT1 | 29 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT2 | 29 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT3 | 42 | 2024-10-01 | 2025-10-01 | S | 365
Kilroot | NIKGT4 | 42 | 2024-10-01 | 2025-10-01 | S | 365
Edenderry | ED1 | 118 | 2024-12-26 12:00 | 2025-01-01 08:00 | S | 5.83
Coolkeeragh | NIC30 | 408 | 2025-02-02 | 2025-02-03 | S | 1
Turlough Hill | TH1 | 73 | 2025-03-03 | 2025-03-12 00:30 | S | 9
Turlough Hill | TH2 | 73 | 2025-03-03 | 2025-03-12 00:30 | S | 9
Turlough Hill | TH3 | 73 | 2025-03-03 | 2025-03-12 00:30 | S | 9
Turlough Hill | TH4 | 73 | 2025-03-03 | 2025-03-12 00:30 | S | 9
Ballylumford | NIBGT2 | 58 | 2025-03-17 | 2025-03-23 | S | 6
Ballylumford | NIB31 | 249 | 2025-03-21 | 2025-03-24 | S | 3
Lee | LE2 | 4 | 2025-03-24 | 2025-04-04 00:30 | S | 11
Ballylumford | NIB32 | 249 | 2025-03-28 | 2025-03-31 | S | 3
Huntstown | HNC | 342 | 2025-04-01 | 2025-04-22 | S | 21
Ardnacrusha | AA2 | 22 | 2025-04-07 08:00 | 2025-04-11 20:00 | S | 4.5
Edenderry | ED1 | 118 | 2025-04-17 17:00 | 2025-04-23 08:00 | S | 5.58
Lee | LE3 | 8 | 2025-04-22 | 2025-05-02 00:30 | S | 10
Erne | ER1 | 10 | 2025-04-23 08:00 | 2025-05-14 20:00 | S | 21.5
Poolbeg | PB4 | 154 | 2025-04-24 | 2025-05-04 00:30 | S | 10
Poolbeg | PB6 | 168 | 2025-04-24 | 2025-04-29 00:30 | S | 5
Ardnacrusha | AA3 | 19 | 2025-04-28 08:00 | 2025-05-30 20:00 | S | 32.5
Coolkeeragh | NIC30 | 408 | 2025-05-03 | 2025-05-05 | S | 2
Moneypoint | MP1 | 285 | 2025-05-03 22:00 | 2025-05-15 22:00 | S | 12
Moneypoint | MP2 | 285 | 2025-05-09 22:00 | 2025-07-04 22:00 | S | 56
Poolbeg | PB5 | 146 | 2025-05-12 | 2025-05-17 00:30 | S | 5
Coolkeeragh | NIC30 | 408 | 2025-05-12 | 2025-05-17 | S | 5
Coolkeeragh | NICGT8 | 53 | 2025-05-12 | 2025-05-17 | S | 5
Dublin Bay | DB1 | 405 | 2025-05-19 | 2025-07-18 00:30 | S | 60
Lee | LE1 | 15 | 2025-05-19 | 2025-05-30 00:30 | S | 11
Ballylumford | NIB10 | 94 | 2025-05-23 | 2025-05-26 | S | 3
Erne | ER3 | 22.5 | 2025-06-09 08:00 | 2025-08-01 20:00 | S | 53.5
Ardnacrusha | AA1 | 21 | 2025-06-09 08:00 | 2025-06-13 20:00 | S | 4.5
Aghada | AT2 | 90 | 2025-06-13 | 2025-06-16 00:30 | S | 3
Moyle | MOYLE | 450 | 2025-06-17 | 2025-06-20 | 250 | 3
Aghada | AT4 | 90 | 2025-06-27 | 2025-06-30 00:30 | S | 3
Edenderry | ED1 | 118 | 2025-07-04 12:00 | 2025-09-01 08:00 | S | 58.83
Coolkeeragh | NIC30 | 408 | 2025-07-05 | 2025-07-06 | S | 1
Ballylumford | NIB31 | 249 | 2025-08-08 | 2025-08-11 | S | 3
Ballylumford | NIB32 | 249 | 2025-08-08 | 2025-08-15 | 161 | 7
Ballylumford | NIB31 | 249 | 2025-08-11 | 2025-08-22 | 161 | 11
Ballylumford | NIB32 | 249 | 2025-08-15 | 2025-08-18 | S | 3
Ardnacrusha | AA4 | 24 | 2025-08-25 07:30 | 2025-09-26 20:00 | S | 32.5
Coolkeeragh | NIC30 | 408 | 2025-09-01 | 2025-09-11 | S | 10
Edenderry | ED3 | 58 | 2025-09-05 09:00 | 2025-09-05 18:30 | S | 0.38
Erne | ER2 | 10 | 2025-09-08 08:00 | 2025-09-12 20:00 | S | 4.5
Moneypoint | MP3 | 285 | 2025-09-12 22:00 | 2025-09-24 22:30 | S | 12
Ballylumford | NIBGT1 | 58 | 2025-09-17 | 2025-09-23 | S | 6
Erne | ER4 | 22.5 | 2025-09-22 07:30 | 2025-09-26 20:00 | S | 4.5
Ballylumford | NIBGT2 | 58 | 2025-09-23 | 2025-09-29 | S | 6
Whitegate | WG1 | 444 | 2025-09-26 | 2025-10-07 | S | 11
Tynagh | TYC | 384 | 2025-09-28 20:00 | 2025-10-03 22:00 | S | 5.08
Ballylumford | NIB10 | 94 | 2025-11-13 | 2025-11-16 | S | 3
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10