## Outage Plan EirGrid
2026 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2026 |  |  |  |  | Feb '2026 |  |  |  | Mar '2026 |  |  |  |  | Apr '2026 |  |  |  | May '2026 |  |  |  | Jun '2026 |  |  |  |  | Jul '2026 |  |  |  | Aug '2026 |  |  |  |  | Sep '2026 |  |  |  | Oct '2026 |  |  |  | Nov '2026 |  |  |  |  | Dec '2026
|  | Week | 1 '2026 | 2 '2026 | 3 '2026 | 4 '2026 | 5 '2026 | 6 '2026 | 7 '2026 | 8 '2026 | 9 '2026 | 10 '2026 | 11 '2026 | 12 '2026 | 13 '2026 | 14 '2026 | 15 '2026 | 16 '2026 | 17 '2026 | 18 '2026 | 19 '2026 | 20 '2026 | 21 '2026 | 22 '2026 | 23 '2026 | 24 '2026 | 25 '2026 | 26 '2026 | 27 '2026 | 28 '2026 | 29 '2026 | 30 '2026 | 31 '2026 | 32 '2026 | 33 '2026 | 34 '2026 | 35 '2026 | 36 '2026 | 37 '2026 | 38 '2026 | 39 '2026 | 40 '2026 | 41 '2026 | 42 '2026 | 43 '2026 | 44 '2026 | 45 '2026 | 46 '2026 | 47 '2026 | 48 '2026 | 49 '2026 | 50 '2026 | 51 '2026 | 52 '2026 | 53 '2026
Station | Unit | NPR
Aghada | AD2 | 449 | [15 empty] | S | S | S | S
Aghada | AD3 | 19 | [14 empty] | S
Aghada | AD4 | 75 | [15 empty] | S | S | [24 empty] | S | S
Aghada | AD5 | 75 | [16 empty] | S | S | [24 empty] | S | S
Aghada | AT1 | 90
Aghada | AT2 | 90 | [23 empty] | S
Aghada | AT4 | 90 | [25 empty] | S
Ardnacrusha | AA1 | 21 | [34 empty] | S | S | S | S
Ardnacrusha | AA2 | 22 | [16 empty] | S
Ardnacrusha | AA3 | 19 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [19 empty] | S | S | S | S | S | S | S | S
Aughinish Alumina | EB1 | 25
Banoge | OD1 | 9
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [39 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17 | [15 empty] | S | S | S | S | S | S | S | S
Dublin Bay | DB1 | 415 | [23 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | S | S | S | S | S | S | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Endeco Technologies | EC1 | 53
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 17
Endeco Technologies | EC6 | 4
Enel X | AE1 | 80
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 23
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 5
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [29 empty] | S
Erne | ER2 | 10 | [27 empty] | S
Erne | ER3 | 23 | [37 empty] | S
Erne | ER4 | 23 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
EWIC | EW1 | 500 | [15 empty] | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464 | [18 empty] | S | S | S | S
Huntstown | HN2 | 402 | [31 empty] | S | S | S
Huntstown | HNC | 342 | [22 empty] | S | S | S | S | S
Inchicore | IH1 | 30 | [41 empty] | S
Irishtown | IS2 | 30 | [20 empty] | S
Irishtown | IS3 | 64 | [37 empty] | S
Kilcumber | OE2 | 25
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [16 empty] | S | S | S | S | S
Lee | LE2 | 4 | [12 empty] | S | S |  |  | S | S
Lee | LE3 | 8 | [23 empty] | S | S
Liffey | LI1 | 15 | [15 empty] | S | S | S | S | S | S | S | S | S | S
Liffey | LI2 | 15 | [15 empty] | S | S | S | S | S | S | S | S | S | S
Liffey | LI4 | 4 | [33 empty] | S | S
Liffey | LI5 | 4 | [29 empty] | S | S
Lisdrum | LF1 | 60
Loughtown | GLK | 500
Moneypoint | MP1 | 285 | [21 empty] | S | S
Moneypoint | MP2 | 285 | [18 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [38 empty] | S | S
Moneypoint | MP5 | 1
Northwall | NW8 | 199
Poolbeg | PB4 | 156 | [17 empty] | S | S
Poolbeg | PB5 | 153 | [19 empty] | S | S
Poolbeg | PB6 | 168 | [16 empty] | S
Poolbeg | PB7 | 64 | [32 empty] | S
Poolbeg | PB8 | 75 | [18 empty] | S | S | [26 empty] | S | S
Powerhouse Generation | PG1 | 10
Powerhouse Generation | PG2 | 4
Powerhouse Generation | PG6 | 4
Rhode | RP1 | 52 | [20 empty] | S | S
Rhode | RP2 | 52 | [20 empty] | S | S
Seal Rock | SK3 | 83 | [32 empty] | S
Seal Rock | SK4 | 83 | [26 empty] | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tawnaghmore | TP3 | 52 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [10 empty] | S | S | S
Turlough Hill | TH2 | 73 | [10 empty] | S | S | S
Turlough Hill | TH3 | 73 | [10 empty] | S | S | S
Turlough Hill | TH4 | 73 | [10 empty] | S | S | S
Tynagh | TYC | 404 | [32 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 8
Veolia Alternative Energy | DP2 | 21
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 59
VIOTAS | EE2 | 25
VIOTAS | EE3 | 13
VIOTAS | EE4 | 15
VIOTAS | EE5 | 25
VIOTAS | EE6 | 14
VIOTAS | EE7 | 37
VIOTAS | EE8 | 5
VIOTAS | EE9 | 5
VIOTAS | VS1 | 5
VIOTAS | VS2 | 6
Whitebank | DW1 | 62 | [17 empty] | S | S | S | S
Whitegate | WG1 | 444 | [35 empty] | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2025-12-26 12:00 | 2026-01-01 08:00 | S | 5.83
Erne | ER4 | 23 | 2026-01-01 | 2026-09-20 | S | 262
Seal Rock | SK4 | 83 | 2026-03-02 06:00 | 2026-03-04 18:00 | S | 2.5
Turlough Hill | TH3 | 73 | 2026-03-08 06:00 | 2026-03-27 18:00 | S | 19.5
Turlough Hill | TH4 | 73 | 2026-03-08 06:00 | 2026-03-27 18:00 | S | 19.5
Turlough Hill | TH2 | 73 | 2026-03-08 06:00 | 2026-03-27 18:00 | S | 19.5
Turlough Hill | TH1 | 73 | 2026-03-08 06:00 | 2026-03-27 18:00 | S | 19.5
Lee | LE2 | 4 | 2026-03-23 08:00 | 2026-04-03 20:00 | S | 11.5
Edenderry | ED1 | 118 | 2026-03-26 17:00 | 2026-04-01 08:00 | S | 5.58
Aghada | AT1 | 90 | 2026-03-27 08:00 | 2026-03-31 20:00 | S | 4.5
Whitebank | DW1 | 61.5 | 2026-04-02 | 2026-04-25 23:00 | 26 | 23.92
Tawnaghmore | TP1 | 52 | 2026-04-04 09:00 | 2026-08-31 17:00 | S | 149.33
Tawnaghmore | TP3 | 52 | 2026-04-04 09:00 | 2026-08-31 17:00 | S | 149.33
Seal Rock | SK3 | 83 | 2026-04-06 06:00 | 2026-04-08 18:00 | S | 2.5
Aghada | AD3 | 19 | 2026-04-06 07:00 | 2026-04-11 19:00 | S | 5.5
Ardnacrusha | AA3 | 19 | 2026-04-07 08:00 | 2026-09-18 20:00 | S | 164.5
Poolbeg | PB6 | 168 | 2026-04-10 | 2026-04-23 | 84 | 13
Drybridge | IW1 | 17 | 2026-04-11 | 2026-06-06 | S | 56
Aghada | AD2 | 449 | 2026-04-12 | 2026-05-10 20:00 | S | 28.83
Aghada | AD4 | 75 | 2026-04-13 07:00 | 2026-04-23 19:00 | S | 10.5
Liffey | LI1 | 15 | 2026-04-13 08:00 | 2026-06-19 20:00 | S | 67.5
Liffey | LI2 | 15 | 2026-04-13 08:00 | 2026-06-19 20:00 | S | 67.5
EWIC | EW1 | 500 | 2026-04-13 09:00 | 2026-04-13 21:00 | S | 0.5
EWIC | EW1 | 500 | 2026-04-13 21:00 | 2026-04-19 23:00 | S | 6.08
Inchicore | IH1 | 30 | 2026-04-14 07:00 | 2026-04-17 19:00 | S | 3.5
Lee | LE1 | 15 | 2026-04-20 08:00 | 2026-05-22 20:00 | S | 32.5
Ardnacrusha | AA2 | 22 | 2026-04-20 08:00 | 2026-04-24 20:00 | S | 4.5
Lee | LE2 | 4 | 2026-04-21 08:00 | 2026-04-30 20:00 | S | 9.5
Poolbeg | PB6 | 168 | 2026-04-22 | 2026-04-30 | S | 8
Aghada | AD5 | 75 | 2026-04-23 07:00 | 2026-05-03 19:00 | S | 10.5
Whitebank | DW1 | 61.5 | 2026-04-25 23:00 | 2026-05-25 23:00 | S | 30
Poolbeg | PB6 | 168 | 2026-04-30 | 2026-05-09 20:00 | 84 | 9.83
Poolbeg | PB4 | 156 | 2026-04-30 | 2026-05-09 20:00 | S | 9.83
Great Island | GI4 | 464 | 2026-05-01 | 2026-05-30 | S | 29
Moneypoint | MP2 | 285 | 2026-05-01 22:00 | 2026-08-25 22:00 | S | 116
Poolbeg | PB8 | 75 | 2026-05-05 07:00 | 2026-05-15 19:00 | S | 10.5
Poolbeg | PB5 | 153 | 2026-05-10 | 2026-05-21 20:00 | S | 11.83
Poolbeg | PB6 | 168 | 2026-05-10 | 2026-05-21 20:00 | 84 | 11.83
Ardnacrusha | AA4 | 24 | 2026-05-11 08:00 | 2026-07-03 20:00 | S | 53.5
Seal Rock | SK3 | 83 | 2026-05-11 18:00 | 2026-05-14 18:00 | S | 3
Seal Rock | SK4 | 83 | 2026-05-12 | 2026-05-14 12:00 | S | 2.5
Rhode | RP1 | 52 | 2026-05-15 08:00 | 2026-05-29 20:00 | S | 14.5
Rhode | RP2 | 52 | 2026-05-15 08:00 | 2026-05-29 20:00 | S | 14.5
Irishtown | IS2 | 30 | 2026-05-18 07:00 | 2026-05-23 19:00 | S | 5.5
Moneypoint | MP1 | 285 | 2026-05-22 22:00 | 2026-06-09 22:00 | S | 18
Whitebank | DW1 | 61.5 | 2026-05-25 23:00 | 2026-06-03 23:00 | 26 | 9
Huntstown | HNC | 342 | 2026-06-01 21:00 | 2026-07-07 21:00 | S | 36
Dublin Bay | DB1 | 415 | 2026-06-05 12:00 | 2026-10-03 18:00 | S | 120.25
Aghada | AT2 | 90 | 2026-06-07 08:00 | 2026-06-17 20:00 | S | 10.5
Lee | LE3 | 8 | 2026-06-08 08:00 | 2026-06-19 20:00 | S | 11.5
Moneypoint | MP5 | 1 | 2026-06-15 | 2026-06-18 19:00 | S | 3.75
Northwall | NW8 | 199 | 2026-06-15 08:00 | 2026-06-17 18:00 | 160 | 2.42
Lisdrum | LF1 | 60 | 2026-06-16 08:00 | 2026-06-26 17:00 | 45 | 10.33
Northwall | NW8 | 199 | 2026-06-18 08:00 | 2026-06-20 18:00 | 160 | 2.42
Aghada | AT4 | 90 | 2026-06-19 08:00 | 2026-06-29 20:00 | S | 10.5
Northwall | NW8 | 199 | 2026-06-22 08:00 | 2026-06-24 18:00 | 160 | 2.42
Northwall | NW8 | 199 | 2026-06-25 08:00 | 2026-06-27 18:00 | 160 | 2.42
Seal Rock | SK4 | 83 | 2026-06-29 06:00 | 2026-07-03 18:00 | S | 4.5
Northwall | NW8 | 199 | 2026-06-29 08:00 | 2026-07-01 18:00 | 160 | 2.42
Northwall | NW8 | 199 | 2026-07-02 08:00 | 2026-07-04 18:00 | 160 | 2.42
Edenderry | ED1 | 118 | 2026-07-03 12:00 | 2026-09-25 08:00 | S | 83.83
Cloniffeen | SI1 | 50 | 2026-07-06 08:00 | 2026-07-07 17:00 | S | 1.33
Cloniffeen | SI2 | 50 | 2026-07-06 08:00 | 2026-07-07 17:00 | S | 1.33
Northwall | NW8 | 199 | 2026-07-06 08:00 | 2026-07-07 18:00 | S | 1.42
Erne | ER2 | 10 | 2026-07-06 08:00 | 2026-07-10 20:00 | S | 4.5
Derrycarney | LU1 | 50 | 2026-07-20 08:00 | 2026-07-21 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2026-07-20 08:00 | 2026-07-21 17:00 | S | 1.33
Erne | ER1 | 10 | 2026-07-20 08:00 | 2026-07-24 20:00 | S | 4.5
Liffey | LI5 | 4 | 2026-07-20 08:00 | 2026-07-31 17:00 | S | 11.33
Huntstown | HN2 | 402 | 2026-08-01 | 2026-08-26 00:30 | S | 25
Tynagh | TYC | 404 | 2026-08-07 20:00 | 2026-08-17 23:00 | S | 10.08
Poolbeg | PB7 | 64 | 2026-08-10 | 2026-08-15 19:00 | S | 5.75
Seal Rock | SK3 | 83 | 2026-08-10 06:00 | 2026-08-14 18:00 | S | 4.5
Liffey | LI4 | 4 | 2026-08-17 08:00 | 2026-08-28 17:00 | S | 11.33
Ardnacrusha | AA1 | 21 | 2026-08-24 08:00 | 2026-09-18 20:00 | S | 25.5
Whitegate | WG1 | 444 | 2026-08-29 21:00 | 2026-09-08 21:00 | S | 10
Shannonbridge | SQ1 | 262 | 2026-09-07 08:00 | 2026-09-09 17:00 | 224 | 2.33
Shannonbridge | SQ1 | 262 | 2026-09-10 08:00 | 2026-09-12 17:00 | 224 | 2.33
Irishtown | IS3 | 64 | 2026-09-14 | 2026-09-19 19:00 | S | 5.75
Shannonbridge | SQ1 | 262 | 2026-09-14 08:00 | 2026-09-16 17:00 | 224 | 2.33
Erne | ER3 | 23 | 2026-09-14 08:00 | 2026-09-18 20:00 | S | 4.5
Edenderry | ED3 | 58 | 2026-09-16 08:00 | 2026-09-16 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2026-09-16 08:00 | 2026-09-16 18:00 | S | 0.42
Shannonbridge | SQ1 | 262 | 2026-09-17 | 2026-09-19 | 128 | 2
Shannonbridge | SQ1 | 262 | 2026-09-17 08:00 | 2026-09-19 17:00 | 224 | 2.33
Moneypoint | MP3 | 285 | 2026-09-18 22:00 | 2026-10-06 22:00 | S | 18
Lisdrum | LF1 | 60 | 2026-09-21 08:00 | 2026-09-23 17:00 | S | 2.33
Shannonbridge | SQ1 | 262 | 2026-09-21 08:00 | 2026-09-23 17:00 | 224 | 2.33
Shannonbridge | SQ1 | 262 | 2026-09-24 08:00 | 2026-09-26 17:00 | 224 | 2.33
Corduff | FG2 | 64 | 2026-09-28 | 2026-10-03 19:00 | S | 5.75
Shannonbridge | SQ1 | 262 | 2026-09-28 08:00 | 2026-09-30 17:00 | 224 | 2.33
Shannonbridge | SQ1 | 262 | 2026-10-01 | 2026-10-03 | 128 | 2
Shannonbridge | SQ1 | 262 | 2026-10-03 | 2026-10-03 17:00 | 224 | 0.67
Whitebank | DW1 | 61.5 | 2026-10-05 | 2026-10-09 | 26 | 4
Whitebank | DW1 | 61.5 | 2026-10-12 | 2026-10-16 | 26 | 4
Aghada | AD4 | 75 | 2026-10-12 07:00 | 2026-10-22 19:00 | S | 10.5
Inchicore | IH1 | 30 | 2026-10-12 07:00 | 2026-10-17 19:00 | S | 5.5
Seal Rock | SK4 | 83 | 2026-10-19 06:00 | 2026-10-21 18:00 | S | 2.5
Aghada | AD3 | 19 | 2026-10-19 07:00 | 2026-10-22 19:00 | S | 3.5
Aghada | AD5 | 75 | 2026-10-21 07:00 | 2026-11-01 19:00 | S | 11.5
Irishtown | IS2 | 30 | 2026-11-09 06:00 | 2026-11-12 20:00 | S | 3.58
Poolbeg | PB8 | 75 | 2026-11-16 07:00 | 2026-11-27 19:00 | S | 11.5
Seal Rock | SK3 | 83 | 2026-11-30 06:00 | 2026-12-02 18:00 | S | 2.5
Lisdrum | LF1 | 60 | 2026-12-01 08:00 | 2026-12-01 17:00 | S | 0.33
Lisdrum | LF1 | 60 | 2026-12-01 08:00 | 2026-12-04 17:00 | 45 | 3.33
Edenderry | ED1 | 118 | 2026-12-26 12:00 | 2027-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2026 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2026 |  |  |  |  | Feb '2026 |  |  |  | Mar '2026 |  |  |  |  | Apr '2026 |  |  |  | May '2026 |  |  |  | Jun '2026 |  |  |  |  | Jul '2026 |  |  |  | Aug '2026 |  |  |  |  | Sep '2026 |  |  |  | Oct '2026 |  |  |  | Nov '2026 |  |  |  |  | Dec '2026
|  | Week | 1 '2026 | 2 '2026 | 3 '2026 | 4 '2026 | 5 '2026 | 6 '2026 | 7 '2026 | 8 '2026 | 9 '2026 | 10 '2026 | 11 '2026 | 12 '2026 | 13 '2026 | 14 '2026 | 15 '2026 | 16 '2026 | 17 '2026 | 18 '2026 | 19 '2026 | 20 '2026 | 21 '2026 | 22 '2026 | 23 '2026 | 24 '2026 | 25 '2026 | 26 '2026 | 27 '2026 | 28 '2026 | 29 '2026 | 30 '2026 | 31 '2026 | 32 '2026 | 33 '2026 | 34 '2026 | 35 '2026 | 36 '2026 | 37 '2026 | 38 '2026 | 39 '2026 | 40 '2026 | 41 '2026 | 42 '2026 | 43 '2026 | 44 '2026 | 45 '2026 | 46 '2026 | 47 '2026 | 48 '2026 | 49 '2026 | 50 '2026 | 51 '2026 | 52 '2026 | 53 '2026
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2
Ballydown BESS | NIBLD | 12
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249 | [33 empty] | S
Ballylumford | NIB32 | 249 | [20 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIBGT1 | 58 | [40 empty] | S
Ballylumford | NIBGT2 | 58 | [41 empty] | S
Carmeen | NICMN | 20
Castlereagh BESS | NICSB | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [35 empty] | S | S | S | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [20 empty] | S
Drumkee BESS | NIDK1 | 50
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Kells BESS | NIKEB | 50
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [42 empty] | S
Kilroot | NIKGT4 | 42
Kilroot | NIKGT6 | 350
Kilroot | NIKGT7 | 350
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Mullavilly BESS | NIMZ1 | 50
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Ballylumford | NIB31 | 249 | 2025-03-12 22:00 | 2026-01-03 | 161 | 296.08
Coolkeeragh | NIC30 | 408 | 2026-03-10 | 2026-03-12 | S | 2
Ballylumford | NIB31 | 249 | 2026-04-10 | 2026-04-13 | S | 3
Ballylumford | NIB10 | 94 | 2026-04-24 | 2026-04-28 | S | 4
Ballylumford | NIB32 | 249 | 2026-05-18 | 2026-07-17 | S | 60
Coolkeeragh | NICGT8 | 53 | 2026-05-18 | 2026-05-23 | S | 5
Coolkeeragh | NIC30 | 408 | 2026-06-09 | 2026-06-10 | S | 1
Coolkeeragh | NIC30 | 408 | 2026-06-10 | 2026-06-13 | S | 3
Moyle | MOYLE | 450 | 2026-06-16 | 2026-06-19 | 250 | 3
Ballylumford | NIB32 | 249 | 2026-08-17 | 2026-08-31 | 161 | 14
Ballylumford | NIB31 | 249 | 2026-08-17 | 2026-08-22 | S | 5
Ballylumford | NIB31 | 249 | 2026-08-21 | 2026-08-31 | 161 | 10
Coolkeeragh | NIC30 | 408 | 2026-09-01 | 2026-10-19 | S | 48
Kilroot | NIKGT1 | 29 | 2026-10-01 | 2026-10-04 | S | 3
Kilroot | NIKGT2 | 29 | 2026-10-04 | 2026-10-07 | S | 3
Ballylumford | NIBGT1 | 58 | 2026-10-07 | 2026-10-13 | S | 6
Ballylumford | NIBGT2 | 58 | 2026-10-13 | 2026-10-19 | S | 6
Kilroot | NIKGT3 | 42 | 2026-10-19 | 2026-10-24 | S | 5
Kilroot | NIKGT4 | 42 | 2026-10-24 | 2026-10-29 | S | 5
Ballylumford | NIB10 | 94 | 2026-11-06 | 2026-11-10 | S | 4
Coolkeeragh | NIC30 | 408 | 2026-12-15 | 2026-12-16 | S | 1
Coolkeeragh | NIC30 | 408 | 2026-12-16 | 2026-12-19 | S | 3
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2026 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2026 |  |  |  |  | Feb '2026 |  |  |  | Mar '2026 |  |  |  |  | Apr '2026 |  |  |  | May '2026 |  |  |  | Jun '2026 |  |  |  |  | Jul '2026 |  |  |  | Aug '2026 |  |  |  |  | Sep '2026 |  |  |  | Oct '2026 |  |  |  | Nov '2026 |  |  |  |  | Dec '2026
|  | Week | 1 '2026 | 2 '2026 | 3 '2026 | 4 '2026 | 5 '2026 | 6 '2026 | 7 '2026 | 8 '2026 | 9 '2026 | 10 '2026 | 11 '2026 | 12 '2026 | 13 '2026 | 14 '2026 | 15 '2026 | 16 '2026 | 17 '2026 | 18 '2026 | 19 '2026 | 20 '2026 | 21 '2026 | 22 '2026 | 23 '2026 | 24 '2026 | 25 '2026 | 26 '2026 | 27 '2026 | 28 '2026 | 29 '2026 | 30 '2026 | 31 '2026 | 32 '2026 | 33 '2026 | 34 '2026 | 35 '2026 | 36 '2026 | 37 '2026 | 38 '2026 | 39 '2026 | 40 '2026 | 41 '2026 | 42 '2026 | 43 '2026 | 44 '2026 | 45 '2026 | 46 '2026 | 47 '2026 | 48 '2026 | 49 '2026 | 50 '2026 | 51 '2026 | 52 '2026 | 53 '2026
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2
Aghada | AD2 | 449 | [15 empty] | S | S | S | S
Aghada | AD3 | 19 | [14 empty] | S
Aghada | AD4 | 75 | [15 empty] | S | S | [24 empty] | S | S
Aghada | AD5 | 75 | [16 empty] | S | S | [24 empty] | S | S
Aghada | AT1 | 90
Aghada | AT2 | 90 | [23 empty] | S
Aghada | AT4 | 90 | [25 empty] | S
Ardnacrusha | AA1 | 21 | [34 empty] | S | S | S | S
Ardnacrusha | AA2 | 22 | [16 empty] | S
Ardnacrusha | AA3 | 19 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA4 | 24 | [19 empty] | S | S | S | S | S | S | S | S
Aughinish Alumina | EB1 | 25
Ballydown BESS | NIBLD | 12
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249 | [33 empty] | S
Ballylumford | NIB32 | 249 | [20 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIBGT1 | 58 | [40 empty] | S
Ballylumford | NIBGT2 | 58 | [41 empty] | S
Banoge | OD1 | 9
Carmeen | NICMN | 20
Castlereagh BESS | NICSB | 50
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [35 empty] | S | S | S | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [20 empty] | S
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [39 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drumkee BESS | NIDK1 | 50
Drybridge | IW1 | 17 | [15 empty] | S | S | S | S | S | S | S | S
Dublin Bay | DB1 | 415 | [23 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | S | S | S | S | S | S | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | EC1 | 53
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 17
Endeco Technologies | EC6 | 4
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Enel X | AE1 | 80
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 23
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 5
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | ET1 | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
Erne | ER1 | 10 | [29 empty] | S
Erne | ER2 | 10 | [27 empty] | S
Erne | ER3 | 23 | [37 empty] | S
Erne | ER4 | 23 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
EWIC | EW1 | 500 | [15 empty] | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464 | [18 empty] | S | S | S | S
Huntstown | HN2 | 402 | [31 empty] | S | S | S
Huntstown | HNC | 342 | [22 empty] | S | S | S | S | S
Inchicore | IH1 | 30 | [41 empty] | S
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Irishtown | IS2 | 30 | [20 empty] | S
Irishtown | IS3 | 64 | [37 empty] | S
Kells BESS | NIKEB | 50
Kilcumber | OE2 | 25
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [42 empty] | S
Kilroot | NIKGT4 | 42
Kilroot | NIKGT6 | 350
Kilroot | NIKGT7 | 350
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [16 empty] | S | S | S | S | S
Lee | LE2 | 4 | [12 empty] | S | S |  |  | S | S
Lee | LE3 | 8 | [23 empty] | S | S
Liffey | LI1 | 15 | [15 empty] | S | S | S | S | S | S | S | S | S | S
Liffey | LI2 | 15 | [15 empty] | S | S | S | S | S | S | S | S | S | S
Liffey | LI4 | 4 | [33 empty] | S | S
Liffey | LI5 | 4 | [29 empty] | S | S
Lisahally | NILPS | 18
Lisdrum | LF1 | 60
Loughtown | GLK | 500
Moneypoint | MP1 | 285 | [21 empty] | S | S
Moneypoint | MP2 | 285 | [18 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Moneypoint | MP3 | 285 | [38 empty] | S | S
Moneypoint | MP5 | 1
Moyle | MOYLE | 450
Mullavilly BESS | NIMZ1 | 50
Northwall | NW8 | 199
Poolbeg | PB4 | 156 | [17 empty] | S | S
Poolbeg | PB5 | 153 | [19 empty] | S | S
Poolbeg | PB6 | 168 | [16 empty] | S
Poolbeg | PB7 | 64 | [32 empty] | S
Poolbeg | PB8 | 75 | [18 empty] | S | S | [26 empty] | S | S
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14
Powerhouse Generation | PG1 | 10
Powerhouse Generation | PG2 | 4
Powerhouse Generation | PG6 | 4
Rhode | RP1 | 52 | [20 empty] | S | S
Rhode | RP2 | 52 | [20 empty] | S | S
Seal Rock | SK3 | 83 | [32 empty] | S
Seal Rock | SK4 | 83 | [26 empty] | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tawnaghmore | TP3 | 52 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [10 empty] | S | S | S
Turlough Hill | TH2 | 73 | [10 empty] | S | S | S
Turlough Hill | TH3 | 73 | [10 empty] | S | S | S
Turlough Hill | TH4 | 73 | [10 empty] | S | S | S
Tynagh | TYC | 404 | [32 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 8
Veolia Alternative Energy | DP2 | 21
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 59
VIOTAS | EE2 | 25
VIOTAS | EE3 | 13
VIOTAS | EE4 | 15
VIOTAS | EE5 | 25
VIOTAS | EE6 | 14
VIOTAS | EE7 | 37
VIOTAS | EE8 | 5
VIOTAS | EE9 | 5
VIOTAS | VS1 | 5
VIOTAS | VS2 | 6
Whitebank | DW1 | 62 | [17 empty] | S | S | S | S
Whitegate | WG1 | 444 | [35 empty] | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Ballylumford | NIB31 | 249 | 2025-03-12 22:00 | 2026-01-03 | 161 | 296.08
Edenderry | ED1 | 118 | 2025-12-26 12:00 | 2026-01-01 08:00 | S | 5.83
Erne | ER4 | 23 | 2026-01-01 | 2026-09-20 | S | 262
Seal Rock | SK4 | 83 | 2026-03-02 06:00 | 2026-03-04 18:00 | S | 2.5
Turlough Hill | TH3 | 73 | 2026-03-08 06:00 | 2026-03-27 18:00 | S | 19.5
Turlough Hill | TH4 | 73 | 2026-03-08 06:00 | 2026-03-27 18:00 | S | 19.5
Turlough Hill | TH2 | 73 | 2026-03-08 06:00 | 2026-03-27 18:00 | S | 19.5
Turlough Hill | TH1 | 73 | 2026-03-08 06:00 | 2026-03-27 18:00 | S | 19.5
Coolkeeragh | NIC30 | 408 | 2026-03-10 | 2026-03-12 | S | 2
Lee | LE2 | 4 | 2026-03-23 08:00 | 2026-04-03 20:00 | S | 11.5
Edenderry | ED1 | 118 | 2026-03-26 17:00 | 2026-04-01 08:00 | S | 5.58
Aghada | AT1 | 90 | 2026-03-27 08:00 | 2026-03-31 20:00 | S | 4.5
Whitebank | DW1 | 61.5 | 2026-04-02 | 2026-04-25 23:00 | 26 | 23.92
Tawnaghmore | TP1 | 52 | 2026-04-04 09:00 | 2026-08-31 17:00 | S | 149.33
Tawnaghmore | TP3 | 52 | 2026-04-04 09:00 | 2026-08-31 17:00 | S | 149.33
Seal Rock | SK3 | 83 | 2026-04-06 06:00 | 2026-04-08 18:00 | S | 2.5
Aghada | AD3 | 19 | 2026-04-06 07:00 | 2026-04-11 19:00 | S | 5.5
Ardnacrusha | AA3 | 19 | 2026-04-07 08:00 | 2026-09-18 20:00 | S | 164.5
Poolbeg | PB6 | 168 | 2026-04-10 | 2026-04-23 | 84 | 13
Ballylumford | NIB31 | 249 | 2026-04-10 | 2026-04-13 | S | 3
Drybridge | IW1 | 17 | 2026-04-11 | 2026-06-06 | S | 56
Aghada | AD2 | 449 | 2026-04-12 | 2026-05-10 20:00 | S | 28.83
Aghada | AD4 | 75 | 2026-04-13 07:00 | 2026-04-23 19:00 | S | 10.5
Liffey | LI1 | 15 | 2026-04-13 08:00 | 2026-06-19 20:00 | S | 67.5
Liffey | LI2 | 15 | 2026-04-13 08:00 | 2026-06-19 20:00 | S | 67.5
EWIC | EW1 | 500 | 2026-04-13 09:00 | 2026-04-13 21:00 | S | 0.5
EWIC | EW1 | 500 | 2026-04-13 21:00 | 2026-04-19 23:00 | S | 6.08
Inchicore | IH1 | 30 | 2026-04-14 07:00 | 2026-04-17 19:00 | S | 3.5
Lee | LE1 | 15 | 2026-04-20 08:00 | 2026-05-22 20:00 | S | 32.5
Ardnacrusha | AA2 | 22 | 2026-04-20 08:00 | 2026-04-24 20:00 | S | 4.5
Lee | LE2 | 4 | 2026-04-21 08:00 | 2026-04-30 20:00 | S | 9.5
Poolbeg | PB6 | 168 | 2026-04-22 | 2026-04-30 | S | 8
Aghada | AD5 | 75 | 2026-04-23 07:00 | 2026-05-03 19:00 | S | 10.5
Ballylumford | NIB10 | 94 | 2026-04-24 | 2026-04-28 | S | 4
Whitebank | DW1 | 61.5 | 2026-04-25 23:00 | 2026-05-25 23:00 | S | 30
Poolbeg | PB6 | 168 | 2026-04-30 | 2026-05-09 20:00 | 84 | 9.83
Poolbeg | PB4 | 156 | 2026-04-30 | 2026-05-09 20:00 | S | 9.83
Great Island | GI4 | 464 | 2026-05-01 | 2026-05-30 | S | 29
Moneypoint | MP2 | 285 | 2026-05-01 22:00 | 2026-08-25 22:00 | S | 116
Poolbeg | PB8 | 75 | 2026-05-05 07:00 | 2026-05-15 19:00 | S | 10.5
Poolbeg | PB5 | 153 | 2026-05-10 | 2026-05-21 20:00 | S | 11.83
Poolbeg | PB6 | 168 | 2026-05-10 | 2026-05-21 20:00 | 84 | 11.83
Ardnacrusha | AA4 | 24 | 2026-05-11 08:00 | 2026-07-03 20:00 | S | 53.5
Seal Rock | SK3 | 83 | 2026-05-11 18:00 | 2026-05-14 18:00 | S | 3
Seal Rock | SK4 | 83 | 2026-05-12 | 2026-05-14 12:00 | S | 2.5
Rhode | RP1 | 52 | 2026-05-15 08:00 | 2026-05-29 20:00 | S | 14.5
Rhode | RP2 | 52 | 2026-05-15 08:00 | 2026-05-29 20:00 | S | 14.5
Ballylumford | NIB32 | 249 | 2026-05-18 | 2026-07-17 | S | 60
Coolkeeragh | NICGT8 | 53 | 2026-05-18 | 2026-05-23 | S | 5
Irishtown | IS2 | 30 | 2026-05-18 07:00 | 2026-05-23 19:00 | S | 5.5
Moneypoint | MP1 | 285 | 2026-05-22 22:00 | 2026-06-09 22:00 | S | 18
Whitebank | DW1 | 61.5 | 2026-05-25 23:00 | 2026-06-03 23:00 | 26 | 9
Huntstown | HNC | 342 | 2026-06-01 21:00 | 2026-07-07 21:00 | S | 36
Dublin Bay | DB1 | 415 | 2026-06-05 12:00 | 2026-10-03 18:00 | S | 120.25
Aghada | AT2 | 90 | 2026-06-07 08:00 | 2026-06-17 20:00 | S | 10.5
Lee | LE3 | 8 | 2026-06-08 08:00 | 2026-06-19 20:00 | S | 11.5
Coolkeeragh | NIC30 | 408 | 2026-06-09 | 2026-06-10 | S | 1
Coolkeeragh | NIC30 | 408 | 2026-06-10 | 2026-06-13 | S | 3
Moneypoint | MP5 | 1 | 2026-06-15 | 2026-06-18 19:00 | S | 3.75
Northwall | NW8 | 199 | 2026-06-15 08:00 | 2026-06-17 18:00 | 160 | 2.42
Moyle | MOYLE | 450 | 2026-06-16 | 2026-06-19 | 250 | 3
Lisdrum | LF1 | 60 | 2026-06-16 08:00 | 2026-06-26 17:00 | 45 | 10.33
Northwall | NW8 | 199 | 2026-06-18 08:00 | 2026-06-20 18:00 | 160 | 2.42
Aghada | AT4 | 90 | 2026-06-19 08:00 | 2026-06-29 20:00 | S | 10.5
Northwall | NW8 | 199 | 2026-06-22 08:00 | 2026-06-24 18:00 | 160 | 2.42
Northwall | NW8 | 199 | 2026-06-25 08:00 | 2026-06-27 18:00 | 160 | 2.42
Seal Rock | SK4 | 83 | 2026-06-29 06:00 | 2026-07-03 18:00 | S | 4.5
Northwall | NW8 | 199 | 2026-06-29 08:00 | 2026-07-01 18:00 | 160 | 2.42
Northwall | NW8 | 199 | 2026-07-02 08:00 | 2026-07-04 18:00 | 160 | 2.42
Edenderry | ED1 | 118 | 2026-07-03 12:00 | 2026-09-25 08:00 | S | 83.83
Cloniffeen | SI1 | 50 | 2026-07-06 08:00 | 2026-07-07 17:00 | S | 1.33
Cloniffeen | SI2 | 50 | 2026-07-06 08:00 | 2026-07-07 17:00 | S | 1.33
Northwall | NW8 | 199 | 2026-07-06 08:00 | 2026-07-07 18:00 | S | 1.42
Erne | ER2 | 10 | 2026-07-06 08:00 | 2026-07-10 20:00 | S | 4.5
Derrycarney | LU1 | 50 | 2026-07-20 08:00 | 2026-07-21 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2026-07-20 08:00 | 2026-07-21 17:00 | S | 1.33
Erne | ER1 | 10 | 2026-07-20 08:00 | 2026-07-24 20:00 | S | 4.5
Liffey | LI5 | 4 | 2026-07-20 08:00 | 2026-07-31 17:00 | S | 11.33
Huntstown | HN2 | 402 | 2026-08-01 | 2026-08-26 00:30 | S | 25
Tynagh | TYC | 404 | 2026-08-07 20:00 | 2026-08-17 23:00 | S | 10.08
Poolbeg | PB7 | 64 | 2026-08-10 | 2026-08-15 19:00 | S | 5.75
Seal Rock | SK3 | 83 | 2026-08-10 06:00 | 2026-08-14 18:00 | S | 4.5
Ballylumford | NIB32 | 249 | 2026-08-17 | 2026-08-31 | 161 | 14
Ballylumford | NIB31 | 249 | 2026-08-17 | 2026-08-22 | S | 5
Liffey | LI4 | 4 | 2026-08-17 08:00 | 2026-08-28 17:00 | S | 11.33
Ballylumford | NIB31 | 249 | 2026-08-21 | 2026-08-31 | 161 | 10
Ardnacrusha | AA1 | 21 | 2026-08-24 08:00 | 2026-09-18 20:00 | S | 25.5
Whitegate | WG1 | 444 | 2026-08-29 21:00 | 2026-09-08 21:00 | S | 10
Coolkeeragh | NIC30 | 408 | 2026-09-01 | 2026-10-19 | S | 48
Shannonbridge | SQ1 | 262 | 2026-09-07 08:00 | 2026-09-09 17:00 | 224 | 2.33
Shannonbridge | SQ1 | 262 | 2026-09-10 08:00 | 2026-09-12 17:00 | 224 | 2.33
Irishtown | IS3 | 64 | 2026-09-14 | 2026-09-19 19:00 | S | 5.75
Shannonbridge | SQ1 | 262 | 2026-09-14 08:00 | 2026-09-16 17:00 | 224 | 2.33
Erne | ER3 | 23 | 2026-09-14 08:00 | 2026-09-18 20:00 | S | 4.5
Edenderry | ED3 | 58 | 2026-09-16 08:00 | 2026-09-16 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2026-09-16 08:00 | 2026-09-16 18:00 | S | 0.42
Shannonbridge | SQ1 | 262 | 2026-09-17 | 2026-09-19 | 128 | 2
Shannonbridge | SQ1 | 262 | 2026-09-17 08:00 | 2026-09-19 17:00 | 224 | 2.33
Moneypoint | MP3 | 285 | 2026-09-18 22:00 | 2026-10-06 22:00 | S | 18
Lisdrum | LF1 | 60 | 2026-09-21 08:00 | 2026-09-23 17:00 | S | 2.33
Shannonbridge | SQ1 | 262 | 2026-09-21 08:00 | 2026-09-23 17:00 | 224 | 2.33
Shannonbridge | SQ1 | 262 | 2026-09-24 08:00 | 2026-09-26 17:00 | 224 | 2.33
Corduff | FG2 | 64 | 2026-09-28 | 2026-10-03 19:00 | S | 5.75
Shannonbridge | SQ1 | 262 | 2026-09-28 08:00 | 2026-09-30 17:00 | 224 | 2.33
Shannonbridge | SQ1 | 262 | 2026-10-01 | 2026-10-03 | 128 | 2
Kilroot | NIKGT1 | 29 | 2026-10-01 | 2026-10-04 | S | 3
Shannonbridge | SQ1 | 262 | 2026-10-03 | 2026-10-03 17:00 | 224 | 0.67
Kilroot | NIKGT2 | 29 | 2026-10-04 | 2026-10-07 | S | 3
Whitebank | DW1 | 61.5 | 2026-10-05 | 2026-10-09 | 26 | 4
Ballylumford | NIBGT1 | 58 | 2026-10-07 | 2026-10-13 | S | 6
Whitebank | DW1 | 61.5 | 2026-10-12 | 2026-10-16 | 26 | 4
Aghada | AD4 | 75 | 2026-10-12 07:00 | 2026-10-22 19:00 | S | 10.5
Inchicore | IH1 | 30 | 2026-10-12 07:00 | 2026-10-17 19:00 | S | 5.5
Ballylumford | NIBGT2 | 58 | 2026-10-13 | 2026-10-19 | S | 6
Kilroot | NIKGT3 | 42 | 2026-10-19 | 2026-10-24 | S | 5
Seal Rock | SK4 | 83 | 2026-10-19 06:00 | 2026-10-21 18:00 | S | 2.5
Aghada | AD3 | 19 | 2026-10-19 07:00 | 2026-10-22 19:00 | S | 3.5
Aghada | AD5 | 75 | 2026-10-21 07:00 | 2026-11-01 19:00 | S | 11.5
Kilroot | NIKGT4 | 42 | 2026-10-24 | 2026-10-29 | S | 5
Ballylumford | NIB10 | 94 | 2026-11-06 | 2026-11-10 | S | 4
Irishtown | IS2 | 30 | 2026-11-09 06:00 | 2026-11-12 20:00 | S | 3.58
Poolbeg | PB8 | 75 | 2026-11-16 07:00 | 2026-11-27 19:00 | S | 11.5
Seal Rock | SK3 | 83 | 2026-11-30 06:00 | 2026-12-02 18:00 | S | 2.5
Lisdrum | LF1 | 60 | 2026-12-01 08:00 | 2026-12-01 17:00 | S | 0.33
Lisdrum | LF1 | 60 | 2026-12-01 08:00 | 2026-12-04 17:00 | 45 | 3.33
Coolkeeragh | NIC30 | 408 | 2026-12-15 | 2026-12-16 | S | 1
Coolkeeragh | NIC30 | 408 | 2026-12-16 | 2026-12-19 | S | 3
Edenderry | ED1 | 118 | 2026-12-26 12:00 | 2027-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10