## Outage Plan EirGrid
2025 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2025 |  |  |  |  | Feb '2025 |  |  |  | Mar '2025 |  |  |  |  | Apr '2025 |  |  |  | May '2025 |  |  |  | Jun '2025 |  |  |  |  | Jul '2025 |  |  |  | Aug '2025 |  |  |  | Sep '2025 |  |  |  |  | Oct '2025 |  |  |  | Nov '2025 |  |  |  | Dec '2025
|  | Week | 1 '2025 | 2 '2025 | 3 '2025 | 4 '2025 | 5 '2025 | 6 '2025 | 7 '2025 | 8 '2025 | 9 '2025 | 10 '2025 | 11 '2025 | 12 '2025 | 13 '2025 | 14 '2025 | 15 '2025 | 16 '2025 | 17 '2025 | 18 '2025 | 19 '2025 | 20 '2025 | 21 '2025 | 22 '2025 | 23 '2025 | 24 '2025 | 25 '2025 | 26 '2025 | 27 '2025 | 28 '2025 | 29 '2025 | 30 '2025 | 31 '2025 | 32 '2025 | 33 '2025 | 34 '2025 | 35 '2025 | 36 '2025 | 37 '2025 | 38 '2025 | 39 '2025 | 40 '2025 | 41 '2025 | 42 '2025 | 43 '2025 | 44 '2025 | 45 '2025 | 46 '2025 | 47 '2025 | 48 '2025 | 49 '2025 | 50 '2025 | 51 '2025 | 52 '2025 | 53 '2025
Station | Unit | NPR
Aghada | AD2 | 449 | [13 empty] | F |  |  |  | F | [20 empty] | F | F | F
Aghada | AD3 | 19
Aghada | AD4 | 75 | [15 empty] | F | F | [24 empty] | F
Aghada | AD5 | 75
Aghada | AT1 | 90 | [9 empty] | S | S | S | S | F | F | F | [9 empty] | S
Aghada | AT2 | 90 | [12 empty] | S | S | F | F
Aghada | AT4 | 90 | [13 empty] | S | F | F | F | F | F | F
Ardnacrusha | AA1 | 21 | [23 empty] | F
Ardnacrusha | AA2 | 22 | [17 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | F | F | F | F
Ardnacrusha | AA3 | 19 | [14 empty] | F |  |  |  |  | F | [5 empty] | F
Ardnacrusha | AA4 | 24 | [24 empty] | F | [8 empty] | F | F | F | F | F | F | F
Aughinish Alumina | EB1 | 25
Ballymakaily | IL1 | 18
Ballymakaily | IL2 | 18
Ballymakaily | IL3 | 18
Ballymakaily | IL4 | 18
Ballymakaily | IL5 | 18
Ballymakaily | IL6 | 18
Banoge | OD1 | 9
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [13 empty] | F | [25 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50 | [13 empty] | F | F
Derrycarney | LU2 | 50 | [13 empty] | F | F
Drybridge | IW1 | 17 | [19 empty] | F | F
Dublin Bay | DB1 | 415 | [16 empty] | F | F | F
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [20 empty] | F |  |  |  |  | S | S | S | S
Edenderry | ED3 | 58 | [30 empty] | S | S | S | S | F | F
Edenderry | ED5 | 58 | [30 empty] | S | S | S | S | S
Electric Ireland | EI1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Endeco Technologies | EC1 | 53
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 17
Endeco Technologies | EC6 | 4
Enel X | AE1 | 80
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 23
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 5
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [20 empty] | S
Erne | ER2 | 10 | [14 empty] | S
Erne | ER3 | 23 | [26 empty] | S | S
Erne | ER4 | 23 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
EWIC | EW1 | 500 | [15 empty] | S | F | F | F
Gardnershill | GP1 | 8
Golagh | GO2 | 3 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Gorman | GF1 | 50
Great Island | GI4 | 464 | [11 empty] | F | [7 empty] | F | F | F | F | [10 empty] | F | F | F | F
Huntstown | HN2 | 402 |  |  |  |  | F | F | F | F | F | F | F | F | F | F | F | F | F |  |  |  |  | F | F | F | F
Huntstown | HNC | 342 | [17 empty] | S | S
Inchicore | IH1 | 30 | [41 empty] | S
Irishtown | IS2 | 30 | [20 empty] | S
Irishtown | IS3 | 64 | [20 empty] | S |  |  |  |  | F
Kilcumber | OE2 | 25
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [22 empty] | S | S
Lee | LE2 | 4 | [12 empty] | S | S | [8 empty] | S | S
Lee | LE3 | 8 | [16 empty] | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI1 | 15 | [16 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI2 | 15 | [16 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI4 | 4 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI5 | 4 | [19 empty] | F | F | F
Lisdrum | LF1 | 60
Loughtown | GLK | 500 | S | S | S | S
Moneypoint | MP1 | 285 | [12 empty] | F | F |  |  |  |  | S | S | S | S | S | S | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F | F
Moneypoint | MP2 | 285 |  |  |  |  | F | F | F | F | [5 empty] | F | F | [15 empty] | F
Moneypoint | MP3 | 285 | F | F | F |  |  |  |  | F | [18 empty] | F | F | F | [6 empty] | F | F | F
Moneypoint | MP5 | 1
Northwall | NW8 | 199
Poolbeg | PB4 | 156
Poolbeg | PB5 | 153 | [24 empty] | F | F | [11 empty] | S
Poolbeg | PB6 | 168
Poolbeg | PB7 | 64 | [14 empty] | F | [17 empty] | S |  |  | F | F | F | F | F | F | F | F | F |  |  |  | S
Poolbeg | PB8 | 75 | [46 empty] | S | S
Powerhouse Generation | PG1 | 10
Powerhouse Generation | PG2 | 4
Powerhouse Generation | PG6 | 4
Rhode | RP1 | 52 |  | F | [18 empty] | S | S
Rhode | RP2 | 52 | [20 empty] | S | S
Seal Rock | SK3 | 83 | [28 empty] | S | S | F | F
Seal Rock | SK4 | 83 | [13 empty] | F | F | [8 empty] | S
Shannonbridge | SQ1 | 262 | [8 empty] | F | [20 empty] | F | F | F | F | F | F
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [24 empty] | S | S
Tawnaghmore | TP3 | 52 | [18 empty] | F | [5 empty] | S | S |  |  |  | F
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [12 empty] | S
Turlough Hill | TH2 | 73 | [12 empty] | S
Turlough Hill | TH3 | 73 | [13 empty] | S | S | F | F | F
Turlough Hill | TH4 | 73 | [13 empty] | S | S
Tynagh | TYC | 404 | [17 empty] | F | [16 empty] | F | F | F | F | F | F | F | F | F | F | F
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 8
Veolia Alternative Energy | DP2 | 21
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 59
VIOTAS | EE2 | 25
VIOTAS | EE3 | 13
VIOTAS | EE4 | 15
VIOTAS | EE5 | 25
VIOTAS | EE6 | 14
VIOTAS | EE7 | 37
VIOTAS | EE8 | 5
VIOTAS | EE9 | 5
VIOTAS | VS1 | 5
VIOTAS | VS2 | 6
Whitebank | DW1 | 62 | [6 empty] | F |  | F | F | F | F |  | F
Whitegate | WG1 | 444 | [17 empty] | F | F | [16 empty] | S | F

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Golagh | GO2 | 3 | 2023-04-17 15:30 | 2026-01-01 | F | 989.33
Liffey | LI4 | 4 | 2024-07-30 08:00 | 2025-10-31 17:00 | F | 458.33
Moneypoint | MP3 | 285 | 2024-10-25 22:00 | 2025-01-21 23:00 | F | 88
Rhode | RP1 | 52 | 2024-12-11 22:30 | 2025-01-06 08:00 | 26 | 25.38
Moneypoint | MP1 | 285 | 2024-12-28 08:00 | 2025-01-02 21:00 | F | 5.5
Loughtown | GLK | 500 | 2025-01-01 | 2025-01-29 23:30 | S | 28.96
Moneypoint | MP2 | 285 | 2025-01-01 | 2025-01-07 06:00 | 220 | 6.25
Erne | ER4 | 23 | 2025-01-01 | 2025-10-31 20:00 | F | 303.83
Whitebank | DW1 | 61.5 | 2025-01-02 09:00 | 2025-01-03 23:00 | 59 | 1.58
Irishtown | IS3 | 64 | 2025-01-02 20:00 | 2025-01-03 09:00 | F | 0.5
Moneypoint | MP1 | 285 | 2025-01-02 21:00 | 2025-01-06 17:30 | 220 | 3.83
Edenderry | ED1 | 118 | 2025-01-05 13:00 | 2025-01-06 09:30 | 50 | 0.83
Rhode | RP1 | 52 | 2025-01-06 08:00 | 2025-01-10 13:30 | F | 4.21
Edenderry | ED1 | 118 | 2025-01-06 09:30 | 2025-01-06 11:00 | 41 | 0.04
Whitebank | DW1 | 61.5 | 2025-01-06 10:00 | 2025-01-28 11:00 | 57 | 22
Edenderry | ED1 | 118 | 2025-01-06 11:00 | 2025-01-06 17:30 | 50 | 0.25
Liffey | LI2 | 15 | 2025-01-06 16:30 | 2025-01-07 14:00 | F | 0.88
Aghada | AD2 | 449 | 2025-01-06 17:30 | 2025-01-07 17:00 | F | 0.96
Edenderry | ED1 | 118 | 2025-01-06 17:30 | 2025-01-06 23:30 | 70 | 0.25
Moneypoint | MP1 | 285 | 2025-01-06 17:30 | 2025-01-08 19:30 | 230 | 2.08
Moneypoint | MP2 | 285 | 2025-01-07 06:00 | 2025-01-07 12:00 | F | 0.25
Moneypoint | MP2 | 285 | 2025-01-07 12:00 | 2025-01-07 15:00 | 235 | 0.08
Moneypoint | MP2 | 285 | 2025-01-07 15:00 | 2025-01-20 08:00 | 250 | 12.67
Dunsoghly | DG1 | 50 | 2025-01-08 18:00 | 2025-01-09 15:30 | 23 | 0.88
Moneypoint | MP1 | 285 | 2025-01-08 19:30 | 2025-01-20 16:00 | 240 | 11.83
Whitegate | WG1 | 444 | 2025-01-09 23:00 | 2025-01-13 23:00 | F | 4
Edenderry | ED1 | 118 | 2025-01-11 19:00 | 2025-01-13 18:00 | 50 | 1.92
Poolbeg | PB7 | 64 | 2025-01-12 01:30 | 2025-01-12 12:00 | F | 0.42
Shannonbridge | SQ1 | 262 | 2025-01-13 08:00 | 2025-01-13 18:00 | 160 | 0.42
Poolbeg | PB7 | 64 | 2025-01-13 08:00 | 2025-01-13 14:00 | F | 0.25
Erne | ER2 | 10 | 2025-01-13 08:00 | 2025-01-14 15:30 | F | 1.29
Rhode | RP2 | 52 | 2025-01-13 09:00 | 2025-01-13 15:00 | F | 0.25
Shannonbridge | SQ1 | 262 | 2025-01-14 08:00 | 2025-01-14 18:00 | 160 | 0.42
Inchicore | IH1 | 30 | 2025-01-14 08:00 | 2025-01-31 17:30 | 25 | 17.38
Erne | ER2 | 10 | 2025-01-14 17:30 | 2025-01-15 22:00 | F | 1.17
Lee | LE1 | 15 | 2025-01-15 08:00 | 2025-01-15 17:00 | F | 0.33
Edenderry | ED1 | 118 | 2025-01-15 12:00 | 2025-01-16 04:30 | F | 0.67
Edenderry | ED1 | 118 | 2025-01-16 04:30 | 2025-01-17 16:00 | 41 | 1.46
Corduff | FG2 | 64 | 2025-01-16 08:00 | 2025-01-16 17:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-01-17 08:00 | 2025-01-17 18:00 | 160 | 0.42
Shannonbridge | SQ1 | 262 | 2025-01-18 04:00 | 2025-01-19 20:00 | F | 1.67
Shannonbridge | SQ1 | 262 | 2025-01-20 06:00 | 2025-01-24 17:00 | 160 | 4.42
Moneypoint | MP2 | 285 | 2025-01-20 08:00 | 2025-01-20 13:00 | F | 0.17
Moneypoint | MP2 | 285 | 2025-01-20 13:00 | 2025-01-25 14:00 | 250 | 5
Moneypoint | MP1 | 285 | 2025-01-20 16:00 | 2025-02-12 18:30 | 260 | 23.08
Moneypoint | MP3 | 285 | 2025-01-21 23:00 | 2025-01-27 18:00 | 260 | 5.75
Edenderry | ED3 | 58 | 2025-01-22 16:30 | 2025-01-23 23:00 | F | 1.25
Edenderry | ED3 | 58 | 2025-01-23 23:00 | 2025-01-24 21:00 | F | 0.92
Tawnaghmore | TP1 | 52 | 2025-01-24 06:30 | 2025-01-28 11:00 | F | 4.17
Tawnaghmore | TP3 | 52 | 2025-01-24 06:30 | 2025-01-28 11:00 | F | 4.17
Rhode | RP2 | 52 | 2025-01-24 07:30 | 2025-01-26 16:00 | F | 2.33
Rhode | RP1 | 52 | 2025-01-24 07:30 | 2025-01-26 16:00 | F | 2.33
Corduff | FG2 | 64 | 2025-01-24 19:00 | 2025-01-27 11:00 | F | 2.67
Moneypoint | MP2 | 285 | 2025-01-25 14:00 | 2025-02-23 18:00 | F | 29.17
Edenderry | ED1 | 118 | 2025-01-26 09:00 | 2025-01-26 10:00 | F | 0
Seal Rock | SK4 | 83 | 2025-01-27 06:00 | 2025-01-29 18:00 | S | 2.5
Drybridge | IW1 | 17 | 2025-01-27 08:30 | 2025-01-29 12:30 | F | 2.17
Moneypoint | MP3 | 285 | 2025-01-27 18:00 | 2025-02-06 08:30 | 240 | 9.58
Whitebank | DW1 | 61.5 | 2025-01-28 11:00 | 2025-02-09 21:00 | 53 | 12.42
Dublin Bay | DB1 | 415 | 2025-01-28 21:00 | 2025-01-28 22:00 | F | 0
Huntstown | HN2 | 402 | 2025-01-28 23:00 | 2025-04-27 02:00 | F | 88.08
Shannonbridge | SQ1 | 262 | 2025-01-29 13:00 | 2025-01-29 17:00 | 160 | 0.17
Lee | LE2 | 4 | 2025-01-29 14:00 | 2025-01-29 19:30 | 1 | 0.21
Lee | LE1 | 15 | 2025-01-29 14:00 | 2025-01-29 19:00 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-01-30 07:00 | 2025-01-30 14:00 | 160 | 0.25
Shannonbridge | SQ1 | 262 | 2025-01-30 14:00 | 2025-01-30 18:00 | 160 | 0.17
Aghada | AD2 | 449 | 2025-02-01 06:00 | 2025-02-01 15:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-02-01 07:00 | 2025-02-01 17:00 | 160 | 0.42
Edenderry | ED1 | 118 | 2025-02-01 17:00 | 2025-02-03 00:30 | 50 | 1.29
Shannonbridge | SQ1 | 262 | 2025-02-03 07:00 | 2025-02-03 16:00 | 160 | 0.33
Shannonbridge | SQ1 | 262 | 2025-02-04 06:00 | 2025-02-04 07:30 | F | 0.04
Poolbeg | PB6 | 168 | 2025-02-04 08:00 | 2025-02-05 12:00 | F | 1.17
Tawnaghmore | TP1 | 52 | 2025-02-04 09:30 | 2025-03-05 21:00 | 40 | 29.46
Tawnaghmore | TP3 | 52 | 2025-02-04 09:30 | 2025-02-05 21:00 | 40 | 1.46
Edenderry | ED1 | 118 | 2025-02-04 15:30 | 2025-02-05 05:00 | 41 | 0.54
Liffey | LI2 | 15 | 2025-02-04 16:30 | 2025-02-07 09:00 | F | 2.67
Liffey | LI1 | 15 | 2025-02-04 16:30 | 2025-02-07 09:00 | F | 2.67
Erne | ER2 | 10 | 2025-02-06 08:00 | 2025-02-06 09:30 | F | 0.04
Moneypoint | MP3 | 285 | 2025-02-06 08:30 | 2025-02-16 12:00 | 250 | 10.12
Whitebank | DW1 | 61.5 | 2025-02-06 21:00 | 2025-03-07 15:00 | F | 28.75
Great Island | GI4 | 464 | 2025-02-06 22:30 | 2025-02-07 17:00 | F | 0.75
Lisdrum | LF1 | 60 | 2025-02-07 10:00 | 2025-02-07 14:00 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-02-08 10:00 | 2025-02-08 14:00 | F | 0.17
Poolbeg | PB6 | 168 | 2025-02-09 23:00 | 2025-02-10 03:00 | 88 | 0.17
Poolbeg | PB7 | 64 | 2025-02-10 08:00 | 2025-02-10 17:00 | F | 0.33
Irishtown | IS3 | 64 | 2025-02-10 08:00 | 2025-02-10 17:00 | F | 0.33
Whitebank | DW1 | 61.5 | 2025-02-10 17:00 | 2025-02-13 10:30 | 56 | 2.71
Irishtown | IS3 | 64 | 2025-02-11 08:00 | 2025-02-11 17:00 | F | 0.33
Corduff | FG2 | 64 | 2025-02-12 08:00 | 2025-02-12 17:00 | F | 0.33
Whitegate | WG1 | 444 | 2025-02-12 12:30 | 2025-02-12 16:00 | F | 0.12
Moneypoint | MP1 | 285 | 2025-02-12 18:30 | 2025-03-24 07:00 | 270 | 39.5
Whitebank | DW1 | 61.5 | 2025-02-13 10:30 | 2025-02-13 14:00 | 50 | 0.12
Edenderry | ED1 | 118 | 2025-02-13 13:00 | 2025-02-17 18:00 | F | 4.17
Whitebank | DW1 | 61.5 | 2025-02-13 14:00 | 2025-02-14 09:30 | 56 | 0.79
Lee | LE1 | 15 | 2025-02-14 | 2025-02-14 08:00 | 4 | 0.33
Lee | LE2 | 4 | 2025-02-14 | 2025-02-14 08:00 | 1 | 0.33
Lee | LE3 | 8 | 2025-02-14 | 2025-02-14 08:00 | 4 | 0.33
Whitebank | DW1 | 61.5 | 2025-02-14 16:00 | 2025-02-23 00:30 | 52 | 8.33
Shannonbridge | SQ1 | 262 | 2025-02-15 08:00 | 2025-02-15 13:30 | F | 0.21
Lee | LE3 | 8 | 2025-02-15 08:30 | 2025-02-15 12:00 | F | 0.12
Moneypoint | MP3 | 285 | 2025-02-16 12:00 | 2025-02-27 | F | 10.5
Lee | LE3 | 8 | 2025-02-16 15:00 | 2025-02-17 12:30 | 4 | 0.88
Drybridge | IW1 | 17 | 2025-02-16 20:30 | 2025-02-20 15:30 | F | 3.75
Shannonbridge | SQ1 | 262 | 2025-02-17 10:00 | 2025-02-17 14:00 | 160 | 0.17
Poolbeg | PB7 | 64 | 2025-02-17 10:00 | 2025-02-17 12:30 | F | 0.08
Edenderry | ED1 | 118 | 2025-02-17 18:00 | 2025-02-18 08:00 | 41 | 0.58
Aghada | AD3 | 19 | 2025-02-18 08:00 | 2025-03-07 17:00 | 16 | 17.33
Edenderry | ED1 | 118 | 2025-02-18 08:00 | 2025-02-18 11:00 | 60 | 0.08
Shannonbridge | SQ1 | 262 | 2025-02-18 10:00 | 2025-02-18 14:00 | 160 | 0.17
Whitegate | WG1 | 444 | 2025-02-19 05:00 | 2025-02-19 08:00 | F | 0.08
Edenderry | ED1 | 118 | 2025-02-19 10:30 | 2025-02-19 19:00 | 50 | 0.33
Turlough Hill | TH3 | 73 | 2025-02-20 06:30 | 2025-02-20 08:00 | F | 0.04
Shannonbridge | SQ1 | 262 | 2025-02-20 09:00 | 2025-02-20 13:00 | 192 | 0.17
Ardnacrusha | AA4 | 24 | 2025-02-20 16:30 | 2025-02-20 19:00 | F | 0.08
Whitebank | DW1 | 61.5 | 2025-02-22 23:30 | 2025-02-28 03:00 | 22 | 5.12
Moneypoint | MP2 | 285 | 2025-02-23 18:00 | 2025-03-26 13:00 | 250 | 30.75
Liffey | LI5 | 4 | 2025-02-24 15:00 | 2025-02-24 16:00 | F | 0
Tynagh | TYC | 404 | 2025-02-25 05:30 | 2025-02-27 16:00 | F | 2.42
Shannonbridge | SQ1 | 262 | 2025-02-25 19:30 | 2025-02-26 13:30 | 192 | 0.75
Shannonbridge | SQ1 | 262 | 2025-02-26 13:30 | 2025-03-05 00:30 | F | 6.42
Erne | ER1 | 10 | 2025-02-26 16:00 | 2025-02-26 17:00 | F | 0
Erne | ER3 | 23 | 2025-02-26 16:00 | 2025-02-26 17:00 | F | 0
Erne | ER2 | 10 | 2025-02-26 16:00 | 2025-02-27 11:00 | F | 0.75
Moneypoint | MP3 | 285 | 2025-02-27 | 2025-03-11 12:30 | 250 | 12.5
Whitebank | DW1 | 61.5 | 2025-02-28 03:00 | 2025-03-08 15:00 | 20 | 8.5
Aghada | AT1 | 90 | 2025-03-01 14:00 | 2025-04-02 | S | 31.42
Turlough Hill | TH2 | 73 | 2025-03-01 14:30 | 2025-03-01 20:30 | F | 0.25
Edenderry | ED1 | 118 | 2025-03-01 23:30 | 2025-03-04 12:00 | 41 | 2.5
Turlough Hill | TH1 | 73 | 2025-03-04 02:30 | 2025-03-05 19:00 | F | 1.67
Turlough Hill | TH2 | 73 | 2025-03-04 02:30 | 2025-03-05 19:00 | F | 1.67
Turlough Hill | TH3 | 73 | 2025-03-04 02:30 | 2025-03-05 19:00 | F | 1.67
Turlough Hill | TH4 | 73 | 2025-03-04 02:30 | 2025-03-05 19:00 | F | 1.67
Great Island | GI4 | 464 | 2025-03-04 19:00 | 2025-03-06 17:00 | F | 1.92
Shannonbridge | SQ1 | 262 | 2025-03-05 00:30 | 2025-03-07 17:00 | 96 | 2.67
Irishtown | IS2 | 30 | 2025-03-05 08:00 | 2025-03-06 17:00 | 17 | 1.33
Inchicore | IH1 | 30 | 2025-03-05 08:00 | 2025-03-12 17:00 | 17 | 7.33
Turlough Hill | TH1 | 73 | 2025-03-07 07:00 | 2025-03-07 08:00 | F | 0
Turlough Hill | TH2 | 73 | 2025-03-07 07:00 | 2025-03-07 08:00 | F | 0
Turlough Hill | TH3 | 73 | 2025-03-07 07:00 | 2025-03-07 08:00 | F | 0
Turlough Hill | TH4 | 73 | 2025-03-07 07:00 | 2025-03-07 08:00 | F | 0
Turlough Hill | TH3 | 73 | 2025-03-07 08:00 | 2025-03-07 18:00 | S | 0.42
Turlough Hill | TH1 | 73 | 2025-03-07 08:00 | 2025-03-07 18:00 | S | 0.42
Turlough Hill | TH2 | 73 | 2025-03-07 08:00 | 2025-03-07 18:00 | S | 0.42
Turlough Hill | TH4 | 73 | 2025-03-07 08:00 | 2025-03-07 18:00 | S | 0.42
Shannonbridge | SQ1 | 262 | 2025-03-08 08:00 | 2025-03-08 17:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-03-08 08:00 | 2025-03-08 17:00 | 160 | 0.33
Whitebank | DW1 | 61.5 | 2025-03-08 15:00 | 2025-03-24 06:00 | F | 15.58
Liffey | LI5 | 4 | 2025-03-09 20:00 | 2025-03-10 08:00 | F | 0.5
Shannonbridge | SQ1 | 262 | 2025-03-10 08:00 | 2025-03-10 16:00 | 192 | 0.33
Tarbert | TB5 | 160 | 2025-03-10 08:30 | 2025-03-11 17:00 | F | 1.33
Dublin Bay | DB1 | 415 | 2025-03-11 01:30 | 2025-03-11 08:00 | 239 | 0.25
Moneypoint | MP3 | 285 | 2025-03-11 12:30 | 2025-03-12 19:00 | 210 | 1.25
Tarbert | TB5 | 160 | 2025-03-12 08:30 | 2025-03-13 17:00 | F | 1.33
Moneypoint | MP3 | 285 | 2025-03-12 19:00 | 2025-03-12 23:00 | F | 0.17
Moneypoint | MP3 | 285 | 2025-03-12 23:00 | 2025-03-13 22:30 | 210 | 0.96
Liffey | LI5 | 4 | 2025-03-13 10:30 | 2025-03-14 11:00 | F | 1
Moneypoint | MP3 | 285 | 2025-03-13 22:30 | 2025-03-14 02:00 | F | 0.12
Moneypoint | MP3 | 285 | 2025-03-14 02:00 | 2025-03-18 17:30 | 260 | 4.62
Edenderry | ED1 | 118 | 2025-03-15 00:30 | 2025-03-18 18:00 | 51 | 3.71
Seal Rock | SK4 | 83 | 2025-03-16 11:00 | 2025-03-16 13:00 | F | 0.08
Poolbeg | PB6 | 168 | 2025-03-18 08:00 | 2025-03-18 14:00 | F | 0.25
Great Island | GI4 | 464 | 2025-03-18 17:00 | 2025-03-18 20:00 | F | 0.08
Moneypoint | MP3 | 285 | 2025-03-18 17:30 | 2025-03-21 18:00 | 265 | 3
Great Island | GI4 | 464 | 2025-03-18 22:00 | 2025-03-24 01:00 | F | 5.08
Moneypoint | MP3 | 285 | 2025-03-21 18:00 | 2025-03-23 18:00 | 250 | 2
Dublin Bay | DB1 | 415 | 2025-03-21 20:00 | 2025-03-29 20:00 | F | 8
Aghada | AT2 | 90 | 2025-03-23 | 2025-04-05 | S | 13
Turlough Hill | TH1 | 73 | 2025-03-23 08:00 | 2025-04-01 19:00 | S | 9.42
Turlough Hill | TH2 | 73 | 2025-03-23 08:00 | 2025-04-01 17:00 | S | 9.33
Moneypoint | MP3 | 285 | 2025-03-23 18:00 | 2025-03-31 07:30 | 220 | 7.54
Lee | LE2 | 4 | 2025-03-24 | 2025-04-04 20:00 | S | 11.83
Whitebank | DW1 | 61.5 | 2025-03-24 06:00 | 2025-03-31 09:00 | 27 | 7.08
Seal Rock | SK3 | 83 | 2025-03-24 06:00 | 2025-03-26 18:00 | S | 2.5
Moneypoint | MP1 | 285 | 2025-03-24 07:00 | 2025-03-24 15:30 | F | 0.33
Erne | ER2 | 10 | 2025-03-24 08:00 | 2025-03-25 15:00 | F | 1.25
Erne | ER1 | 10 | 2025-03-24 08:00 | 2025-03-25 15:00 | F | 1.25
Irishtown | IS3 | 64 | 2025-03-24 08:00 | 2025-03-24 11:00 | F | 0.08
Moneypoint | MP1 | 285 | 2025-03-24 15:30 | 2025-03-24 22:30 | 270 | 0.25
Moneypoint | MP1 | 285 | 2025-03-24 22:30 | 2025-03-27 22:00 | 250 | 2.96
Turlough Hill | TH3 | 73 | 2025-03-25 11:00 | 2025-03-25 21:00 | F | 0.42
Turlough Hill | TH4 | 73 | 2025-03-25 11:00 | 2025-03-25 21:00 | F | 0.42
Lisdrum | LF1 | 60 | 2025-03-26 07:30 | 2025-03-26 17:00 | F | 0.38
Erne | ER3 | 23 | 2025-03-26 08:30 | 2025-03-26 16:30 | F | 0.33
Moneypoint | MP2 | 285 | 2025-03-26 13:00 | 2025-03-27 20:30 | F | 1.29
Edenderry | ED1 | 118 | 2025-03-27 07:00 | 2025-03-27 16:30 | 41 | 0.38
Shannonbridge | SQ1 | 262 | 2025-03-27 08:00 | 2025-03-27 16:00 | 224 | 0.33
Erne | ER3 | 23 | 2025-03-27 08:00 | 2025-03-31 08:00 | F | 4
Moneypoint | MP2 | 285 | 2025-03-27 20:30 | 2025-04-01 15:00 | 250 | 4.75
Moneypoint | MP1 | 285 | 2025-03-27 22:00 | 2025-04-06 22:00 | F | 10
Edenderry | ED1 | 118 | 2025-03-28 07:00 | 2025-03-28 15:00 | 41 | 0.33
Shannonbridge | SQ1 | 262 | 2025-03-28 08:00 | 2025-03-28 16:00 | 224 | 0.33
Aghada | AT4 | 90 | 2025-03-28 12:00 | 2025-04-10 | S | 12.5
Turlough Hill | TH3 | 73 | 2025-03-28 17:00 | 2025-04-02 08:00 | F | 4.58
Shannonbridge | SQ1 | 262 | 2025-03-29 08:00 | 2025-03-29 16:00 | 224 | 0.33
Dublin Bay | DB1 | 415 | 2025-03-29 21:30 | 2025-04-01 | F | 2.08
Shannonbridge | SQ1 | 262 | 2025-03-30 08:00 | 2025-03-30 12:00 | 224 | 0.17
Seal Rock | SK4 | 83 | 2025-03-31 01:00 | 2025-04-01 18:00 | F | 1.67
Seal Rock | SK3 | 83 | 2025-03-31 05:30 | 2025-03-31 08:30 | F | 0.08
Moneypoint | MP3 | 285 | 2025-03-31 07:30 | 2025-03-31 14:30 | F | 0.25
Corduff | FG2 | 64 | 2025-03-31 08:00 | 2025-04-05 20:00 | F | 5.5
Tawnaghmore | TP1 | 52 | 2025-03-31 08:30 | 2025-04-08 12:30 | 30 | 8.17
Whitebank | DW1 | 61.5 | 2025-03-31 09:00 | 2025-03-31 16:00 | 24 | 0.25
Moneypoint | MP3 | 285 | 2025-03-31 14:30 | 2025-04-02 05:00 | 250 | 1.58
Whitebank | DW1 | 61.5 | 2025-03-31 16:00 | 2025-04-07 01:00 | F | 6.33
Aghada | AD2 | 449 | 2025-04-01 01:00 | 2025-04-05 21:30 | F | 4.83
Dublin Bay | DB1 | 415 | 2025-04-01 01:30 | 2025-04-02 12:00 | F | 1.42
Moneypoint | MP2 | 285 | 2025-04-01 15:00 | 2025-04-14 17:30 | F | 13.08
Turlough Hill | TH2 | 73 | 2025-04-01 17:00 | 2025-04-02 12:00 | F | 0.75
Seal Rock | SK4 | 83 | 2025-04-01 18:00 | 2025-04-10 23:00 | F | 9.17
Aghada | AT1 | 90 | 2025-04-02 | 2025-04-21 | F | 19
Moneypoint | MP3 | 285 | 2025-04-02 05:00 | 2025-04-02 22:00 | 200 | 0.67
Turlough Hill | TH4 | 73 | 2025-04-02 08:00 | 2025-04-10 13:00 | S | 8.17
Derrycarney | LU1 | 50 | 2025-04-02 08:00 | 2025-04-11 11:30 | F | 9.12
Derrycarney | LU2 | 50 | 2025-04-02 08:00 | 2025-04-11 11:30 | F | 9.12
Turlough Hill | TH3 | 73 | 2025-04-02 08:00 | 2025-04-11 17:00 | S | 9.33
Moneypoint | MP3 | 285 | 2025-04-02 22:00 | 2025-04-26 06:30 | 250 | 23.33
Tarbert | TB5 | 160 | 2025-04-02 22:00 | 2025-04-05 18:30 | F | 2.83
Shannonbridge | SQ1 | 262 | 2025-04-04 08:00 | 2025-04-04 18:00 | 224 | 0.42
Turlough Hill | TH1 | 73 | 2025-04-04 09:30 | 2025-04-04 13:30 | F | 0.17
Aghada | AT2 | 90 | 2025-04-05 | 2025-04-23 | F | 18
Shannonbridge | SQ1 | 262 | 2025-04-05 08:00 | 2025-04-05 18:00 | 192 | 0.42
Tarbert | TB5 | 160 | 2025-04-05 18:30 | 2025-04-12 11:00 | 50 | 6.67
Shannonbridge | SQ1 | 262 | 2025-04-06 08:00 | 2025-04-06 18:00 | 192 | 0.42
Edenderry | ED1 | 118 | 2025-04-06 18:30 | 2025-04-07 16:30 | 90 | 0.92
Moneypoint | MP1 | 285 | 2025-04-06 22:00 | 2025-04-25 20:00 | 250 | 18.92
Whitebank | DW1 | 61.5 | 2025-04-07 01:00 | 2025-04-07 11:00 | 22 | 0.42
Aghada | AD3 | 19 | 2025-04-07 07:00 | 2025-04-10 22:00 | S | 3.58
Shannonbridge | SQ1 | 262 | 2025-04-07 08:00 | 2025-04-07 16:00 | 224 | 0.33
Poolbeg | PB7 | 64 | 2025-04-07 08:00 | 2025-04-11 13:00 | F | 4.17
Erne | ER2 | 10 | 2025-04-07 08:00 | 2025-04-11 20:00 | S | 4.5
Whitebank | DW1 | 61.5 | 2025-04-07 11:00 | 2025-04-09 20:00 | 24 | 2.33
Shannonbridge | SQ1 | 262 | 2025-04-08 08:00 | 2025-04-08 16:00 | 224 | 0.33
Ardnacrusha | AA3 | 19 | 2025-04-08 11:30 | 2025-04-15 15:00 | F | 7.12
Tawnaghmore | TP1 | 52 | 2025-04-08 12:30 | 2025-04-11 19:00 | F | 3.25
Loughtown | GLK | 500 | 2025-04-08 17:00 | 2025-04-10 23:00 | F | 2.25
Rhode | RP2 | 52 | 2025-04-08 20:30 | 2025-04-09 12:00 | 26 | 0.62
Tynagh | TYC | 404 | 2025-04-08 22:00 | 2025-04-09 05:30 | F | 0.29
Edenderry | ED1 | 118 | 2025-04-09 00:30 | 2025-04-09 13:00 | 98 | 0.5
Shannonbridge | SQ1 | 262 | 2025-04-09 08:00 | 2025-04-09 16:00 | 224 | 0.33
Edenderry | ED1 | 118 | 2025-04-09 13:00 | 2025-04-09 16:30 | 55 | 0.12
Whitebank | DW1 | 61.5 | 2025-04-09 22:00 | 2025-04-10 15:00 | F | 0.67
Aghada | AT4 | 90 | 2025-04-10 | 2025-05-03 21:00 | F | 23.83
Whitebank | DW1 | 61.5 | 2025-04-10 15:00 | 2025-04-11 06:00 | 24 | 0.58
Tobertoreen | XT2 | 11 | 2025-04-11 05:30 | 2025-04-11 17:30 | F | 0.5
Turlough Hill | TH3 | 73 | 2025-04-11 17:00 | 2025-05-04 12:00 | F | 22.75
Shannonbridge | SQ1 | 262 | 2025-04-12 08:00 | 2025-04-12 16:00 | 224 | 0.33
Dublin Bay | DB1 | 415 | 2025-04-13 05:00 | 2025-04-13 22:30 | F | 0.71
Shannonbridge | SQ1 | 262 | 2025-04-13 08:00 | 2025-04-13 16:00 | 224 | 0.33
Aghada | AD4 | 75 | 2025-04-14 07:00 | 2025-04-24 20:00 | F | 10.5
Shannonbridge | SQ1 | 262 | 2025-04-14 08:00 | 2025-04-14 16:00 | 224 | 0.33
Inchicore | IH1 | 30 | 2025-04-14 08:00 | 2025-04-14 17:00 | 25 | 0.33
Irishtown | IS3 | 64 | 2025-04-14 08:00 | 2025-04-15 16:00 | F | 1.33
EWIC | EW1 | 500 | 2025-04-14 09:00 | 2025-04-14 21:00 | S | 0.5
Whitebank | DW1 | 61.5 | 2025-04-14 13:00 | 2025-04-14 16:00 | 50 | 0.08
Whitebank | DW1 | 61.5 | 2025-04-14 16:00 | 2025-04-14 18:00 | 40 | 0.08
Moneypoint | MP2 | 285 | 2025-04-14 17:30 | 2025-04-16 23:30 | 250 | 2.25
Whitebank | DW1 | 61.5 | 2025-04-14 18:00 | 2025-04-17 08:00 | 24 | 2.58
EWIC | EW1 | 500 | 2025-04-14 21:00 | 2025-04-18 23:00 | S | 4.08
Inchicore | IH1 | 30 | 2025-04-15 08:00 | 2025-04-15 17:00 | 20 | 0.33
Shannonbridge | SQ1 | 262 | 2025-04-15 08:00 | 2025-04-15 16:00 | 224 | 0.33
Corduff | FG2 | 64 | 2025-04-15 12:00 | 2025-04-15 16:00 | F | 0.17
Aghada | AD2 | 449 | 2025-04-15 13:30 | 2025-04-18 12:00 | F | 2.92
Moneypoint | MP5 | 1 | 2025-04-15 14:00 | 2025-04-18 17:00 | F | 3.08
Ardnacrusha | AA3 | 19 | 2025-04-16 05:30 | 2025-04-16 13:00 | F | 0.29
Shannonbridge | SQ1 | 262 | 2025-04-16 08:00 | 2025-04-16 16:00 | 224 | 0.33
Inchicore | IH1 | 30 | 2025-04-16 08:00 | 2025-04-16 17:00 | 20 | 0.33
Moneypoint | MP2 | 285 | 2025-04-16 23:30 | 2025-04-20 11:00 | F | 3.46
Inchicore | IH1 | 30 | 2025-04-17 08:00 | 2025-04-17 17:00 | 25 | 0.33
Edenderry | ED1 | 118 | 2025-04-17 17:00 | 2025-04-22 14:00 | S | 4.83
Inchicore | IH1 | 30 | 2025-04-18 08:00 | 2025-04-18 17:00 | 25 | 0.33
EWIC | EW1 | 500 | 2025-04-18 23:00 | 2025-05-09 23:00 | F | 21
Moneypoint | MP2 | 285 | 2025-04-20 11:00 | 2025-04-23 17:00 | 250 | 3.25
Aghada | AT1 | 90 | 2025-04-21 09:00 | 2025-04-21 21:00 | F | 0.5
Whitebank | DW1 | 61.5 | 2025-04-21 18:00 | 2025-04-25 | 26 | 3.25
Lee | LE3 | 8 | 2025-04-22 | 2025-05-16 20:00 | S | 24.83
Banoge | OD1 | 9 | 2025-04-22 02:00 | 2025-04-22 23:00 | F | 0.83
Liffey | LI2 | 15 | 2025-04-22 08:00 | 2025-09-05 17:00 | S | 136.33
Liffey | LI1 | 15 | 2025-04-22 08:00 | 2025-09-05 17:00 | S | 136.33
Edenderry | ED1 | 118 | 2025-04-22 14:00 | 2025-04-23 11:00 | 41 | 0.83
Aghada | AT2 | 90 | 2025-04-23 | 2025-05-05 23:00 | 60 | 12.92
Tarbert | TB5 | 160 | 2025-04-23 08:00 | 2025-04-24 17:00 | 50 | 1.33
Dublin Bay | DB1 | 415 | 2025-04-23 09:30 | 2025-05-09 20:00 | F | 16.42
Moneypoint | MP2 | 285 | 2025-04-23 17:00 | 2025-04-23 21:00 | F | 0.17
Moneypoint | MP2 | 285 | 2025-04-23 21:00 | 2025-04-29 14:00 | 250 | 5.67
Aghada | AD5 | 75 | 2025-04-24 07:00 | 2025-04-28 07:00 | 47 | 4
Aghada | AT1 | 90 | 2025-04-24 19:00 | 2025-04-25 16:00 | F | 0.83
Moneypoint | MP1 | 285 | 2025-04-25 20:00 | 2025-05-07 22:00 | 260 | 12.08
Moneypoint | MP3 | 285 | 2025-04-26 06:30 | 2025-04-26 08:00 | F | 0.04
Moneypoint | MP3 | 285 | 2025-04-26 08:00 | 2025-04-30 22:30 | 250 | 4.58
Huntstown | HNC | 342 | 2025-04-26 12:00 | 2025-05-13 17:00 | S | 17.17
Aghada | AD2 | 449 | 2025-04-26 22:00 | 2025-05-07 | F | 10.08
Edenderry | ED1 | 118 | 2025-04-26 23:00 | 2025-04-28 17:00 | 41 | 1.75
Whitegate | WG1 | 444 | 2025-04-27 18:00 | 2025-05-09 23:00 | F | 12.17
Aghada | AD5 | 75 | 2025-04-28 07:00 | 2025-04-29 12:00 | F | 1.17
Ardnacrusha | AA2 | 22 | 2025-04-28 08:00 | 2025-09-19 20:00 | S | 144.5
Edenderry | ED1 | 118 | 2025-04-28 17:00 | 2025-04-29 15:30 | 54 | 0.92
Tynagh | TYC | 404 | 2025-04-28 20:00 | 2025-05-04 23:00 | F | 6.08
Aghada | AD5 | 75 | 2025-04-29 12:00 | 2025-05-06 17:00 | 69 | 7.17
Moneypoint | MP2 | 285 | 2025-04-29 14:00 | 2025-04-29 19:30 | F | 0.21
Aghada | AT1 | 90 | 2025-04-29 19:00 | 2025-04-30 17:00 | F | 0.92
Moneypoint | MP2 | 285 | 2025-04-29 19:30 | 2025-06-16 | 250 | 47.17
Poolbeg | PB7 | 64 | 2025-04-30 17:00 | 2025-05-02 16:00 | F | 1.92
Moneypoint | MP3 | 285 | 2025-04-30 22:30 | 2025-05-05 00:30 | 260 | 4.08
Irishtown | IS2 | 30 | 2025-05-02 19:00 | 2025-05-03 09:30 | F | 0.58
Irishtown | IS3 | 64 | 2025-05-02 21:00 | 2025-05-03 09:30 | F | 0.5
Aghada | AT4 | 90 | 2025-05-03 21:00 | 2025-05-04 17:30 | 60 | 0.83
Aghada | AT4 | 90 | 2025-05-04 17:30 | 2025-05-16 20:00 | F | 12.08
Moneypoint | MP3 | 285 | 2025-05-05 00:30 | 2025-05-06 06:00 | F | 1.21
Aghada | AT2 | 90 | 2025-05-05 23:00 | 2025-05-06 13:00 | F | 0.58
Moneypoint | MP3 | 285 | 2025-05-06 06:00 | 2025-06-12 05:00 | 230 | 36.92
Tawnaghmore | TP3 | 52 | 2025-05-06 09:00 | 2025-05-14 19:00 | F | 8.42
Lisdrum | LF1 | 60 | 2025-05-07 08:00 | 2025-05-07 18:00 | 45 | 0.42
Shannonbridge | SQ1 | 262 | 2025-05-07 08:00 | 2025-05-07 17:00 | 224 | 0.33
Moneypoint | MP1 | 285 | 2025-05-07 22:00 | 2025-07-25 22:00 | S | 79
Lisdrum | LF1 | 60 | 2025-05-08 07:30 | 2025-05-08 17:00 | F | 0.38
Shannonbridge | SQ1 | 262 | 2025-05-08 08:00 | 2025-05-08 17:00 | 224 | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-09 08:00 | 2025-05-09 17:00 | 192 | 0.33
Great Island | GI4 | 464 | 2025-05-10 | 2025-06-09 | F | 30
Drybridge | IW1 | 17 | 2025-05-10 | 2025-05-23 | F | 13
Edenderry | ED1 | 118 | 2025-05-11 06:30 | 2025-05-12 23:00 | 70 | 1.67
Seal Rock | SK3 | 83 | 2025-05-12 06:00 | 2025-05-15 18:00 | S | 3.5
Ardnacrusha | AA3 | 19 | 2025-05-12 08:00 | 2025-05-16 20:00 | F | 4.5
Shannonbridge | SQ1 | 262 | 2025-05-12 08:00 | 2025-05-12 17:00 | 224 | 0.33
Aghada | AD3 | 19 | 2025-05-12 10:00 | 2025-05-12 12:00 | F | 0.08
Aghada | AD2 | 449 | 2025-05-12 14:00 | 2025-05-13 | F | 0.42
Inchicore | IH1 | 30 | 2025-05-12 14:00 | 2025-05-12 16:00 | F | 0.08
Seal Rock | SK4 | 83 | 2025-05-13 | 2025-05-15 12:00 | S | 2.5
Shannonbridge | SQ1 | 262 | 2025-05-13 08:00 | 2025-05-13 17:00 | 224 | 0.33
Poolbeg | PB8 | 75 | 2025-05-13 10:00 | 2025-05-13 12:00 | F | 0.08
Turlough Hill | TH1 | 73 | 2025-05-13 10:00 | 2025-05-13 14:00 | F | 0.17
Irishtown | IS2 | 30 | 2025-05-13 14:00 | 2025-05-13 16:00 | F | 0.08
Huntstown | HNC | 342 | 2025-05-13 17:00 | 2025-05-27 21:00 | 215 | 14.17
Aghada | AD2 | 449 | 2025-05-14 04:30 | 2025-05-14 17:00 | F | 0.5
Liffey | LI5 | 4 | 2025-05-14 08:00 | 2025-05-30 17:00 | F | 16.33
Shannonbridge | SQ1 | 262 | 2025-05-14 08:00 | 2025-05-14 17:00 | 224 | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-15 08:00 | 2025-05-15 17:00 | 224 | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-16 08:00 | 2025-05-16 17:00 | 224 | 0.33
Rhode | RP1 | 52 | 2025-05-16 09:00 | 2025-06-03 17:00 | S | 18.33
Aghada | AD2 | 449 | 2025-05-16 09:30 | 2025-05-16 19:00 | F | 0.38
Lee | LE3 | 8 | 2025-05-16 20:00 | 2025-05-30 20:00 | F | 14
Aghada | AD2 | 449 | 2025-05-17 01:00 | 2025-05-17 14:30 | F | 0.54
EWIC | EW1 | 500 | 2025-05-17 04:00 | 2025-05-21 11:00 | F | 4.25
Turlough Hill | TH2 | 73 | 2025-05-17 07:30 | 2025-05-17 18:00 | F | 0.42
Rhode | RP2 | 52 | 2025-05-17 09:00 | 2025-06-03 17:00 | S | 17.33
Aghada | AD2 | 449 | 2025-05-18 14:00 | 2025-05-20 17:00 | F | 2.08
Irishtown | IS2 | 30 | 2025-05-19 06:00 | 2025-05-24 19:00 | S | 5.5
Irishtown | IS3 | 64 | 2025-05-19 06:00 | 2025-05-24 19:00 | S | 5.5
Erne | ER1 | 10 | 2025-05-19 08:00 | 2025-05-23 20:00 | S | 4.5
Shannonbridge | SQ1 | 262 | 2025-05-19 08:00 | 2025-05-19 17:00 | 224 | 0.33
Poolbeg | PB7 | 64 | 2025-05-19 08:30 | 2025-05-19 17:00 | F | 0.33
Aghada | AT4 | 90 | 2025-05-19 10:00 | 2025-05-19 22:00 | F | 0.5
Shannonbridge | SQ1 | 262 | 2025-05-20 08:00 | 2025-05-20 17:00 | 224 | 0.33
Edenderry | ED1 | 118 | 2025-05-20 08:00 | 2025-05-26 11:30 | F | 6.12
Shannonbridge | SQ1 | 262 | 2025-05-21 08:00 | 2025-05-21 17:00 | 224 | 0.33
Corduff | FG2 | 64 | 2025-05-21 08:30 | 2025-05-21 17:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-22 08:00 | 2025-05-22 17:00 | 224 | 0.33
Tarbert | TB5 | 160 | 2025-05-22 08:00 | 2025-05-22 17:00 | 47 | 0.33
Corduff | FG2 | 64 | 2025-05-22 08:30 | 2025-05-22 17:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-23 08:00 | 2025-05-23 17:00 | 224 | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-26 08:00 | 2025-05-26 17:00 | 224 | 0.33
Whitegate | WG1 | 444 | 2025-05-26 08:30 | 2025-05-26 23:00 | F | 0.58
Edenderry | ED1 | 118 | 2025-05-26 11:30 | 2025-05-26 23:00 | 41 | 0.46
Edenderry | ED1 | 118 | 2025-05-26 23:00 | 2025-05-29 07:00 | F | 2.33
EWIC | EW1 | 500 | 2025-05-27 07:00 | 2025-05-30 | F | 2.67
Shannonbridge | SQ1 | 262 | 2025-05-27 08:00 | 2025-05-27 17:00 | 224 | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-28 08:00 | 2025-05-28 17:00 | 224 | 0.33
Huntstown | HN2 | 402 | 2025-05-28 23:00 | 2025-06-25 17:00 | F | 27.75
Shannonbridge | SQ1 | 262 | 2025-05-29 08:00 | 2025-05-29 17:00 | 224 | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-30 08:00 | 2025-05-30 17:00 | 224 | 0.33
Turlough Hill | TH1 | 73 | 2025-05-30 14:00 | 2025-05-30 16:00 | F | 0.08
Edenderry | ED1 | 118 | 2025-05-30 20:30 | 2025-06-03 08:00 | 90 | 3.46
Lee | LE3 | 8 | 2025-06-02 07:30 | 2025-10-01 16:00 | F | 121.33
Shannonbridge | SQ1 | 262 | 2025-06-02 08:00 | 2025-06-02 17:00 | 224 | 0.33
Lee | LE1 | 15 | 2025-06-03 08:00 | 2025-06-13 20:00 | S | 10.5
Shannonbridge | SQ1 | 262 | 2025-06-03 08:00 | 2025-06-03 17:00 | 224 | 0.33
Irishtown | IS2 | 30 | 2025-06-03 14:00 | 2025-06-03 15:00 | F | 0
Poolbeg | PB4 | 156 | 2025-06-03 22:00 | 2025-06-06 | F | 2.08
Poolbeg | PB6 | 168 | 2025-06-03 22:00 | 2025-06-14 18:00 | 84 | 10.83
Shannonbridge | SQ1 | 262 | 2025-06-04 08:00 | 2025-06-04 17:00 | 224 | 0.33
Lee | LE2 | 4 | 2025-06-04 08:00 | 2025-06-12 20:00 | S | 8.5
Shannonbridge | SQ1 | 262 | 2025-06-05 08:00 | 2025-06-05 17:00 | 224 | 0.33
Huntstown | HNC | 342 | 2025-06-05 09:00 | 2025-06-05 13:30 | 220 | 0.17
Poolbeg | PB4 | 156 | 2025-06-06 | 2025-06-14 20:00 | S | 8.83
Shannonbridge | SQ1 | 262 | 2025-06-06 08:00 | 2025-06-06 17:00 | 224 | 0.33
Irishtown | IS3 | 64 | 2025-06-06 11:30 | 2025-06-09 19:00 | F | 3.29
Ardnacrusha | AA4 | 24 | 2025-06-07 11:00 | 2025-06-09 14:30 | F | 2.12
Edenderry | ED1 | 118 | 2025-06-08 04:00 | 2025-06-20 11:00 | 55 | 12.25
Seal Rock | SK4 | 83 | 2025-06-09 06:00 | 2025-06-13 18:00 | S | 4.5
Ardnacrusha | AA1 | 21 | 2025-06-09 08:00 | 2025-06-13 20:00 | F | 4.5
Shannonbridge | SQ1 | 262 | 2025-06-09 08:00 | 2025-06-09 17:00 | 224 | 0.33
Turlough Hill | TH3 | 73 | 2025-06-09 21:30 | 2025-06-10 13:00 | F | 0.62
Shannonbridge | SQ1 | 262 | 2025-06-10 08:00 | 2025-06-10 17:00 | 224 | 0.33
Shannonbridge | SQ1 | 262 | 2025-06-11 08:00 | 2025-06-11 17:00 | 224 | 0.33
Aghada | AD3 | 19 | 2025-06-11 09:30 | 2025-06-11 12:30 | F | 0.08
Aghada | AD4 | 75 | 2025-06-11 13:30 | 2025-06-11 16:30 | F | 0.08
Moneypoint | MP3 | 285 | 2025-06-12 05:00 | 2025-06-12 10:00 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-06-12 08:00 | 2025-06-12 17:00 | 224 | 0.33
Aghada | AD5 | 75 | 2025-06-12 09:30 | 2025-06-12 12:30 | F | 0.08
Moneypoint | MP3 | 285 | 2025-06-12 10:00 | 2025-06-30 11:30 | 230 | 18.04
Rhode | RP1 | 52 | 2025-06-12 17:00 | 2025-06-14 16:00 | F | 1.92
Shannonbridge | SQ1 | 262 | 2025-06-13 08:00 | 2025-06-13 17:00 | 224 | 0.33
Tawnaghmore | TP1 | 52 | 2025-06-13 09:00 | 2025-06-27 17:00 | S | 14.33
Tawnaghmore | TP3 | 52 | 2025-06-13 09:00 | 2025-06-27 17:00 | S | 14.33
Rhode | RP2 | 52 | 2025-06-14 12:00 | 2025-06-14 15:00 | F | 0.08
Poolbeg | PB6 | 168 | 2025-06-14 18:00 | 2025-06-16 18:00 | F | 2
Poolbeg | PB5 | 153 | 2025-06-15 | 2025-06-28 20:00 | F | 13.83
Aghada | AD2 | 449 | 2025-06-15 18:30 | 2025-06-16 08:00 | F | 0.54
Moneypoint | MP5 | 1 | 2025-06-16 | 2025-06-19 19:00 | S | 3.75
Moneypoint | MP2 | 285 | 2025-06-16 | 2025-06-19 19:00 | F | 3.75
Dunsoghly | DG1 | 50 | 2025-06-16 08:00 | 2025-06-19 17:00 | F | 3.33
Shannonbridge | SQ1 | 262 | 2025-06-16 08:00 | 2025-06-16 17:00 | 224 | 0.33
Liffey | LI5 | 4 | 2025-06-16 08:00 | 2025-06-18 13:00 | F | 2.17
Northwall | NW8 | 199 | 2025-06-16 08:00 | 2025-06-18 18:00 | 160 | 2.42
Poolbeg | PB6 | 168 | 2025-06-16 18:00 | 2025-06-20 20:00 | 84 | 4.08
Whitebank | DW1 | 61.5 | 2025-06-16 21:00 | 2025-06-17 15:00 | F | 0.75
Lisdrum | LF1 | 60 | 2025-06-17 08:00 | 2025-06-17 18:00 | 30 | 0.42
Shannonbridge | SQ1 | 262 | 2025-06-17 08:00 | 2025-06-17 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-18 08:00 | 2025-06-18 18:00 | 30 | 0.42
Shannonbridge | SQ1 | 262 | 2025-06-18 08:00 | 2025-06-18 17:00 | 224 | 0.33
Ardnacrusha | AA4 | 24 | 2025-06-18 08:00 | 2025-06-24 08:30 | F | 6
Ardnacrusha | AA3 | 19 | 2025-06-18 08:00 | 2025-06-18 16:00 | F | 0.33
Lisdrum | LF1 | 60 | 2025-06-19 08:00 | 2025-06-19 18:00 | F | 0.42
Shannonbridge | SQ1 | 262 | 2025-06-19 08:00 | 2025-06-19 17:00 | 224 | 0.33
Northwall | NW8 | 199 | 2025-06-19 08:00 | 2025-06-19 17:00 | 127 | 0.33
Moneypoint | MP2 | 285 | 2025-06-19 19:00 | 2025-06-20 | 250 | 0.17
Moneypoint | MP2 | 285 | 2025-06-20 | 2025-06-25 22:00 | F | 5.92
Northwall | NW8 | 199 | 2025-06-20 08:00 | 2025-06-21 18:00 | 160 | 1.42
Shannonbridge | SQ1 | 262 | 2025-06-20 08:00 | 2025-06-20 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-20 08:00 | 2025-06-20 18:00 | 30 | 0.42
Edenderry | ED1 | 118 | 2025-06-20 11:00 | 2025-07-22 08:00 | S | 31.83
Poolbeg | PB6 | 168 | 2025-06-20 20:00 | 2025-06-28 20:00 | F | 8
Irishtown | IS3 | 64 | 2025-06-21 03:30 | 2025-06-30 17:00 | F | 9.54
Lisdrum | LF1 | 60 | 2025-06-21 08:00 | 2025-06-21 18:00 | 30 | 0.42
Lisdrum | LF1 | 60 | 2025-06-22 08:00 | 2025-06-22 18:00 | 30 | 0.42
Aghada | AT1 | 90 | 2025-06-23 | 2025-06-27 | S | 4
Northwall | NW8 | 199 | 2025-06-23 08:00 | 2025-06-25 18:00 | 160 | 2.42
Lisdrum | LF1 | 60 | 2025-06-23 08:00 | 2025-06-23 18:00 | 30 | 0.42
Shannonbridge | SQ1 | 262 | 2025-06-23 08:00 | 2025-06-23 17:00 | 224 | 0.33
Tynagh | TYC | 404 | 2025-06-23 08:00 | 2025-06-23 17:00 | F | 0.33
Ardnacrusha | AA3 | 19 | 2025-06-23 12:00 | 2025-06-30 14:30 | F | 7.08
Shannonbridge | SQ1 | 262 | 2025-06-24 08:00 | 2025-06-24 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-24 08:00 | 2025-06-24 18:00 | 30 | 0.42
Tarbert | TB5 | 160 | 2025-06-24 08:00 | 2025-06-25 17:00 | F | 1.33
Shannonbridge | SQ1 | 262 | 2025-06-25 08:00 | 2025-06-25 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-25 08:00 | 2025-06-25 18:00 | 30 | 0.42
Liffey | LI5 | 4 | 2025-06-25 09:00 | 2025-06-25 15:00 | F | 0.25
Moneypoint | MP2 | 285 | 2025-06-25 22:00 | 2025-07-05 | 250 | 9.08
Shannonbridge | SQ1 | 262 | 2025-06-26 08:00 | 2025-06-26 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-26 08:00 | 2025-06-26 18:00 | 30 | 0.42
Northwall | NW8 | 199 | 2025-06-26 08:00 | 2025-06-28 18:00 | 160 | 2.42
Whitebank | DW1 | 61.5 | 2025-06-26 21:00 | 2025-06-27 15:00 | F | 0.75
Shannonbridge | SQ1 | 262 | 2025-06-27 08:00 | 2025-06-27 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-27 08:00 | 2025-06-27 18:00 | 30 | 0.42
Aghada | AD2 | 449 | 2025-06-27 22:00 | 2025-06-29 22:00 | F | 2
Aghada | AT1 | 90 | 2025-06-28 15:00 | 2025-06-29 14:30 | F | 0.96
Shannonbridge | SQ1 | 262 | 2025-06-29 08:00 | 2025-06-30 08:00 | 128 | 1
Shannonbridge | SQ1 | 262 | 2025-06-30 08:00 | 2025-06-30 17:00 | 96 | 0.33
Erne | ER3 | 23 | 2025-06-30 08:00 | 2025-07-11 20:00 | S | 11.5
Northwall | NW8 | 199 | 2025-06-30 08:00 | 2025-07-02 18:00 | 160 | 2.42
Inchicore | IH1 | 30 | 2025-06-30 09:30 | 2025-06-30 11:30 | F | 0.08
Moneypoint | MP3 | 285 | 2025-06-30 11:30 | 2025-07-21 18:00 | F | 21.25
Irishtown | IS2 | 30 | 2025-06-30 12:00 | 2025-06-30 14:00 | F | 0.08
Poolbeg | PB8 | 75 | 2025-06-30 14:30 | 2025-06-30 16:30 | F | 0.08
Tynagh | TYC | 404 | 2025-06-30 15:00 | 2025-06-30 20:30 | F | 0.21
Shannonbridge | SQ1 | 262 | 2025-07-01 08:00 | 2025-07-01 17:00 | 96 | 0.33
Aghada | AT4 | 90 | 2025-07-01 18:30 | 2025-07-02 12:00 | F | 0.71
Shannonbridge | SQ1 | 262 | 2025-07-02 08:00 | 2025-07-02 17:00 | 96 | 0.33
Turlough Hill | TH1 | 73 | 2025-07-02 10:00 | 2025-07-02 15:00 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-07-03 08:00 | 2025-07-03 17:00 | 96 | 0.33
Northwall | NW8 | 199 | 2025-07-03 08:00 | 2025-07-05 18:00 | 160 | 2.42
Inchicore | IH1 | 30 | 2025-07-03 09:30 | 2025-07-03 14:30 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-07-04 08:00 | 2025-07-04 17:00 | 96 | 0.33
Irishtown | IS2 | 30 | 2025-07-04 09:30 | 2025-07-04 14:30 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-07-05 08:00 | 2025-07-05 17:00 | 96 | 0.33
Great Island | GI4 | 464 | 2025-07-06 13:30 | 2025-07-06 15:30 | F | 0.08
Cloniffeen | SI1 | 50 | 2025-07-07 08:00 | 2025-07-08 17:00 | S | 1.33
Northwall | NW8 | 199 | 2025-07-07 08:00 | 2025-07-08 18:00 | F | 1.42
Shannonbridge | SQ1 | 262 | 2025-07-07 08:00 | 2025-07-07 17:00 | 96 | 0.33
Cloniffeen | SI2 | 50 | 2025-07-07 08:00 | 2025-07-08 17:00 | S | 1.33
Shannonbridge | SQ1 | 262 | 2025-07-08 08:00 | 2025-07-08 17:00 | 96 | 0.33
Shannonbridge | SQ1 | 262 | 2025-07-09 08:00 | 2025-07-09 17:00 | 96 | 0.33
Shannonbridge | SQ1 | 262 | 2025-07-10 08:00 | 2025-07-10 17:00 | 96 | 0.33
Irishtown | IS3 | 64 | 2025-07-10 14:00 | 2025-07-14 17:00 | F | 4.08
Shannonbridge | SQ1 | 262 | 2025-07-11 08:00 | 2025-07-11 17:00 | 96 | 0.33
Shannonbridge | SQ1 | 262 | 2025-07-12 08:00 | 2025-07-12 17:00 | 96 | 0.33
Seal Rock | SK3 | 83 | 2025-07-13 06:00 | 2025-07-31 18:00 | S | 18.5
Shannonbridge | SQ1 | 262 | 2025-07-13 08:00 | 2025-07-13 17:00 | 96 | 0.33
Tawnaghmore | TP1 | 52 | 2025-07-14 | 2025-07-22 | 30 | 8
Shannonbridge | SQ1 | 262 | 2025-07-14 08:00 | 2025-07-14 17:00 | 96 | 0.33
Aghada | AT4 | 90 | 2025-07-14 10:00 | 2025-07-16 22:00 | F | 2.5
Poolbeg | PB8 | 75 | 2025-07-14 11:00 | 2025-07-14 13:00 | F | 0.08
Shannonbridge | SQ1 | 262 | 2025-07-15 08:00 | 2025-07-15 17:00 | 96 | 0.33
Aghada | AD3 | 19 | 2025-07-15 09:30 | 2025-07-15 14:30 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-07-16 08:00 | 2025-07-16 17:00 | 96 | 0.33
Lisdrum | LF1 | 60 | 2025-07-17 07:00 | 2025-07-17 17:00 | F | 0.42
Shannonbridge | SQ1 | 262 | 2025-07-17 08:00 | 2025-07-17 17:00 | 96 | 0.33
Aghada | AD4 | 75 | 2025-07-17 09:30 | 2025-07-17 14:30 | S | 0.17
Shannonbridge | SQ1 | 262 | 2025-07-18 08:00 | 2025-07-18 17:00 | 96 | 0.33
Aghada | AD5 | 75 | 2025-07-18 09:30 | 2025-07-18 14:30 | F | 0.17
Tynagh | TYC | 404 | 2025-07-19 23:00 | 2025-07-23 23:00 | F | 4
Shannonbridge | SQ1 | 262 | 2025-07-20 08:00 | 2025-08-29 20:00 | F | 40.5
Liffey | LI5 | 4 | 2025-07-20 22:30 | 2025-07-22 08:30 | F | 1.42
Derrycarney | LU1 | 50 | 2025-07-21 08:00 | 2025-07-22 17:00 | S | 1.33
Tawnaghmore | TP3 | 52 | 2025-07-21 08:00 | 2025-07-25 17:00 | F | 4.33
Tarbert | TB5 | 160 | 2025-07-21 08:00 | 2025-07-22 17:00 | 100 | 1.33
Derrycarney | LU2 | 50 | 2025-07-21 08:00 | 2025-07-22 17:00 | S | 1.33
Aghada | AT4 | 90 | 2025-07-22 15:30 | 2025-07-23 18:00 | F | 1.08
Edenderry | ED1 | 118 | 2025-07-22 16:30 | 2025-07-22 22:30 | 41 | 0.25
Derrycarney | LU1 | 50 | 2025-07-22 17:00 | 2025-07-23 17:00 | F | 1
Derrycarney | LU2 | 50 | 2025-07-22 17:00 | 2025-07-23 17:00 | F | 1
Edenderry | ED1 | 118 | 2025-07-23 06:30 | 2025-07-24 14:00 | 41 | 1.29
Tarbert | TB5 | 160 | 2025-07-23 08:00 | 2025-07-24 17:00 | 100 | 1.33
Aghada | AD2 | 449 | 2025-07-23 20:30 | 2025-07-23 21:30 | F | 0
Edenderry | ED1 | 118 | 2025-07-24 14:00 | 2025-07-25 23:00 | 52 | 1.33
Tawnaghmore | TP1 | 52 | 2025-07-25 | 2025-10-01 | 30 | 68
Tarbert | TB5 | 160 | 2025-07-25 08:00 | 2025-07-26 17:00 | 100 | 1.33
Moneypoint | MP1 | 285 | 2025-07-25 22:00 | 2025-10-16 22:00 | F | 83
Edenderry | ED1 | 118 | 2025-07-25 23:00 | 2025-07-29 08:30 | 52 | 3.38
Moneypoint | MP2 | 285 | 2025-07-28 13:00 | 2025-08-01 15:00 | F | 4.08
Edenderry | ED5 | 58 | 2025-07-29 08:00 | 2025-09-01 17:00 | S | 34.33
Edenderry | ED3 | 58 | 2025-07-29 08:00 | 2025-08-28 18:00 | S | 30.42
Edenderry | ED1 | 118 | 2025-07-29 08:30 | 2025-07-30 08:30 | 80 | 1
Turlough Hill | TH1 | 73 | 2025-07-29 23:00 | 2025-07-30 17:00 | F | 0.75
Turlough Hill | TH2 | 73 | 2025-07-29 23:00 | 2025-07-30 17:00 | F | 0.75
Lisdrum | LF1 | 60 | 2025-07-30 08:00 | 2025-07-30 14:00 | F | 0.25
Edenderry | ED1 | 118 | 2025-07-30 08:30 | 2025-07-31 08:30 | 90 | 1
Turlough Hill | TH3 | 73 | 2025-07-30 09:00 | 2025-07-30 17:00 | F | 0.33
Turlough Hill | TH4 | 73 | 2025-07-30 09:00 | 2025-07-30 17:00 | F | 0.33
Edenderry | ED1 | 118 | 2025-07-31 08:30 | 2025-08-03 23:00 | 100 | 3.58
Seal Rock | SK3 | 83 | 2025-07-31 17:00 | 2025-08-10 10:00 | F | 9.67
Dublin Bay | DB1 | 415 | 2025-08-03 15:30 | 2025-08-05 13:00 | 214 | 1.88
Edenderry | ED1 | 118 | 2025-08-04 08:00 | 2025-08-08 23:00 | 50 | 4.58
Tarbert | TB5 | 160 | 2025-08-05 08:00 | 2025-08-06 17:00 | 100 | 1.33
Corduff | FG2 | 64 | 2025-08-06 08:00 | 2025-08-06 17:00 | F | 0.33
Edenderry | ED1 | 118 | 2025-08-08 23:00 | 2025-08-16 04:00 | 100 | 7.17
Poolbeg | PB7 | 64 | 2025-08-11 06:00 | 2025-08-16 19:00 | S | 5.5
Aghada | AT1 | 90 | 2025-08-12 | 2025-08-13 | F | 1
Edenderry | ED1 | 118 | 2025-08-16 04:00 | 2025-08-19 18:00 | F | 3.58
Poolbeg | PB6 | 168 | 2025-08-17 05:30 | 2025-08-20 15:00 | F | 3.38
Aghada | AD2 | 449 | 2025-08-17 23:00 | 2025-08-22 | F | 4
Ardnacrusha | AA4 | 24 | 2025-08-18 08:00 | 2025-10-03 16:00 | F | 46.33
Edenderry | ED1 | 118 | 2025-08-19 18:00 | 2025-08-20 07:00 | 41 | 0.5
Edenderry | ED1 | 118 | 2025-08-20 07:00 | 2025-08-20 11:00 | 41 | 0.17
Edenderry | ED1 | 118 | 2025-08-20 11:00 | 2025-08-21 09:00 | 41 | 0.92
Edenderry | ED1 | 118 | 2025-08-21 09:00 | 2025-09-27 23:00 | 100 | 37.58
Great Island | GI4 | 464 | 2025-08-21 10:00 | 2025-09-15 | F | 24.58
Tynagh | TYC | 404 | 2025-08-22 20:00 | 2025-11-12 08:00 | F | 81.5
Whitebank | DW1 | 61.5 | 2025-08-24 22:00 | 2025-08-25 15:00 | F | 0.67
Whitebank | DW1 | 61.5 | 2025-08-25 15:00 | 2025-08-30 17:00 | 26 | 5.08
Tarbert | TB5 | 160 | 2025-08-26 08:00 | 2025-08-29 18:00 | 100 | 3.42
Erne | ER1 | 10 | 2025-08-28 15:00 | 2025-08-29 16:00 | F | 1
Turlough Hill | TH3 | 73 | 2025-08-28 18:00 | 2025-09-01 16:00 | F | 3.92
Edenderry | ED3 | 58 | 2025-08-28 18:00 | 2025-09-04 15:30 | F | 6.88
Shannonbridge | SQ1 | 262 | 2025-08-29 20:30 | 2025-09-05 17:00 | 128 | 6.83
Whitegate | WG1 | 444 | 2025-08-30 21:00 | 2025-09-09 21:00 | S | 10
Aghada | AT4 | 90 | 2025-09-02 10:00 | 2025-09-05 21:00 | F | 3.42
Seal Rock | SK3 | 83 | 2025-09-02 14:00 | 2025-09-03 18:00 | F | 1.17
Poolbeg | PB7 | 64 | 2025-09-02 18:00 | 2025-09-19 17:00 | F | 16.92
Poolbeg | PB7 | 64 | 2025-09-03 09:00 | 2025-10-31 18:00 | F | 58.33
Erne | ER1 | 10 | 2025-09-04 09:00 | 2025-09-04 16:00 | F | 0.25
Moneypoint | MP3 | 285 | 2025-09-04 16:00 | 2025-09-23 22:00 | F | 19.25
Liffey | LI1 | 15 | 2025-09-05 17:00 | 2025-11-21 17:00 | F | 77
Liffey | LI2 | 15 | 2025-09-05 17:00 | 2025-11-21 17:00 | F | 77
Erne | ER1 | 10 | 2025-09-08 08:00 | 2025-09-08 16:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-09-08 12:00 | 2025-09-08 17:00 | 96 | 0.17
Loughtown | GLK | 500 | 2025-09-08 23:00 | 2025-09-09 11:00 | F | 0.5
Shannonbridge | SQ1 | 262 | 2025-09-09 08:00 | 2025-09-09 14:00 | 96 | 0.25
Shannonbridge | SQ1 | 262 | 2025-09-09 14:00 | 2025-09-09 17:00 | F | 0.08
Whitegate | WG1 | 444 | 2025-09-09 21:00 | 2025-09-16 21:00 | F | 7
Shannonbridge | SQ1 | 262 | 2025-09-10 08:00 | 2025-09-10 17:00 | 96 | 0.33
Shannonbridge | SQ1 | 262 | 2025-09-11 08:00 | 2025-09-11 17:00 | 96 | 0.33
Shannonbridge | SQ1 | 262 | 2025-09-12 08:00 | 2025-09-12 17:00 | 96 | 0.33
Shannonbridge | SQ1 | 262 | 2025-09-12 17:00 | 2025-10-01 12:00 | 128 | 18.75
Poolbeg | PB5 | 153 | 2025-09-14 22:00 | 2025-09-19 20:00 | S | 4.92
Poolbeg | PB6 | 168 | 2025-09-14 22:00 | 2025-09-19 20:00 | 84 | 4.92
Aghada | AT4 | 90 | 2025-09-15 | 2025-09-17 | F | 2
Irishtown | IS3 | 64 | 2025-09-15 06:00 | 2025-09-18 16:00 | S | 3.42
Shannonbridge | SQ1 | 262 | 2025-09-15 08:00 | 2025-09-15 17:00 | 96 | 0.33
Lisdrum | LF1 | 60 | 2025-09-16 08:00 | 2025-09-16 18:00 | 30 | 0.42
Shannonbridge | SQ1 | 262 | 2025-09-16 08:00 | 2025-09-16 17:00 | 96 | 0.33
Lisdrum | LF1 | 60 | 2025-09-17 08:00 | 2025-09-17 09:30 | 30 | 0.04
Shannonbridge | SQ1 | 262 | 2025-09-17 08:00 | 2025-09-17 17:00 | 96 | 0.33
Lisdrum | LF1 | 60 | 2025-09-17 09:30 | 2025-09-17 12:00 | F | 0.08
Lisdrum | LF1 | 60 | 2025-09-17 12:00 | 2025-09-17 18:00 | 30 | 0.25
EWIC | EW1 | 500 | 2025-09-18 07:00 | 2025-09-19 07:00 | F | 1
Huntstown | HN2 | 402 | 2025-09-19 07:30 | 2025-09-19 18:00 | F | 0.42
Tawnaghmore | TP3 | 52 | 2025-09-19 12:00 | 2025-09-30 17:00 | 30 | 11.17
Ardnacrusha | AA2 | 22 | 2025-09-19 20:00 | 2025-10-20 20:00 | F | 31
Poolbeg | PB6 | 168 | 2025-09-19 20:00 | 2025-09-25 13:30 | 84 | 5.71
Cloniffeen | SI1 | 50 | 2025-09-22 08:00 | 2025-09-22 17:00 | F | 0.33
Cloniffeen | SI2 | 50 | 2025-09-22 08:00 | 2025-09-22 17:00 | F | 0.33
Tarbert | TB5 | 160 | 2025-09-22 17:00 | 2025-10-07 17:00 | 50 | 15
Corduff | FG2 | 64 | 2025-09-23 03:30 | 2025-09-23 17:00 | F | 0.54
Lisdrum | LF1 | 60 | 2025-09-23 08:00 | 2025-09-25 17:00 | S | 2.33
Aghada | AD2 | 449 | 2025-09-23 22:00 | 2025-10-16 | F | 22.08
Shannonbridge | SQ1 | 262 | 2025-09-24 08:00 | 2025-09-24 17:00 | 96 | 0.33
Whitebank | DW1 | 61.5 | 2025-09-24 10:30 | 2025-09-24 14:30 | 30 | 0.17
Shannonbridge | SQ1 | 262 | 2025-09-25 08:00 | 2025-09-25 17:00 | F | 0.33
Whitebank | DW1 | 61.5 | 2025-09-25 20:00 | 2025-09-25 22:00 | 50 | 0.08
Moneypoint | MP3 | 285 | 2025-09-26 12:00 | 2025-09-26 23:00 | F | 0.42
Edenderry | ED1 | 118 | 2025-09-27 23:00 | 2025-10-02 | F | 4
Corduff | FG2 | 64 | 2025-09-29 06:00 | 2025-10-04 19:00 | S | 5.5
Shannonbridge | SQ1 | 262 | 2025-09-30 09:00 | 2025-09-30 17:00 | F | 0.33
Turlough Hill | TH3 | 73 | 2025-10-01 10:00 | 2025-10-01 16:00 | F | 0.25
Turlough Hill | TH4 | 73 | 2025-10-01 10:00 | 2025-10-01 16:00 | F | 0.25
Turlough Hill | TH2 | 73 | 2025-10-01 10:00 | 2025-10-01 16:00 | F | 0.25
Turlough Hill | TH1 | 73 | 2025-10-01 10:00 | 2025-10-01 16:00 | F | 0.25
Edenderry | ED1 | 118 | 2025-10-02 | 2025-10-02 23:00 | 41 | 0.92
Gorman | GF1 | 50 | 2025-10-09 09:00 | 2025-10-09 17:00 | F | 0.33
Inchicore | IH1 | 30 | 2025-10-10 13:00 | 2025-10-13 07:00 | 20 | 2.75
Whitebank | DW1 | 61.5 | 2025-10-12 | 2025-10-16 | 26 | 4
Inchicore | IH1 | 30 | 2025-10-13 07:00 | 2025-10-18 19:00 | S | 5.5
Aghada | AD4 | 75 | 2025-10-13 07:00 | 2025-10-18 19:00 | F | 5.5
Aghada | AD5 | 75 | 2025-10-17 13:00 | 2025-10-23 13:00 | F | 6
Aghada | AD4 | 75 | 2025-10-18 19:00 | 2025-10-23 19:00 | 25 | 5
Tarbert | TB5 | 160 | 2025-10-20 08:00 | 2025-10-23 17:00 | 100 | 3.33
Turlough Hill | TH4 | 73 | 2025-10-21 09:00 | 2025-10-21 14:00 | F | 0.17
Turlough Hill | TH3 | 73 | 2025-10-21 09:00 | 2025-10-21 14:00 | F | 0.17
Turlough Hill | TH1 | 73 | 2025-10-21 09:00 | 2025-10-21 14:00 | F | 0.17
Turlough Hill | TH2 | 73 | 2025-10-21 09:00 | 2025-10-21 14:00 | F | 0.17
Aghada | AD5 | 75 | 2025-10-23 13:00 | 2025-11-02 19:30 | 50 | 10.25
Tarbert | TB5 | 160 | 2025-10-24 08:00 | 2025-10-27 17:00 | 100 | 3.33
Tarbert | TB5 | 160 | 2025-10-28 08:00 | 2025-10-31 17:00 | 100 | 3.33
Seal Rock | SK4 | 83 | 2025-11-03 06:00 | 2025-11-05 18:00 | S | 2.5
Dublin Bay | DB1 | 415 | 2025-11-14 22:00 | 2025-11-21 20:00 | F | 6.92
Poolbeg | PB8 | 75 | 2025-11-17 06:00 | 2025-11-28 19:00 | S | 11.5
Poolbeg | PB7 | 64 | 2025-11-24 06:00 | 2025-11-28 19:00 | S | 4.5
Seal Rock | SK3 | 83 | 2025-12-08 06:00 | 2025-12-10 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2025-12-26 12:00 | 2026-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2025 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2025 |  |  |  |  | Feb '2025 |  |  |  | Mar '2025 |  |  |  |  | Apr '2025 |  |  |  | May '2025 |  |  |  | Jun '2025 |  |  |  |  | Jul '2025 |  |  |  | Aug '2025 |  |  |  | Sep '2025 |  |  |  |  | Oct '2025 |  |  |  | Nov '2025 |  |  |  | Dec '2025
|  | Week | 1 '2025 | 2 '2025 | 3 '2025 | 4 '2025 | 5 '2025 | 6 '2025 | 7 '2025 | 8 '2025 | 9 '2025 | 10 '2025 | 11 '2025 | 12 '2025 | 13 '2025 | 14 '2025 | 15 '2025 | 16 '2025 | 17 '2025 | 18 '2025 | 19 '2025 | 20 '2025 | 21 '2025 | 22 '2025 | 23 '2025 | 24 '2025 | 25 '2025 | 26 '2025 | 27 '2025 | 28 '2025 | 29 '2025 | 30 '2025 | 31 '2025 | 32 '2025 | 33 '2025 | 34 '2025 | 35 '2025 | 36 '2025 | 37 '2025 | 38 '2025 | 39 '2025 | 40 '2025 | 41 '2025 | 42 '2025 | 43 '2025 | 44 '2025 | 45 '2025 | 46 '2025 | 47 '2025 | 48 '2025 | 49 '2025 | 50 '2025 | 51 '2025 | 52 '2025 | 53 '2025
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ballydown BESS | NIBLD | 12
Ballylumford | NIB10 | 94 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Ballylumford | NIB31 | 249 | F | F | F | F | F | F | F | F | F | F | [19 empty] | F | F | F
Ballylumford | NIB32 | 249 | F | F | F | F | F | [8 empty] | F | [28 empty] | F
Ballylumford | NIBGT1 | 58 | [29 empty] | F
Ballylumford | NIBGT2 | 58
Carmeen | NICMN | 20
Castlereagh BESS | NICSB | 50 | [19 empty] | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [26 empty] | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F
Coolkeeragh | NICGT8 | 53
Drumkee BESS | NIDK1 | 50
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Kells BESS | NIKEB | 50
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [22 empty] | F | [10 empty] | F
Kilroot | NIKGT4 | 42 | [11 empty] | F | [13 empty] | F
Kilroot | NIKGT6 | 350 | [34 empty] | F
Kilroot | NIKGT7 | 350
Lisahally | NILPS | 18 |  |  | S | [16 empty] | S | S
Moyle | MOYLE | 450 | [27 empty] | S
Mullavilly BESS | NIMZ1 | 50
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Ballylumford | NIB10 | 94 | 2024-12-07 11:00 | 2025-04-11 09:00 | F | 124.92
Ballylumford | NIB32 | 249 | 2024-12-07 11:00 | 2025-02-04 16:00 | F | 59.17
Ballylumford | NIB31 | 249 | 2024-12-07 11:00 | 2025-03-08 19:00 | F | 91.33
Ballylumford | NIBGT2 | 58 | 2024-12-11 09:00 | 2025-01-20 12:00 | 55 | 40.08
Activation Energy | NIAEA | 2 | 2025-01-01 | 2026-01-01 | S | 365
Lisahally | NILPS | 17.6 | 2025-01-12 | 2025-01-18 | S | 6
Coolkeeragh | NICGT8 | 53 | 2025-01-16 07:30 | 2025-01-17 18:30 | 26 | 1.42
Castlereagh BESS | NICSB | 50 | 2025-01-24 06:00 | 2025-01-24 17:00 | F | 0.42
Kilroot | NIKGT7 | 350 | 2025-01-24 06:00 | 2025-01-24 09:30 | F | 0.12
Kells BESS | NIKEB | 50 | 2025-01-24 07:00 | 2025-01-28 | F | 3.67
Lisahally | NILPS | 17.6 | 2025-01-24 09:30 | 2025-01-24 18:00 | F | 0.33
Coolkeeragh | NICGT8 | 53 | 2025-01-24 10:00 | 2025-01-25 15:00 | 26 | 1.17
Lisahally | NILPS | 17.6 | 2025-01-24 20:30 | 2025-01-27 12:30 | F | 2.67
Coolkeeragh | NICGT8 | 53 | 2025-01-28 08:00 | 2025-01-30 18:00 | 26 | 2.42
Carmeen | NICMN | 20 | 2025-02-04 13:30 | 2025-02-04 16:30 | 16 | 0.08
Ballylumford | NIB32 | 249 | 2025-02-04 16:00 | 2025-02-04 19:00 | 161 | 0.08
Ballylumford | NIB32 | 249 | 2025-02-04 19:00 | 2025-02-04 20:00 | F | 0
Ballylumford | NIB32 | 249 | 2025-02-04 20:00 | 2025-04-01 04:00 | 161 | 55.33
Carmeen | NICMN | 20 | 2025-02-05 10:30 | 2025-02-05 16:00 | 18 | 0.21
Kilroot | NIKGT7 | 350 | 2025-02-08 12:00 | 2025-02-08 20:00 | F | 0.33
Lisahally | NILPS | 17.6 | 2025-02-11 03:00 | 2025-02-11 04:30 | F | 0.04
Ballylumford | NIBGT2 | 58 | 2025-02-13 06:00 | 2025-02-13 15:00 | F | 0.33
Ballylumford | NIBGT1 | 58 | 2025-02-13 06:00 | 2025-02-13 15:00 | F | 0.33
Coolkeeragh | NIC30 | 408 | 2025-02-14 20:00 | 2025-02-16 20:00 | S | 2
Castlereagh BESS | NICSB | 50 | 2025-02-18 08:00 | 2025-02-18 16:00 | F | 0.33
Kilroot | NIKGT6 | 350 | 2025-02-20 10:00 | 2025-02-20 12:00 | F | 0.08
Coolkeeragh | NICGT8 | 53 | 2025-02-21 14:00 | 2025-02-21 15:00 | 26 | 0
Lisahally | NILPS | 17.6 | 2025-02-23 | 2025-02-23 01:00 | F | 0
Kilroot | NIKGT4 | 42 | 2025-02-27 07:00 | 2025-02-27 15:00 | F | 0.33
Kells BESS | NIKEB | 50 | 2025-02-27 10:00 | 2025-02-27 11:00 | F | 0
Carmeen | NICMN | 20 | 2025-02-28 11:00 | 2025-02-28 13:00 | 14 | 0.08
Kilroot | NIKGT7 | 350 | 2025-03-01 07:00 | 2025-03-02 18:00 | S | 1.42
Kilroot | NIKGT6 | 350 | 2025-03-05 07:00 | 2025-03-05 17:30 | F | 0.42
Mullavilly BESS | NIMZ1 | 50 | 2025-03-05 14:00 | 2025-03-05 15:00 | F | 0
Lisahally | NILPS | 17.6 | 2025-03-07 08:30 | 2025-03-07 10:30 | F | 0.08
Ballylumford | NIB31 | 249 | 2025-03-08 19:00 | 2025-03-12 02:00 | 161 | 3.25
Ballylumford | NIB31 | 249 | 2025-03-12 02:00 | 2025-03-12 22:00 | F | 0.83
Ballylumford | NIB31 | 249 | 2025-03-12 22:00 | 2025-06-29 05:00 | 161 | 108.25
Kilroot | NIKGT3 | 42 | 2025-03-18 07:00 | 2025-03-18 20:30 | F | 0.54
Lisahally | NILPS | 17.6 | 2025-03-19 02:00 | 2025-03-19 03:30 | F | 0.04
Kilroot | NIKGT4 | 42 | 2025-03-19 07:00 | 2025-03-24 15:00 | F | 5.33
Lisahally | NILPS | 17.6 | 2025-03-19 09:00 | 2025-03-19 11:00 | F | 0.08
Kilroot | NIKGT3 | 42 | 2025-03-19 13:00 | 2025-03-19 14:00 | F | 0
Kilroot | NIKGT3 | 42 | 2025-03-20 11:00 | 2025-03-20 13:30 | F | 0.08
Kilroot | NIKGT3 | 42 | 2025-03-24 10:00 | 2025-03-24 15:00 | F | 0.17
Kilroot | NIKGT4 | 42 | 2025-03-27 12:00 | 2025-03-28 13:30 | F | 1.04
Ballylumford | NIBGT2 | 58 | 2025-03-30 09:00 | 2025-03-30 14:00 | F | 0.17
Ballylumford | NIBGT1 | 58 | 2025-03-30 10:00 | 2025-03-30 13:00 | F | 0.08
Ballylumford | NIBGT1 | 58 | 2025-03-31 07:00 | 2025-03-31 17:00 | F | 0.42
Ballylumford | NIB32 | 249 | 2025-04-01 04:00 | 2025-04-05 09:00 | F | 4.17
Drumkee BESS | NIDK1 | 50 | 2025-04-02 06:00 | 2025-04-02 10:30 | F | 0.17
Ballylumford | NIBGT2 | 58 | 2025-04-04 11:30 | 2025-04-04 16:00 | F | 0.17
Ballylumford | NIB32 | 249 | 2025-04-05 18:00 | 2025-04-05 21:30 | F | 0.12
Ballylumford | NIB10 | 94 | 2025-04-11 13:00 | 2025-04-11 17:30 | F | 0.17
Ballylumford | NIBGT2 | 58 | 2025-04-12 13:00 | 2025-04-12 14:00 | F | 0
Ballylumford | NIBGT1 | 58 | 2025-04-12 13:00 | 2025-04-12 14:00 | F | 0
Ballydown BESS | NIBLD | 12 | 2025-04-14 10:00 | 2025-04-16 19:00 | F | 2.33
Lisahally | NILPS | 17.6 | 2025-04-15 11:30 | 2025-04-15 12:30 | F | 0
Kilroot | NIKGT3 | 42 | 2025-04-17 14:00 | 2025-04-17 15:30 | F | 0.04
Kilroot | NIKGT3 | 42 | 2025-04-18 10:30 | 2025-04-18 12:00 | F | 0.04
Kilroot | NIKGT4 | 42 | 2025-04-18 10:30 | 2025-04-18 12:00 | F | 0.04
Castlereagh BESS | NICSB | 50 | 2025-04-21 07:00 | 2025-04-21 17:00 | 40 | 0.42
Kilroot | NIKGT6 | 350 | 2025-04-24 06:00 | 2025-04-24 20:00 | S | 0.58
Ballylumford | NIBGT1 | 58 | 2025-04-24 08:00 | 2025-04-24 12:00 | 29 | 0.17
Kilroot | NIKGT6 | 350 | 2025-04-24 20:00 | 2025-04-25 16:00 | F | 0.83
Kilroot | NIKGT2 | 29 | 2025-04-29 09:00 | 2025-04-29 10:30 | F | 0.04
Kilroot | NIKGT1 | 29 | 2025-04-29 09:00 | 2025-04-29 10:30 | F | 0.04
Castlereagh BESS | NICSB | 50 | 2025-04-29 11:00 | 2025-04-29 13:30 | S | 0.08
Carmeen | NICMN | 20 | 2025-04-29 13:30 | 2025-05-09 14:30 | 14 | 10
Ballylumford | NIBGT2 | 58 | 2025-05-02 18:30 | 2025-05-07 15:30 | 29 | 4.83
Ballylumford | NIB32 | 249 | 2025-05-07 10:00 | 2025-05-07 11:00 | F | 0
Lisahally | NILPS | 17.6 | 2025-05-09 06:00 | 2025-05-09 07:00 | F | 0
Lisahally | NILPS | 17.6 | 2025-05-11 06:00 | 2025-05-25 18:00 | S | 14.5
Castlereagh BESS | NICSB | 50 | 2025-05-12 08:00 | 2025-05-16 17:00 | S | 4.33
Coolkeeragh | NIC30 | 408 | 2025-05-12 12:00 | 2025-05-13 19:00 | S | 1.25
Kilroot | NIKGT6 | 350 | 2025-05-14 06:00 | 2025-05-16 20:00 | F | 2.58
Drumkee BESS | NIDK1 | 50 | 2025-05-20 20:00 | 2025-05-21 17:30 | F | 0.88
Kilroot | NIKGT7 | 350 | 2025-05-21 06:00 | 2025-05-24 22:00 | F | 3.67
Kilroot | NIKGT6 | 350 | 2025-05-21 07:00 | 2025-05-21 08:30 | F | 0.04
Drumkee BESS | NIDK1 | 50 | 2025-05-21 21:00 | 2025-05-22 19:30 | F | 0.92
Lisahally | NILPS | 17.6 | 2025-05-25 18:00 | 2025-05-29 11:30 | F | 3.71
Kilroot | NIKGT6 | 350 | 2025-05-27 08:00 | 2025-05-30 20:00 | F | 3.5
Kilroot | NIKGT3 | 42 | 2025-06-02 06:00 | 2025-06-06 14:00 | F | 4.33
Kilroot | NIKGT4 | 42 | 2025-06-04 09:00 | 2025-06-05 17:00 | S | 1.33
Kilroot | NIKGT6 | 350 | 2025-06-04 12:00 | 2025-06-04 15:00 | F | 0.08
Kilroot | NIKGT4 | 42 | 2025-06-05 17:00 | 2025-06-06 12:30 | F | 0.79
Ballylumford | NIB32 | 249 | 2025-06-10 19:00 | 2025-06-13 19:00 | S | 3
Castlereagh BESS | NICSB | 50 | 2025-06-11 08:30 | 2025-06-11 11:30 | F | 0.08
Mullavilly BESS | NIMZ1 | 50 | 2025-06-11 16:00 | 2025-06-12 21:00 | F | 1.17
Lisahally | NILPS | 17.6 | 2025-06-11 22:00 | 2025-06-12 16:30 | F | 0.75
Moyle | MOYLE | 450 | 2025-06-12 14:30 | 2025-06-14 23:00 | F | 2.33
Lisahally | NILPS | 17.6 | 2025-06-13 21:00 | 2025-06-15 13:30 | F | 1.67
Kilroot | NIKGT4 | 42 | 2025-06-16 08:00 | 2025-06-16 16:00 | F | 0.33
Ballylumford | NIB10 | 94 | 2025-06-16 19:00 | 2025-06-19 19:00 | S | 3
Carmeen | NICMN | 20 | 2025-06-18 09:00 | 2025-06-18 15:00 | F | 0.25
Ballylumford | NIB10 | 94 | 2025-06-19 19:00 | 2025-06-21 15:30 | F | 1.83
Moyle | MOYLE | 450 | 2025-06-21 17:00 | 2025-06-21 19:00 | 250 | 0.08
Kilroot | NIKGT4 | 42 | 2025-06-23 06:00 | 2025-06-27 13:30 | F | 4.29
Ballydown BESS | NIBLD | 12 | 2025-06-23 09:30 | 2025-06-23 14:30 | F | 0.17
Ballydown BESS | NIBLD | 12 | 2025-06-24 09:00 | 2025-06-24 19:00 | F | 0.42
Ballydown BESS | NIBLD | 12 | 2025-06-25 08:30 | 2025-06-25 17:30 | F | 0.33
Coolkeeragh | NIC30 | 408 | 2025-06-27 | 2025-08-13 | S | 47
Ballylumford | NIB31 | 249 | 2025-06-29 05:00 | 2025-07-02 17:00 | F | 3.5
Kilroot | NIKGT2 | 29 | 2025-07-02 17:30 | 2025-07-03 13:30 | F | 0.83
Ballylumford | NIB31 | 249 | 2025-07-02 20:00 | 2025-07-04 05:30 | 161 | 1.38
Moyle | MOYLE | 450 | 2025-07-06 08:00 | 2025-07-11 23:00 | S | 5.58
Ballylumford | NIB32 | 249 | 2025-07-15 13:30 | 2025-07-15 20:00 | F | 0.25
Ballylumford | NIBGT1 | 58 | 2025-07-17 08:00 | 2025-07-17 16:00 | 29 | 0.33
Ballylumford | NIB31 | 249 | 2025-07-18 14:00 | 2025-08-08 16:00 | F | 21.08
Ballylumford | NIBGT1 | 58 | 2025-07-21 06:00 | 2025-07-26 13:00 | F | 5.25
Kilroot | NIKGT4 | 42 | 2025-07-23 20:30 | 2025-07-23 22:00 | F | 0.04
Kilroot | NIKGT3 | 42 | 2025-07-23 20:30 | 2025-07-23 22:00 | F | 0.04
Ballylumford | NIB10 | 94 | 2025-07-25 10:30 | 2025-07-25 12:30 | 40 | 0.08
Kilroot | NIKGT1 | 29 | 2025-07-31 09:00 | 2025-07-31 10:00 | F | 0
Kilroot | NIKGT2 | 29 | 2025-07-31 11:00 | 2025-07-31 12:00 | F | 0
Kilroot | NIKGT4 | 42 | 2025-08-01 13:00 | 2025-08-01 15:00 | F | 0.08
Coolkeeragh | NICGT8 | 53 | 2025-08-04 11:00 | 2025-08-05 11:30 | 26 | 1
Ballylumford | NIBGT2 | 58 | 2025-08-12 18:30 | 2025-08-12 20:00 | F | 0.04
Ballylumford | NIBGT1 | 58 | 2025-08-12 18:30 | 2025-08-12 20:00 | F | 0.04
Ballylumford | NIBGT1 | 58 | 2025-08-12 22:30 | 2025-08-13 10:00 | F | 0.46
Ballylumford | NIBGT2 | 58 | 2025-08-12 22:30 | 2025-08-13 10:00 | F | 0.46
Coolkeeragh | NIC30 | 408 | 2025-08-13 | 2025-08-19 | F | 6
Kilroot | NIKGT6 | 350 | 2025-08-13 11:00 | 2025-08-13 15:00 | F | 0.17
Coolkeeragh | NIC30 | 408 | 2025-08-19 | 2025-10-15 20:00 | F | 57.83
Kilroot | NIKGT4 | 42 | 2025-08-19 12:30 | 2025-08-19 18:30 | F | 0.25
Kilroot | NIKGT3 | 42 | 2025-08-19 23:00 | 2025-08-20 01:30 | F | 0.08
Kilroot | NIKGT4 | 42 | 2025-08-19 23:30 | 2025-08-22 13:30 | F | 2.58
Kilroot | NIKGT3 | 42 | 2025-08-20 01:30 | 2025-08-24 10:30 | F | 4.33
Kilroot | NIKGT6 | 350 | 2025-08-25 09:00 | 2025-08-29 18:30 | F | 4.38
Kilroot | NIKGT7 | 350 | 2025-08-26 10:00 | 2025-08-26 13:00 | F | 0.08
Moyle | MOYLE | 450 | 2025-08-26 16:30 | 2025-08-26 17:30 | 250 | 0
Ballylumford | NIB10 | 94 | 2025-08-27 08:00 | 2025-08-27 12:00 | F | 0.17
Kilroot | NIKGT3 | 42 | 2025-08-28 20:00 | 2025-08-29 18:30 | F | 0.92
Kilroot | NIKGT4 | 42 | 2025-08-28 20:00 | 2025-08-29 18:30 | F | 0.92
Kilroot | NIKGT3 | 42 | 2025-09-09 12:00 | 2025-09-09 16:30 | F | 0.17
Kilroot | NIKGT4 | 42 | 2025-09-10 12:00 | 2025-09-10 17:30 | F | 0.21
Ballylumford | NIB10 | 94 | 2025-09-15 11:30 | 2025-09-15 18:00 | F | 0.25
Ballylumford | NIB10 | 94 | 2025-09-16 08:30 | 2025-09-16 11:30 | F | 0.08
Kilroot | NIKGT2 | 29 | 2025-10-07 19:00 | 2025-10-08 19:00 | F | 1
Kells BESS | NIKEB | 50 | 2025-10-13 09:00 | 2025-10-14 16:00 | S | 1.25
Kells BESS | NIKEB | 50 | 2025-10-14 16:00 | 2025-10-17 17:00 | S | 3
Ballylumford | NIB32 | 249 | 2025-10-18 19:00 | 2025-10-26 19:00 | F | 8
Castlereagh BESS | NICSB | 50 | 2025-10-20 09:00 | 2025-10-20 17:00 | 40 | 0.33
Mullavilly BESS | NIMZ1 | 50 | 2025-11-01 | 2025-11-03 01:00 | S | 2
Drumkee BESS | NIDK1 | 50 | 2025-11-01 | 2025-11-04 | S | 3
Coolkeeragh | NIC30 | 408 | 2025-12-09 12:00 | 2025-12-12 22:00 | S | 3.42
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2025 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2025 |  |  |  |  | Feb '2025 |  |  |  | Mar '2025 |  |  |  |  | Apr '2025 |  |  |  | May '2025 |  |  |  | Jun '2025 |  |  |  |  | Jul '2025 |  |  |  | Aug '2025 |  |  |  | Sep '2025 |  |  |  |  | Oct '2025 |  |  |  | Nov '2025 |  |  |  | Dec '2025
|  | Week | 1 '2025 | 2 '2025 | 3 '2025 | 4 '2025 | 5 '2025 | 6 '2025 | 7 '2025 | 8 '2025 | 9 '2025 | 10 '2025 | 11 '2025 | 12 '2025 | 13 '2025 | 14 '2025 | 15 '2025 | 16 '2025 | 17 '2025 | 18 '2025 | 19 '2025 | 20 '2025 | 21 '2025 | 22 '2025 | 23 '2025 | 24 '2025 | 25 '2025 | 26 '2025 | 27 '2025 | 28 '2025 | 29 '2025 | 30 '2025 | 31 '2025 | 32 '2025 | 33 '2025 | 34 '2025 | 35 '2025 | 36 '2025 | 37 '2025 | 38 '2025 | 39 '2025 | 40 '2025 | 41 '2025 | 42 '2025 | 43 '2025 | 44 '2025 | 45 '2025 | 46 '2025 | 47 '2025 | 48 '2025 | 49 '2025 | 50 '2025 | 51 '2025 | 52 '2025 | 53 '2025
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Aghada | AD2 | 449 | [13 empty] | F |  |  |  | F | [20 empty] | F | F | F
Aghada | AD3 | 19
Aghada | AD4 | 75 | [15 empty] | F | F | [24 empty] | F
Aghada | AD5 | 75
Aghada | AT1 | 90 | [9 empty] | S | S | S | S | F | F | F | [9 empty] | S
Aghada | AT2 | 90 | [12 empty] | S | S | F | F
Aghada | AT4 | 90 | [13 empty] | S | F | F | F | F | F | F
Ardnacrusha | AA1 | 21 | [23 empty] | F
Ardnacrusha | AA2 | 22 | [17 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | F | F | F | F
Ardnacrusha | AA3 | 19 | [14 empty] | F |  |  |  |  | F | [5 empty] | F
Ardnacrusha | AA4 | 24 | [24 empty] | F | [8 empty] | F | F | F | F | F | F | F
Aughinish Alumina | EB1 | 25
Ballydown BESS | NIBLD | 12
Ballylumford | NIB10 | 94 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Ballylumford | NIB31 | 249 | F | F | F | F | F | F | F | F | F | F | [19 empty] | F | F | F
Ballylumford | NIB32 | 249 | F | F | F | F | F | [8 empty] | F | [28 empty] | F
Ballylumford | NIBGT1 | 58 | [29 empty] | F
Ballylumford | NIBGT2 | 58
Ballymakaily | IL1 | 18
Ballymakaily | IL2 | 18
Ballymakaily | IL3 | 18
Ballymakaily | IL4 | 18
Ballymakaily | IL5 | 18
Ballymakaily | IL6 | 18
Banoge | OD1 | 9
Carmeen | NICMN | 20
Castlereagh BESS | NICSB | 50 | [19 empty] | S
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [26 empty] | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F
Coolkeeragh | NICGT8 | 53
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [13 empty] | F | [25 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50 | [13 empty] | F | F
Derrycarney | LU2 | 50 | [13 empty] | F | F
Drumkee BESS | NIDK1 | 50
Drybridge | IW1 | 17 | [19 empty] | F | F
Dublin Bay | DB1 | 415 | [16 empty] | F | F | F
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [20 empty] | F |  |  |  |  | S | S | S | S
Edenderry | ED3 | 58 | [30 empty] | S | S | S | S | F | F
Edenderry | ED5 | 58 | [30 empty] | S | S | S | S | S
Electric Ireland | EI1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | EC1 | 53
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 17
Endeco Technologies | EC6 | 4
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Enel X | AE1 | 80
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 23
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 5
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | ET1 | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
Erne | ER1 | 10 | [20 empty] | S
Erne | ER2 | 10 | [14 empty] | S
Erne | ER3 | 23 | [26 empty] | S | S
Erne | ER4 | 23 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
EWIC | EW1 | 500 | [15 empty] | S | F | F | F
Gardnershill | GP1 | 8
Golagh | GO2 | 3 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Gorman | GF1 | 50
Great Island | GI4 | 464 | [11 empty] | F | [7 empty] | F | F | F | F | [10 empty] | F | F | F | F
Huntstown | HN2 | 402 |  |  |  |  | F | F | F | F | F | F | F | F | F | F | F | F | F |  |  |  |  | F | F | F | F
Huntstown | HNC | 342 | [17 empty] | S | S
Inchicore | IH1 | 30 | [41 empty] | S
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Irishtown | IS2 | 30 | [20 empty] | S
Irishtown | IS3 | 64 | [20 empty] | S |  |  |  |  | F
Kells BESS | NIKEB | 50
Kilcumber | OE2 | 25
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [22 empty] | F | [10 empty] | F
Kilroot | NIKGT4 | 42 | [11 empty] | F | [13 empty] | F
Kilroot | NIKGT6 | 350 | [34 empty] | F
Kilroot | NIKGT7 | 350
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [22 empty] | S | S
Lee | LE2 | 4 | [12 empty] | S | S | [8 empty] | S | S
Lee | LE3 | 8 | [16 empty] | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI1 | 15 | [16 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI2 | 15 | [16 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI4 | 4 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Liffey | LI5 | 4 | [19 empty] | F | F | F
Lisahally | NILPS | 18 |  |  | S | [16 empty] | S | S
Lisdrum | LF1 | 60
Loughtown | GLK | 500 | S | S | S | S
Moneypoint | MP1 | 285 | [12 empty] | F | F |  |  |  |  | S | S | S | S | S | S | S | S | S | S | S | S | F | F | F | F | F | F | F | F | F | F | F | F
Moneypoint | MP2 | 285 |  |  |  |  | F | F | F | F | [5 empty] | F | F | [15 empty] | F
Moneypoint | MP3 | 285 | F | F | F |  |  |  |  | F | [18 empty] | F | F | F | [6 empty] | F | F | F
Moneypoint | MP5 | 1
Moyle | MOYLE | 450 | [27 empty] | S
Mullavilly BESS | NIMZ1 | 50
Northwall | NW8 | 199
Poolbeg | PB4 | 156
Poolbeg | PB5 | 153 | [24 empty] | F | F | [11 empty] | S
Poolbeg | PB6 | 168
Poolbeg | PB7 | 64 | [14 empty] | F | [17 empty] | S |  |  | F | F | F | F | F | F | F | F | F |  |  |  | S
Poolbeg | PB8 | 75 | [46 empty] | S | S
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14
Powerhouse Generation | PG1 | 10
Powerhouse Generation | PG2 | 4
Powerhouse Generation | PG6 | 4
Rhode | RP1 | 52 |  | F | [18 empty] | S | S
Rhode | RP2 | 52 | [20 empty] | S | S
Seal Rock | SK3 | 83 | [28 empty] | S | S | F | F
Seal Rock | SK4 | 83 | [13 empty] | F | F | [8 empty] | S
Shannonbridge | SQ1 | 262 | [8 empty] | F | [20 empty] | F | F | F | F | F | F
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [24 empty] | S | S
Tawnaghmore | TP3 | 52 | [18 empty] | F | [5 empty] | S | S |  |  |  | F
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [12 empty] | S
Turlough Hill | TH2 | 73 | [12 empty] | S
Turlough Hill | TH3 | 73 | [13 empty] | S | S | F | F | F
Turlough Hill | TH4 | 73 | [13 empty] | S | S
Tynagh | TYC | 404 | [17 empty] | F | [16 empty] | F | F | F | F | F | F | F | F | F | F | F
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 8
Veolia Alternative Energy | DP2 | 21
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 59
VIOTAS | EE2 | 25
VIOTAS | EE3 | 13
VIOTAS | EE4 | 15
VIOTAS | EE5 | 25
VIOTAS | EE6 | 14
VIOTAS | EE7 | 37
VIOTAS | EE8 | 5
VIOTAS | EE9 | 5
VIOTAS | VS1 | 5
VIOTAS | VS2 | 6
Whitebank | DW1 | 62 | [6 empty] | F |  | F | F | F | F |  | F
Whitegate | WG1 | 444 | [17 empty] | F | F | [16 empty] | S | F

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Golagh | GO2 | 3 | 2023-04-17 15:30 | 2026-01-01 | F | 989.33
Liffey | LI4 | 4 | 2024-07-30 08:00 | 2025-10-31 17:00 | F | 458.33
Moneypoint | MP3 | 285 | 2024-10-25 22:00 | 2025-01-21 23:00 | F | 88
Ballylumford | NIB10 | 94 | 2024-12-07 11:00 | 2025-04-11 09:00 | F | 124.92
Ballylumford | NIB32 | 249 | 2024-12-07 11:00 | 2025-02-04 16:00 | F | 59.17
Ballylumford | NIB31 | 249 | 2024-12-07 11:00 | 2025-03-08 19:00 | F | 91.33
Ballylumford | NIBGT2 | 58 | 2024-12-11 09:00 | 2025-01-20 12:00 | 55 | 40.08
Rhode | RP1 | 52 | 2024-12-11 22:30 | 2025-01-06 08:00 | 26 | 25.38
Moneypoint | MP1 | 285 | 2024-12-28 08:00 | 2025-01-02 21:00 | F | 5.5
Loughtown | GLK | 500 | 2025-01-01 | 2025-01-29 23:30 | S | 28.96
Moneypoint | MP2 | 285 | 2025-01-01 | 2025-01-07 06:00 | 220 | 6.25
Erne | ER4 | 23 | 2025-01-01 | 2025-10-31 20:00 | F | 303.83
Activation Energy | NIAEA | 2 | 2025-01-01 | 2026-01-01 | S | 365
Whitebank | DW1 | 61.5 | 2025-01-02 09:00 | 2025-01-03 23:00 | 59 | 1.58
Irishtown | IS3 | 64 | 2025-01-02 20:00 | 2025-01-03 09:00 | F | 0.5
Moneypoint | MP1 | 285 | 2025-01-02 21:00 | 2025-01-06 17:30 | 220 | 3.83
Edenderry | ED1 | 118 | 2025-01-05 13:00 | 2025-01-06 09:30 | 50 | 0.83
Rhode | RP1 | 52 | 2025-01-06 08:00 | 2025-01-10 13:30 | F | 4.21
Edenderry | ED1 | 118 | 2025-01-06 09:30 | 2025-01-06 11:00 | 41 | 0.04
Whitebank | DW1 | 61.5 | 2025-01-06 10:00 | 2025-01-28 11:00 | 57 | 22
Edenderry | ED1 | 118 | 2025-01-06 11:00 | 2025-01-06 17:30 | 50 | 0.25
Liffey | LI2 | 15 | 2025-01-06 16:30 | 2025-01-07 14:00 | F | 0.88
Aghada | AD2 | 449 | 2025-01-06 17:30 | 2025-01-07 17:00 | F | 0.96
Edenderry | ED1 | 118 | 2025-01-06 17:30 | 2025-01-06 23:30 | 70 | 0.25
Moneypoint | MP1 | 285 | 2025-01-06 17:30 | 2025-01-08 19:30 | 230 | 2.08
Moneypoint | MP2 | 285 | 2025-01-07 06:00 | 2025-01-07 12:00 | F | 0.25
Moneypoint | MP2 | 285 | 2025-01-07 12:00 | 2025-01-07 15:00 | 235 | 0.08
Moneypoint | MP2 | 285 | 2025-01-07 15:00 | 2025-01-20 08:00 | 250 | 12.67
Dunsoghly | DG1 | 50 | 2025-01-08 18:00 | 2025-01-09 15:30 | 23 | 0.88
Moneypoint | MP1 | 285 | 2025-01-08 19:30 | 2025-01-20 16:00 | 240 | 11.83
Whitegate | WG1 | 444 | 2025-01-09 23:00 | 2025-01-13 23:00 | F | 4
Edenderry | ED1 | 118 | 2025-01-11 19:00 | 2025-01-13 18:00 | 50 | 1.92
Lisahally | NILPS | 17.6 | 2025-01-12 | 2025-01-18 | S | 6
Poolbeg | PB7 | 64 | 2025-01-12 01:30 | 2025-01-12 12:00 | F | 0.42
Shannonbridge | SQ1 | 262 | 2025-01-13 08:00 | 2025-01-13 18:00 | 160 | 0.42
Poolbeg | PB7 | 64 | 2025-01-13 08:00 | 2025-01-13 14:00 | F | 0.25
Erne | ER2 | 10 | 2025-01-13 08:00 | 2025-01-14 15:30 | F | 1.29
Rhode | RP2 | 52 | 2025-01-13 09:00 | 2025-01-13 15:00 | F | 0.25
Shannonbridge | SQ1 | 262 | 2025-01-14 08:00 | 2025-01-14 18:00 | 160 | 0.42
Inchicore | IH1 | 30 | 2025-01-14 08:00 | 2025-01-31 17:30 | 25 | 17.38
Erne | ER2 | 10 | 2025-01-14 17:30 | 2025-01-15 22:00 | F | 1.17
Lee | LE1 | 15 | 2025-01-15 08:00 | 2025-01-15 17:00 | F | 0.33
Edenderry | ED1 | 118 | 2025-01-15 12:00 | 2025-01-16 04:30 | F | 0.67
Edenderry | ED1 | 118 | 2025-01-16 04:30 | 2025-01-17 16:00 | 41 | 1.46
Coolkeeragh | NICGT8 | 53 | 2025-01-16 07:30 | 2025-01-17 18:30 | 26 | 1.42
Corduff | FG2 | 64 | 2025-01-16 08:00 | 2025-01-16 17:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-01-17 08:00 | 2025-01-17 18:00 | 160 | 0.42
Shannonbridge | SQ1 | 262 | 2025-01-18 04:00 | 2025-01-19 20:00 | F | 1.67
Shannonbridge | SQ1 | 262 | 2025-01-20 06:00 | 2025-01-24 17:00 | 160 | 4.42
Moneypoint | MP2 | 285 | 2025-01-20 08:00 | 2025-01-20 13:00 | F | 0.17
Moneypoint | MP2 | 285 | 2025-01-20 13:00 | 2025-01-25 14:00 | 250 | 5
Moneypoint | MP1 | 285 | 2025-01-20 16:00 | 2025-02-12 18:30 | 260 | 23.08
Moneypoint | MP3 | 285 | 2025-01-21 23:00 | 2025-01-27 18:00 | 260 | 5.75
Edenderry | ED3 | 58 | 2025-01-22 16:30 | 2025-01-23 23:00 | F | 1.25
Edenderry | ED3 | 58 | 2025-01-23 23:00 | 2025-01-24 21:00 | F | 0.92
Castlereagh BESS | NICSB | 50 | 2025-01-24 06:00 | 2025-01-24 17:00 | F | 0.42
Kilroot | NIKGT7 | 350 | 2025-01-24 06:00 | 2025-01-24 09:30 | F | 0.12
Tawnaghmore | TP1 | 52 | 2025-01-24 06:30 | 2025-01-28 11:00 | F | 4.17
Tawnaghmore | TP3 | 52 | 2025-01-24 06:30 | 2025-01-28 11:00 | F | 4.17
Kells BESS | NIKEB | 50 | 2025-01-24 07:00 | 2025-01-28 | F | 3.67
Rhode | RP2 | 52 | 2025-01-24 07:30 | 2025-01-26 16:00 | F | 2.33
Rhode | RP1 | 52 | 2025-01-24 07:30 | 2025-01-26 16:00 | F | 2.33
Lisahally | NILPS | 17.6 | 2025-01-24 09:30 | 2025-01-24 18:00 | F | 0.33
Coolkeeragh | NICGT8 | 53 | 2025-01-24 10:00 | 2025-01-25 15:00 | 26 | 1.17
Corduff | FG2 | 64 | 2025-01-24 19:00 | 2025-01-27 11:00 | F | 2.67
Lisahally | NILPS | 17.6 | 2025-01-24 20:30 | 2025-01-27 12:30 | F | 2.67
Moneypoint | MP2 | 285 | 2025-01-25 14:00 | 2025-02-23 18:00 | F | 29.17
Edenderry | ED1 | 118 | 2025-01-26 09:00 | 2025-01-26 10:00 | F | 0
Seal Rock | SK4 | 83 | 2025-01-27 06:00 | 2025-01-29 18:00 | S | 2.5
Drybridge | IW1 | 17 | 2025-01-27 08:30 | 2025-01-29 12:30 | F | 2.17
Moneypoint | MP3 | 285 | 2025-01-27 18:00 | 2025-02-06 08:30 | 240 | 9.58
Coolkeeragh | NICGT8 | 53 | 2025-01-28 08:00 | 2025-01-30 18:00 | 26 | 2.42
Whitebank | DW1 | 61.5 | 2025-01-28 11:00 | 2025-02-09 21:00 | 53 | 12.42
Dublin Bay | DB1 | 415 | 2025-01-28 21:00 | 2025-01-28 22:00 | F | 0
Huntstown | HN2 | 402 | 2025-01-28 23:00 | 2025-04-27 02:00 | F | 88.08
Shannonbridge | SQ1 | 262 | 2025-01-29 13:00 | 2025-01-29 17:00 | 160 | 0.17
Lee | LE2 | 4 | 2025-01-29 14:00 | 2025-01-29 19:30 | 1 | 0.21
Lee | LE1 | 15 | 2025-01-29 14:00 | 2025-01-29 19:00 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-01-30 07:00 | 2025-01-30 14:00 | 160 | 0.25
Shannonbridge | SQ1 | 262 | 2025-01-30 14:00 | 2025-01-30 18:00 | 160 | 0.17
Aghada | AD2 | 449 | 2025-02-01 06:00 | 2025-02-01 15:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-02-01 07:00 | 2025-02-01 17:00 | 160 | 0.42
Edenderry | ED1 | 118 | 2025-02-01 17:00 | 2025-02-03 00:30 | 50 | 1.29
Shannonbridge | SQ1 | 262 | 2025-02-03 07:00 | 2025-02-03 16:00 | 160 | 0.33
Shannonbridge | SQ1 | 262 | 2025-02-04 06:00 | 2025-02-04 07:30 | F | 0.04
Poolbeg | PB6 | 168 | 2025-02-04 08:00 | 2025-02-05 12:00 | F | 1.17
Tawnaghmore | TP1 | 52 | 2025-02-04 09:30 | 2025-03-05 21:00 | 40 | 29.46
Tawnaghmore | TP3 | 52 | 2025-02-04 09:30 | 2025-02-05 21:00 | 40 | 1.46
Carmeen | NICMN | 20 | 2025-02-04 13:30 | 2025-02-04 16:30 | 16 | 0.08
Edenderry | ED1 | 118 | 2025-02-04 15:30 | 2025-02-05 05:00 | 41 | 0.54
Ballylumford | NIB32 | 249 | 2025-02-04 16:00 | 2025-02-04 19:00 | 161 | 0.08
Liffey | LI2 | 15 | 2025-02-04 16:30 | 2025-02-07 09:00 | F | 2.67
Liffey | LI1 | 15 | 2025-02-04 16:30 | 2025-02-07 09:00 | F | 2.67
Ballylumford | NIB32 | 249 | 2025-02-04 19:00 | 2025-02-04 20:00 | F | 0
Ballylumford | NIB32 | 249 | 2025-02-04 20:00 | 2025-04-01 04:00 | 161 | 55.33
Carmeen | NICMN | 20 | 2025-02-05 10:30 | 2025-02-05 16:00 | 18 | 0.21
Erne | ER2 | 10 | 2025-02-06 08:00 | 2025-02-06 09:30 | F | 0.04
Moneypoint | MP3 | 285 | 2025-02-06 08:30 | 2025-02-16 12:00 | 250 | 10.12
Whitebank | DW1 | 61.5 | 2025-02-06 21:00 | 2025-03-07 15:00 | F | 28.75
Great Island | GI4 | 464 | 2025-02-06 22:30 | 2025-02-07 17:00 | F | 0.75
Lisdrum | LF1 | 60 | 2025-02-07 10:00 | 2025-02-07 14:00 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-02-08 10:00 | 2025-02-08 14:00 | F | 0.17
Kilroot | NIKGT7 | 350 | 2025-02-08 12:00 | 2025-02-08 20:00 | F | 0.33
Poolbeg | PB6 | 168 | 2025-02-09 23:00 | 2025-02-10 03:00 | 88 | 0.17
Poolbeg | PB7 | 64 | 2025-02-10 08:00 | 2025-02-10 17:00 | F | 0.33
Irishtown | IS3 | 64 | 2025-02-10 08:00 | 2025-02-10 17:00 | F | 0.33
Whitebank | DW1 | 61.5 | 2025-02-10 17:00 | 2025-02-13 10:30 | 56 | 2.71
Lisahally | NILPS | 17.6 | 2025-02-11 03:00 | 2025-02-11 04:30 | F | 0.04
Irishtown | IS3 | 64 | 2025-02-11 08:00 | 2025-02-11 17:00 | F | 0.33
Corduff | FG2 | 64 | 2025-02-12 08:00 | 2025-02-12 17:00 | F | 0.33
Whitegate | WG1 | 444 | 2025-02-12 12:30 | 2025-02-12 16:00 | F | 0.12
Moneypoint | MP1 | 285 | 2025-02-12 18:30 | 2025-03-24 07:00 | 270 | 39.5
Ballylumford | NIBGT2 | 58 | 2025-02-13 06:00 | 2025-02-13 15:00 | F | 0.33
Ballylumford | NIBGT1 | 58 | 2025-02-13 06:00 | 2025-02-13 15:00 | F | 0.33
Whitebank | DW1 | 61.5 | 2025-02-13 10:30 | 2025-02-13 14:00 | 50 | 0.12
Edenderry | ED1 | 118 | 2025-02-13 13:00 | 2025-02-17 18:00 | F | 4.17
Whitebank | DW1 | 61.5 | 2025-02-13 14:00 | 2025-02-14 09:30 | 56 | 0.79
Lee | LE1 | 15 | 2025-02-14 | 2025-02-14 08:00 | 4 | 0.33
Lee | LE2 | 4 | 2025-02-14 | 2025-02-14 08:00 | 1 | 0.33
Lee | LE3 | 8 | 2025-02-14 | 2025-02-14 08:00 | 4 | 0.33
Whitebank | DW1 | 61.5 | 2025-02-14 16:00 | 2025-02-23 00:30 | 52 | 8.33
Coolkeeragh | NIC30 | 408 | 2025-02-14 20:00 | 2025-02-16 20:00 | S | 2
Shannonbridge | SQ1 | 262 | 2025-02-15 08:00 | 2025-02-15 13:30 | F | 0.21
Lee | LE3 | 8 | 2025-02-15 08:30 | 2025-02-15 12:00 | F | 0.12
Moneypoint | MP3 | 285 | 2025-02-16 12:00 | 2025-02-27 | F | 10.5
Lee | LE3 | 8 | 2025-02-16 15:00 | 2025-02-17 12:30 | 4 | 0.88
Drybridge | IW1 | 17 | 2025-02-16 20:30 | 2025-02-20 15:30 | F | 3.75
Shannonbridge | SQ1 | 262 | 2025-02-17 10:00 | 2025-02-17 14:00 | 160 | 0.17
Poolbeg | PB7 | 64 | 2025-02-17 10:00 | 2025-02-17 12:30 | F | 0.08
Edenderry | ED1 | 118 | 2025-02-17 18:00 | 2025-02-18 08:00 | 41 | 0.58
Aghada | AD3 | 19 | 2025-02-18 08:00 | 2025-03-07 17:00 | 16 | 17.33
Edenderry | ED1 | 118 | 2025-02-18 08:00 | 2025-02-18 11:00 | 60 | 0.08
Castlereagh BESS | NICSB | 50 | 2025-02-18 08:00 | 2025-02-18 16:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-02-18 10:00 | 2025-02-18 14:00 | 160 | 0.17
Whitegate | WG1 | 444 | 2025-02-19 05:00 | 2025-02-19 08:00 | F | 0.08
Edenderry | ED1 | 118 | 2025-02-19 10:30 | 2025-02-19 19:00 | 50 | 0.33
Turlough Hill | TH3 | 73 | 2025-02-20 06:30 | 2025-02-20 08:00 | F | 0.04
Shannonbridge | SQ1 | 262 | 2025-02-20 09:00 | 2025-02-20 13:00 | 192 | 0.17
Kilroot | NIKGT6 | 350 | 2025-02-20 10:00 | 2025-02-20 12:00 | F | 0.08
Ardnacrusha | AA4 | 24 | 2025-02-20 16:30 | 2025-02-20 19:00 | F | 0.08
Coolkeeragh | NICGT8 | 53 | 2025-02-21 14:00 | 2025-02-21 15:00 | 26 | 0
Whitebank | DW1 | 61.5 | 2025-02-22 23:30 | 2025-02-28 03:00 | 22 | 5.12
Lisahally | NILPS | 17.6 | 2025-02-23 | 2025-02-23 01:00 | F | 0
Moneypoint | MP2 | 285 | 2025-02-23 18:00 | 2025-03-26 13:00 | 250 | 30.75
Liffey | LI5 | 4 | 2025-02-24 15:00 | 2025-02-24 16:00 | F | 0
Tynagh | TYC | 404 | 2025-02-25 05:30 | 2025-02-27 16:00 | F | 2.42
Shannonbridge | SQ1 | 262 | 2025-02-25 19:30 | 2025-02-26 13:30 | 192 | 0.75
Shannonbridge | SQ1 | 262 | 2025-02-26 13:30 | 2025-03-05 00:30 | F | 6.42
Erne | ER1 | 10 | 2025-02-26 16:00 | 2025-02-26 17:00 | F | 0
Erne | ER3 | 23 | 2025-02-26 16:00 | 2025-02-26 17:00 | F | 0
Erne | ER2 | 10 | 2025-02-26 16:00 | 2025-02-27 11:00 | F | 0.75
Moneypoint | MP3 | 285 | 2025-02-27 | 2025-03-11 12:30 | 250 | 12.5
Kilroot | NIKGT4 | 42 | 2025-02-27 07:00 | 2025-02-27 15:00 | F | 0.33
Kells BESS | NIKEB | 50 | 2025-02-27 10:00 | 2025-02-27 11:00 | F | 0
Whitebank | DW1 | 61.5 | 2025-02-28 03:00 | 2025-03-08 15:00 | 20 | 8.5
Carmeen | NICMN | 20 | 2025-02-28 11:00 | 2025-02-28 13:00 | 14 | 0.08
Kilroot | NIKGT7 | 350 | 2025-03-01 07:00 | 2025-03-02 18:00 | S | 1.42
Aghada | AT1 | 90 | 2025-03-01 14:00 | 2025-04-02 | S | 31.42
Turlough Hill | TH2 | 73 | 2025-03-01 14:30 | 2025-03-01 20:30 | F | 0.25
Edenderry | ED1 | 118 | 2025-03-01 23:30 | 2025-03-04 12:00 | 41 | 2.5
Turlough Hill | TH1 | 73 | 2025-03-04 02:30 | 2025-03-05 19:00 | F | 1.67
Turlough Hill | TH2 | 73 | 2025-03-04 02:30 | 2025-03-05 19:00 | F | 1.67
Turlough Hill | TH3 | 73 | 2025-03-04 02:30 | 2025-03-05 19:00 | F | 1.67
Turlough Hill | TH4 | 73 | 2025-03-04 02:30 | 2025-03-05 19:00 | F | 1.67
Great Island | GI4 | 464 | 2025-03-04 19:00 | 2025-03-06 17:00 | F | 1.92
Shannonbridge | SQ1 | 262 | 2025-03-05 00:30 | 2025-03-07 17:00 | 96 | 2.67
Kilroot | NIKGT6 | 350 | 2025-03-05 07:00 | 2025-03-05 17:30 | F | 0.42
Irishtown | IS2 | 30 | 2025-03-05 08:00 | 2025-03-06 17:00 | 17 | 1.33
Inchicore | IH1 | 30 | 2025-03-05 08:00 | 2025-03-12 17:00 | 17 | 7.33
Mullavilly BESS | NIMZ1 | 50 | 2025-03-05 14:00 | 2025-03-05 15:00 | F | 0
Turlough Hill | TH1 | 73 | 2025-03-07 07:00 | 2025-03-07 08:00 | F | 0
Turlough Hill | TH2 | 73 | 2025-03-07 07:00 | 2025-03-07 08:00 | F | 0
Turlough Hill | TH3 | 73 | 2025-03-07 07:00 | 2025-03-07 08:00 | F | 0
Turlough Hill | TH4 | 73 | 2025-03-07 07:00 | 2025-03-07 08:00 | F | 0
Turlough Hill | TH3 | 73 | 2025-03-07 08:00 | 2025-03-07 18:00 | S | 0.42
Turlough Hill | TH1 | 73 | 2025-03-07 08:00 | 2025-03-07 18:00 | S | 0.42
Turlough Hill | TH2 | 73 | 2025-03-07 08:00 | 2025-03-07 18:00 | S | 0.42
Turlough Hill | TH4 | 73 | 2025-03-07 08:00 | 2025-03-07 18:00 | S | 0.42
Lisahally | NILPS | 17.6 | 2025-03-07 08:30 | 2025-03-07 10:30 | F | 0.08
Shannonbridge | SQ1 | 262 | 2025-03-08 08:00 | 2025-03-08 17:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-03-08 08:00 | 2025-03-08 17:00 | 160 | 0.33
Whitebank | DW1 | 61.5 | 2025-03-08 15:00 | 2025-03-24 06:00 | F | 15.58
Ballylumford | NIB31 | 249 | 2025-03-08 19:00 | 2025-03-12 02:00 | 161 | 3.25
Liffey | LI5 | 4 | 2025-03-09 20:00 | 2025-03-10 08:00 | F | 0.5
Shannonbridge | SQ1 | 262 | 2025-03-10 08:00 | 2025-03-10 16:00 | 192 | 0.33
Tarbert | TB5 | 160 | 2025-03-10 08:30 | 2025-03-11 17:00 | F | 1.33
Dublin Bay | DB1 | 415 | 2025-03-11 01:30 | 2025-03-11 08:00 | 239 | 0.25
Moneypoint | MP3 | 285 | 2025-03-11 12:30 | 2025-03-12 19:00 | 210 | 1.25
Ballylumford | NIB31 | 249 | 2025-03-12 02:00 | 2025-03-12 22:00 | F | 0.83
Tarbert | TB5 | 160 | 2025-03-12 08:30 | 2025-03-13 17:00 | F | 1.33
Moneypoint | MP3 | 285 | 2025-03-12 19:00 | 2025-03-12 23:00 | F | 0.17
Ballylumford | NIB31 | 249 | 2025-03-12 22:00 | 2025-06-29 05:00 | 161 | 108.25
Moneypoint | MP3 | 285 | 2025-03-12 23:00 | 2025-03-13 22:30 | 210 | 0.96
Liffey | LI5 | 4 | 2025-03-13 10:30 | 2025-03-14 11:00 | F | 1
Moneypoint | MP3 | 285 | 2025-03-13 22:30 | 2025-03-14 02:00 | F | 0.12
Moneypoint | MP3 | 285 | 2025-03-14 02:00 | 2025-03-18 17:30 | 260 | 4.62
Edenderry | ED1 | 118 | 2025-03-15 00:30 | 2025-03-18 18:00 | 51 | 3.71
Seal Rock | SK4 | 83 | 2025-03-16 11:00 | 2025-03-16 13:00 | F | 0.08
Kilroot | NIKGT3 | 42 | 2025-03-18 07:00 | 2025-03-18 20:30 | F | 0.54
Poolbeg | PB6 | 168 | 2025-03-18 08:00 | 2025-03-18 14:00 | F | 0.25
Great Island | GI4 | 464 | 2025-03-18 17:00 | 2025-03-18 20:00 | F | 0.08
Moneypoint | MP3 | 285 | 2025-03-18 17:30 | 2025-03-21 18:00 | 265 | 3
Great Island | GI4 | 464 | 2025-03-18 22:00 | 2025-03-24 01:00 | F | 5.08
Lisahally | NILPS | 17.6 | 2025-03-19 02:00 | 2025-03-19 03:30 | F | 0.04
Kilroot | NIKGT4 | 42 | 2025-03-19 07:00 | 2025-03-24 15:00 | F | 5.33
Lisahally | NILPS | 17.6 | 2025-03-19 09:00 | 2025-03-19 11:00 | F | 0.08
Kilroot | NIKGT3 | 42 | 2025-03-19 13:00 | 2025-03-19 14:00 | F | 0
Kilroot | NIKGT3 | 42 | 2025-03-20 11:00 | 2025-03-20 13:30 | F | 0.08
Moneypoint | MP3 | 285 | 2025-03-21 18:00 | 2025-03-23 18:00 | 250 | 2
Dublin Bay | DB1 | 415 | 2025-03-21 20:00 | 2025-03-29 20:00 | F | 8
Aghada | AT2 | 90 | 2025-03-23 | 2025-04-05 | S | 13
Turlough Hill | TH1 | 73 | 2025-03-23 08:00 | 2025-04-01 19:00 | S | 9.42
Turlough Hill | TH2 | 73 | 2025-03-23 08:00 | 2025-04-01 17:00 | S | 9.33
Moneypoint | MP3 | 285 | 2025-03-23 18:00 | 2025-03-31 07:30 | 220 | 7.54
Lee | LE2 | 4 | 2025-03-24 | 2025-04-04 20:00 | S | 11.83
Whitebank | DW1 | 61.5 | 2025-03-24 06:00 | 2025-03-31 09:00 | 27 | 7.08
Seal Rock | SK3 | 83 | 2025-03-24 06:00 | 2025-03-26 18:00 | S | 2.5
Moneypoint | MP1 | 285 | 2025-03-24 07:00 | 2025-03-24 15:30 | F | 0.33
Erne | ER2 | 10 | 2025-03-24 08:00 | 2025-03-25 15:00 | F | 1.25
Erne | ER1 | 10 | 2025-03-24 08:00 | 2025-03-25 15:00 | F | 1.25
Irishtown | IS3 | 64 | 2025-03-24 08:00 | 2025-03-24 11:00 | F | 0.08
Kilroot | NIKGT3 | 42 | 2025-03-24 10:00 | 2025-03-24 15:00 | F | 0.17
Moneypoint | MP1 | 285 | 2025-03-24 15:30 | 2025-03-24 22:30 | 270 | 0.25
Moneypoint | MP1 | 285 | 2025-03-24 22:30 | 2025-03-27 22:00 | 250 | 2.96
Turlough Hill | TH3 | 73 | 2025-03-25 11:00 | 2025-03-25 21:00 | F | 0.42
Turlough Hill | TH4 | 73 | 2025-03-25 11:00 | 2025-03-25 21:00 | F | 0.42
Lisdrum | LF1 | 60 | 2025-03-26 07:30 | 2025-03-26 17:00 | F | 0.38
Erne | ER3 | 23 | 2025-03-26 08:30 | 2025-03-26 16:30 | F | 0.33
Moneypoint | MP2 | 285 | 2025-03-26 13:00 | 2025-03-27 20:30 | F | 1.29
Edenderry | ED1 | 118 | 2025-03-27 07:00 | 2025-03-27 16:30 | 41 | 0.38
Shannonbridge | SQ1 | 262 | 2025-03-27 08:00 | 2025-03-27 16:00 | 224 | 0.33
Erne | ER3 | 23 | 2025-03-27 08:00 | 2025-03-31 08:00 | F | 4
Kilroot | NIKGT4 | 42 | 2025-03-27 12:00 | 2025-03-28 13:30 | F | 1.04
Moneypoint | MP2 | 285 | 2025-03-27 20:30 | 2025-04-01 15:00 | 250 | 4.75
Moneypoint | MP1 | 285 | 2025-03-27 22:00 | 2025-04-06 22:00 | F | 10
Edenderry | ED1 | 118 | 2025-03-28 07:00 | 2025-03-28 15:00 | 41 | 0.33
Shannonbridge | SQ1 | 262 | 2025-03-28 08:00 | 2025-03-28 16:00 | 224 | 0.33
Aghada | AT4 | 90 | 2025-03-28 12:00 | 2025-04-10 | S | 12.5
Turlough Hill | TH3 | 73 | 2025-03-28 17:00 | 2025-04-02 08:00 | F | 4.58
Shannonbridge | SQ1 | 262 | 2025-03-29 08:00 | 2025-03-29 16:00 | 224 | 0.33
Dublin Bay | DB1 | 415 | 2025-03-29 21:30 | 2025-04-01 | F | 2.08
Shannonbridge | SQ1 | 262 | 2025-03-30 08:00 | 2025-03-30 12:00 | 224 | 0.17
Ballylumford | NIBGT2 | 58 | 2025-03-30 09:00 | 2025-03-30 14:00 | F | 0.17
Ballylumford | NIBGT1 | 58 | 2025-03-30 10:00 | 2025-03-30 13:00 | F | 0.08
Seal Rock | SK4 | 83 | 2025-03-31 01:00 | 2025-04-01 18:00 | F | 1.67
Seal Rock | SK3 | 83 | 2025-03-31 05:30 | 2025-03-31 08:30 | F | 0.08
Ballylumford | NIBGT1 | 58 | 2025-03-31 07:00 | 2025-03-31 17:00 | F | 0.42
Moneypoint | MP3 | 285 | 2025-03-31 07:30 | 2025-03-31 14:30 | F | 0.25
Corduff | FG2 | 64 | 2025-03-31 08:00 | 2025-04-05 20:00 | F | 5.5
Tawnaghmore | TP1 | 52 | 2025-03-31 08:30 | 2025-04-08 12:30 | 30 | 8.17
Whitebank | DW1 | 61.5 | 2025-03-31 09:00 | 2025-03-31 16:00 | 24 | 0.25
Moneypoint | MP3 | 285 | 2025-03-31 14:30 | 2025-04-02 05:00 | 250 | 1.58
Whitebank | DW1 | 61.5 | 2025-03-31 16:00 | 2025-04-07 01:00 | F | 6.33
Aghada | AD2 | 449 | 2025-04-01 01:00 | 2025-04-05 21:30 | F | 4.83
Dublin Bay | DB1 | 415 | 2025-04-01 01:30 | 2025-04-02 12:00 | F | 1.42
Ballylumford | NIB32 | 249 | 2025-04-01 04:00 | 2025-04-05 09:00 | F | 4.17
Moneypoint | MP2 | 285 | 2025-04-01 15:00 | 2025-04-14 17:30 | F | 13.08
Turlough Hill | TH2 | 73 | 2025-04-01 17:00 | 2025-04-02 12:00 | F | 0.75
Seal Rock | SK4 | 83 | 2025-04-01 18:00 | 2025-04-10 23:00 | F | 9.17
Aghada | AT1 | 90 | 2025-04-02 | 2025-04-21 | F | 19
Moneypoint | MP3 | 285 | 2025-04-02 05:00 | 2025-04-02 22:00 | 200 | 0.67
Drumkee BESS | NIDK1 | 50 | 2025-04-02 06:00 | 2025-04-02 10:30 | F | 0.17
Turlough Hill | TH4 | 73 | 2025-04-02 08:00 | 2025-04-10 13:00 | S | 8.17
Derrycarney | LU1 | 50 | 2025-04-02 08:00 | 2025-04-11 11:30 | F | 9.12
Derrycarney | LU2 | 50 | 2025-04-02 08:00 | 2025-04-11 11:30 | F | 9.12
Turlough Hill | TH3 | 73 | 2025-04-02 08:00 | 2025-04-11 17:00 | S | 9.33
Moneypoint | MP3 | 285 | 2025-04-02 22:00 | 2025-04-26 06:30 | 250 | 23.33
Tarbert | TB5 | 160 | 2025-04-02 22:00 | 2025-04-05 18:30 | F | 2.83
Shannonbridge | SQ1 | 262 | 2025-04-04 08:00 | 2025-04-04 18:00 | 224 | 0.42
Turlough Hill | TH1 | 73 | 2025-04-04 09:30 | 2025-04-04 13:30 | F | 0.17
Ballylumford | NIBGT2 | 58 | 2025-04-04 11:30 | 2025-04-04 16:00 | F | 0.17
Aghada | AT2 | 90 | 2025-04-05 | 2025-04-23 | F | 18
Shannonbridge | SQ1 | 262 | 2025-04-05 08:00 | 2025-04-05 18:00 | 192 | 0.42
Ballylumford | NIB32 | 249 | 2025-04-05 18:00 | 2025-04-05 21:30 | F | 0.12
Tarbert | TB5 | 160 | 2025-04-05 18:30 | 2025-04-12 11:00 | 50 | 6.67
Shannonbridge | SQ1 | 262 | 2025-04-06 08:00 | 2025-04-06 18:00 | 192 | 0.42
Edenderry | ED1 | 118 | 2025-04-06 18:30 | 2025-04-07 16:30 | 90 | 0.92
Moneypoint | MP1 | 285 | 2025-04-06 22:00 | 2025-04-25 20:00 | 250 | 18.92
Whitebank | DW1 | 61.5 | 2025-04-07 01:00 | 2025-04-07 11:00 | 22 | 0.42
Aghada | AD3 | 19 | 2025-04-07 07:00 | 2025-04-10 22:00 | S | 3.58
Shannonbridge | SQ1 | 262 | 2025-04-07 08:00 | 2025-04-07 16:00 | 224 | 0.33
Poolbeg | PB7 | 64 | 2025-04-07 08:00 | 2025-04-11 13:00 | F | 4.17
Erne | ER2 | 10 | 2025-04-07 08:00 | 2025-04-11 20:00 | S | 4.5
Whitebank | DW1 | 61.5 | 2025-04-07 11:00 | 2025-04-09 20:00 | 24 | 2.33
Shannonbridge | SQ1 | 262 | 2025-04-08 08:00 | 2025-04-08 16:00 | 224 | 0.33
Ardnacrusha | AA3 | 19 | 2025-04-08 11:30 | 2025-04-15 15:00 | F | 7.12
Tawnaghmore | TP1 | 52 | 2025-04-08 12:30 | 2025-04-11 19:00 | F | 3.25
Loughtown | GLK | 500 | 2025-04-08 17:00 | 2025-04-10 23:00 | F | 2.25
Rhode | RP2 | 52 | 2025-04-08 20:30 | 2025-04-09 12:00 | 26 | 0.62
Tynagh | TYC | 404 | 2025-04-08 22:00 | 2025-04-09 05:30 | F | 0.29
Edenderry | ED1 | 118 | 2025-04-09 00:30 | 2025-04-09 13:00 | 98 | 0.5
Shannonbridge | SQ1 | 262 | 2025-04-09 08:00 | 2025-04-09 16:00 | 224 | 0.33
Edenderry | ED1 | 118 | 2025-04-09 13:00 | 2025-04-09 16:30 | 55 | 0.12
Whitebank | DW1 | 61.5 | 2025-04-09 22:00 | 2025-04-10 15:00 | F | 0.67
Aghada | AT4 | 90 | 2025-04-10 | 2025-05-03 21:00 | F | 23.83
Whitebank | DW1 | 61.5 | 2025-04-10 15:00 | 2025-04-11 06:00 | 24 | 0.58
Tobertoreen | XT2 | 11 | 2025-04-11 05:30 | 2025-04-11 17:30 | F | 0.5
Ballylumford | NIB10 | 94 | 2025-04-11 13:00 | 2025-04-11 17:30 | F | 0.17
Turlough Hill | TH3 | 73 | 2025-04-11 17:00 | 2025-05-04 12:00 | F | 22.75
Shannonbridge | SQ1 | 262 | 2025-04-12 08:00 | 2025-04-12 16:00 | 224 | 0.33
Ballylumford | NIBGT2 | 58 | 2025-04-12 13:00 | 2025-04-12 14:00 | F | 0
Ballylumford | NIBGT1 | 58 | 2025-04-12 13:00 | 2025-04-12 14:00 | F | 0
Dublin Bay | DB1 | 415 | 2025-04-13 05:00 | 2025-04-13 22:30 | F | 0.71
Shannonbridge | SQ1 | 262 | 2025-04-13 08:00 | 2025-04-13 16:00 | 224 | 0.33
Aghada | AD4 | 75 | 2025-04-14 07:00 | 2025-04-24 20:00 | F | 10.5
Shannonbridge | SQ1 | 262 | 2025-04-14 08:00 | 2025-04-14 16:00 | 224 | 0.33
Inchicore | IH1 | 30 | 2025-04-14 08:00 | 2025-04-14 17:00 | 25 | 0.33
Irishtown | IS3 | 64 | 2025-04-14 08:00 | 2025-04-15 16:00 | F | 1.33
EWIC | EW1 | 500 | 2025-04-14 09:00 | 2025-04-14 21:00 | S | 0.5
Ballydown BESS | NIBLD | 12 | 2025-04-14 10:00 | 2025-04-16 19:00 | F | 2.33
Whitebank | DW1 | 61.5 | 2025-04-14 13:00 | 2025-04-14 16:00 | 50 | 0.08
Whitebank | DW1 | 61.5 | 2025-04-14 16:00 | 2025-04-14 18:00 | 40 | 0.08
Moneypoint | MP2 | 285 | 2025-04-14 17:30 | 2025-04-16 23:30 | 250 | 2.25
Whitebank | DW1 | 61.5 | 2025-04-14 18:00 | 2025-04-17 08:00 | 24 | 2.58
EWIC | EW1 | 500 | 2025-04-14 21:00 | 2025-04-18 23:00 | S | 4.08
Inchicore | IH1 | 30 | 2025-04-15 08:00 | 2025-04-15 17:00 | 20 | 0.33
Shannonbridge | SQ1 | 262 | 2025-04-15 08:00 | 2025-04-15 16:00 | 224 | 0.33
Lisahally | NILPS | 17.6 | 2025-04-15 11:30 | 2025-04-15 12:30 | F | 0
Corduff | FG2 | 64 | 2025-04-15 12:00 | 2025-04-15 16:00 | F | 0.17
Aghada | AD2 | 449 | 2025-04-15 13:30 | 2025-04-18 12:00 | F | 2.92
Moneypoint | MP5 | 1 | 2025-04-15 14:00 | 2025-04-18 17:00 | F | 3.08
Ardnacrusha | AA3 | 19 | 2025-04-16 05:30 | 2025-04-16 13:00 | F | 0.29
Shannonbridge | SQ1 | 262 | 2025-04-16 08:00 | 2025-04-16 16:00 | 224 | 0.33
Inchicore | IH1 | 30 | 2025-04-16 08:00 | 2025-04-16 17:00 | 20 | 0.33
Moneypoint | MP2 | 285 | 2025-04-16 23:30 | 2025-04-20 11:00 | F | 3.46
Inchicore | IH1 | 30 | 2025-04-17 08:00 | 2025-04-17 17:00 | 25 | 0.33
Kilroot | NIKGT3 | 42 | 2025-04-17 14:00 | 2025-04-17 15:30 | F | 0.04
Edenderry | ED1 | 118 | 2025-04-17 17:00 | 2025-04-22 14:00 | S | 4.83
Inchicore | IH1 | 30 | 2025-04-18 08:00 | 2025-04-18 17:00 | 25 | 0.33
Kilroot | NIKGT3 | 42 | 2025-04-18 10:30 | 2025-04-18 12:00 | F | 0.04
Kilroot | NIKGT4 | 42 | 2025-04-18 10:30 | 2025-04-18 12:00 | F | 0.04
EWIC | EW1 | 500 | 2025-04-18 23:00 | 2025-05-09 23:00 | F | 21
Moneypoint | MP2 | 285 | 2025-04-20 11:00 | 2025-04-23 17:00 | 250 | 3.25
Castlereagh BESS | NICSB | 50 | 2025-04-21 07:00 | 2025-04-21 17:00 | 40 | 0.42
Aghada | AT1 | 90 | 2025-04-21 09:00 | 2025-04-21 21:00 | F | 0.5
Whitebank | DW1 | 61.5 | 2025-04-21 18:00 | 2025-04-25 | 26 | 3.25
Lee | LE3 | 8 | 2025-04-22 | 2025-05-16 20:00 | S | 24.83
Banoge | OD1 | 9 | 2025-04-22 02:00 | 2025-04-22 23:00 | F | 0.83
Liffey | LI2 | 15 | 2025-04-22 08:00 | 2025-09-05 17:00 | S | 136.33
Liffey | LI1 | 15 | 2025-04-22 08:00 | 2025-09-05 17:00 | S | 136.33
Edenderry | ED1 | 118 | 2025-04-22 14:00 | 2025-04-23 11:00 | 41 | 0.83
Aghada | AT2 | 90 | 2025-04-23 | 2025-05-05 23:00 | 60 | 12.92
Tarbert | TB5 | 160 | 2025-04-23 08:00 | 2025-04-24 17:00 | 50 | 1.33
Dublin Bay | DB1 | 415 | 2025-04-23 09:30 | 2025-05-09 20:00 | F | 16.42
Moneypoint | MP2 | 285 | 2025-04-23 17:00 | 2025-04-23 21:00 | F | 0.17
Moneypoint | MP2 | 285 | 2025-04-23 21:00 | 2025-04-29 14:00 | 250 | 5.67
Kilroot | NIKGT6 | 350 | 2025-04-24 06:00 | 2025-04-24 20:00 | S | 0.58
Aghada | AD5 | 75 | 2025-04-24 07:00 | 2025-04-28 07:00 | 47 | 4
Ballylumford | NIBGT1 | 58 | 2025-04-24 08:00 | 2025-04-24 12:00 | 29 | 0.17
Aghada | AT1 | 90 | 2025-04-24 19:00 | 2025-04-25 16:00 | F | 0.83
Kilroot | NIKGT6 | 350 | 2025-04-24 20:00 | 2025-04-25 16:00 | F | 0.83
Moneypoint | MP1 | 285 | 2025-04-25 20:00 | 2025-05-07 22:00 | 260 | 12.08
Moneypoint | MP3 | 285 | 2025-04-26 06:30 | 2025-04-26 08:00 | F | 0.04
Moneypoint | MP3 | 285 | 2025-04-26 08:00 | 2025-04-30 22:30 | 250 | 4.58
Huntstown | HNC | 342 | 2025-04-26 12:00 | 2025-05-13 17:00 | S | 17.17
Aghada | AD2 | 449 | 2025-04-26 22:00 | 2025-05-07 | F | 10.08
Edenderry | ED1 | 118 | 2025-04-26 23:00 | 2025-04-28 17:00 | 41 | 1.75
Whitegate | WG1 | 444 | 2025-04-27 18:00 | 2025-05-09 23:00 | F | 12.17
Aghada | AD5 | 75 | 2025-04-28 07:00 | 2025-04-29 12:00 | F | 1.17
Ardnacrusha | AA2 | 22 | 2025-04-28 08:00 | 2025-09-19 20:00 | S | 144.5
Edenderry | ED1 | 118 | 2025-04-28 17:00 | 2025-04-29 15:30 | 54 | 0.92
Tynagh | TYC | 404 | 2025-04-28 20:00 | 2025-05-04 23:00 | F | 6.08
Kilroot | NIKGT2 | 29 | 2025-04-29 09:00 | 2025-04-29 10:30 | F | 0.04
Kilroot | NIKGT1 | 29 | 2025-04-29 09:00 | 2025-04-29 10:30 | F | 0.04
Castlereagh BESS | NICSB | 50 | 2025-04-29 11:00 | 2025-04-29 13:30 | S | 0.08
Aghada | AD5 | 75 | 2025-04-29 12:00 | 2025-05-06 17:00 | 69 | 7.17
Carmeen | NICMN | 20 | 2025-04-29 13:30 | 2025-05-09 14:30 | 14 | 10
Moneypoint | MP2 | 285 | 2025-04-29 14:00 | 2025-04-29 19:30 | F | 0.21
Aghada | AT1 | 90 | 2025-04-29 19:00 | 2025-04-30 17:00 | F | 0.92
Moneypoint | MP2 | 285 | 2025-04-29 19:30 | 2025-06-16 | 250 | 47.17
Poolbeg | PB7 | 64 | 2025-04-30 17:00 | 2025-05-02 16:00 | F | 1.92
Moneypoint | MP3 | 285 | 2025-04-30 22:30 | 2025-05-05 00:30 | 260 | 4.08
Ballylumford | NIBGT2 | 58 | 2025-05-02 18:30 | 2025-05-07 15:30 | 29 | 4.83
Irishtown | IS2 | 30 | 2025-05-02 19:00 | 2025-05-03 09:30 | F | 0.58
Irishtown | IS3 | 64 | 2025-05-02 21:00 | 2025-05-03 09:30 | F | 0.5
Aghada | AT4 | 90 | 2025-05-03 21:00 | 2025-05-04 17:30 | 60 | 0.83
Aghada | AT4 | 90 | 2025-05-04 17:30 | 2025-05-16 20:00 | F | 12.08
Moneypoint | MP3 | 285 | 2025-05-05 00:30 | 2025-05-06 06:00 | F | 1.21
Aghada | AT2 | 90 | 2025-05-05 23:00 | 2025-05-06 13:00 | F | 0.58
Moneypoint | MP3 | 285 | 2025-05-06 06:00 | 2025-06-12 05:00 | 230 | 36.92
Tawnaghmore | TP3 | 52 | 2025-05-06 09:00 | 2025-05-14 19:00 | F | 8.42
Lisdrum | LF1 | 60 | 2025-05-07 08:00 | 2025-05-07 18:00 | 45 | 0.42
Shannonbridge | SQ1 | 262 | 2025-05-07 08:00 | 2025-05-07 17:00 | 224 | 0.33
Ballylumford | NIB32 | 249 | 2025-05-07 10:00 | 2025-05-07 11:00 | F | 0
Moneypoint | MP1 | 285 | 2025-05-07 22:00 | 2025-07-25 22:00 | S | 79
Lisdrum | LF1 | 60 | 2025-05-08 07:30 | 2025-05-08 17:00 | F | 0.38
Shannonbridge | SQ1 | 262 | 2025-05-08 08:00 | 2025-05-08 17:00 | 224 | 0.33
Lisahally | NILPS | 17.6 | 2025-05-09 06:00 | 2025-05-09 07:00 | F | 0
Shannonbridge | SQ1 | 262 | 2025-05-09 08:00 | 2025-05-09 17:00 | 192 | 0.33
Great Island | GI4 | 464 | 2025-05-10 | 2025-06-09 | F | 30
Drybridge | IW1 | 17 | 2025-05-10 | 2025-05-23 | F | 13
Lisahally | NILPS | 17.6 | 2025-05-11 06:00 | 2025-05-25 18:00 | S | 14.5
Edenderry | ED1 | 118 | 2025-05-11 06:30 | 2025-05-12 23:00 | 70 | 1.67
Seal Rock | SK3 | 83 | 2025-05-12 06:00 | 2025-05-15 18:00 | S | 3.5
Ardnacrusha | AA3 | 19 | 2025-05-12 08:00 | 2025-05-16 20:00 | F | 4.5
Shannonbridge | SQ1 | 262 | 2025-05-12 08:00 | 2025-05-12 17:00 | 224 | 0.33
Castlereagh BESS | NICSB | 50 | 2025-05-12 08:00 | 2025-05-16 17:00 | S | 4.33
Aghada | AD3 | 19 | 2025-05-12 10:00 | 2025-05-12 12:00 | F | 0.08
Coolkeeragh | NIC30 | 408 | 2025-05-12 12:00 | 2025-05-13 19:00 | S | 1.25
Aghada | AD2 | 449 | 2025-05-12 14:00 | 2025-05-13 | F | 0.42
Inchicore | IH1 | 30 | 2025-05-12 14:00 | 2025-05-12 16:00 | F | 0.08
Seal Rock | SK4 | 83 | 2025-05-13 | 2025-05-15 12:00 | S | 2.5
Shannonbridge | SQ1 | 262 | 2025-05-13 08:00 | 2025-05-13 17:00 | 224 | 0.33
Poolbeg | PB8 | 75 | 2025-05-13 10:00 | 2025-05-13 12:00 | F | 0.08
Turlough Hill | TH1 | 73 | 2025-05-13 10:00 | 2025-05-13 14:00 | F | 0.17
Irishtown | IS2 | 30 | 2025-05-13 14:00 | 2025-05-13 16:00 | F | 0.08
Huntstown | HNC | 342 | 2025-05-13 17:00 | 2025-05-27 21:00 | 215 | 14.17
Aghada | AD2 | 449 | 2025-05-14 04:30 | 2025-05-14 17:00 | F | 0.5
Kilroot | NIKGT6 | 350 | 2025-05-14 06:00 | 2025-05-16 20:00 | F | 2.58
Liffey | LI5 | 4 | 2025-05-14 08:00 | 2025-05-30 17:00 | F | 16.33
Shannonbridge | SQ1 | 262 | 2025-05-14 08:00 | 2025-05-14 17:00 | 224 | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-15 08:00 | 2025-05-15 17:00 | 224 | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-16 08:00 | 2025-05-16 17:00 | 224 | 0.33
Rhode | RP1 | 52 | 2025-05-16 09:00 | 2025-06-03 17:00 | S | 18.33
Aghada | AD2 | 449 | 2025-05-16 09:30 | 2025-05-16 19:00 | F | 0.38
Lee | LE3 | 8 | 2025-05-16 20:00 | 2025-05-30 20:00 | F | 14
Aghada | AD2 | 449 | 2025-05-17 01:00 | 2025-05-17 14:30 | F | 0.54
EWIC | EW1 | 500 | 2025-05-17 04:00 | 2025-05-21 11:00 | F | 4.25
Turlough Hill | TH2 | 73 | 2025-05-17 07:30 | 2025-05-17 18:00 | F | 0.42
Rhode | RP2 | 52 | 2025-05-17 09:00 | 2025-06-03 17:00 | S | 17.33
Aghada | AD2 | 449 | 2025-05-18 14:00 | 2025-05-20 17:00 | F | 2.08
Irishtown | IS2 | 30 | 2025-05-19 06:00 | 2025-05-24 19:00 | S | 5.5
Irishtown | IS3 | 64 | 2025-05-19 06:00 | 2025-05-24 19:00 | S | 5.5
Erne | ER1 | 10 | 2025-05-19 08:00 | 2025-05-23 20:00 | S | 4.5
Shannonbridge | SQ1 | 262 | 2025-05-19 08:00 | 2025-05-19 17:00 | 224 | 0.33
Poolbeg | PB7 | 64 | 2025-05-19 08:30 | 2025-05-19 17:00 | F | 0.33
Aghada | AT4 | 90 | 2025-05-19 10:00 | 2025-05-19 22:00 | F | 0.5
Shannonbridge | SQ1 | 262 | 2025-05-20 08:00 | 2025-05-20 17:00 | 224 | 0.33
Edenderry | ED1 | 118 | 2025-05-20 08:00 | 2025-05-26 11:30 | F | 6.12
Drumkee BESS | NIDK1 | 50 | 2025-05-20 20:00 | 2025-05-21 17:30 | F | 0.88
Kilroot | NIKGT7 | 350 | 2025-05-21 06:00 | 2025-05-24 22:00 | F | 3.67
Kilroot | NIKGT6 | 350 | 2025-05-21 07:00 | 2025-05-21 08:30 | F | 0.04
Shannonbridge | SQ1 | 262 | 2025-05-21 08:00 | 2025-05-21 17:00 | 224 | 0.33
Corduff | FG2 | 64 | 2025-05-21 08:30 | 2025-05-21 17:00 | F | 0.33
Drumkee BESS | NIDK1 | 50 | 2025-05-21 21:00 | 2025-05-22 19:30 | F | 0.92
Shannonbridge | SQ1 | 262 | 2025-05-22 08:00 | 2025-05-22 17:00 | 224 | 0.33
Tarbert | TB5 | 160 | 2025-05-22 08:00 | 2025-05-22 17:00 | 47 | 0.33
Corduff | FG2 | 64 | 2025-05-22 08:30 | 2025-05-22 17:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-23 08:00 | 2025-05-23 17:00 | 224 | 0.33
Lisahally | NILPS | 17.6 | 2025-05-25 18:00 | 2025-05-29 11:30 | F | 3.71
Shannonbridge | SQ1 | 262 | 2025-05-26 08:00 | 2025-05-26 17:00 | 224 | 0.33
Whitegate | WG1 | 444 | 2025-05-26 08:30 | 2025-05-26 23:00 | F | 0.58
Edenderry | ED1 | 118 | 2025-05-26 11:30 | 2025-05-26 23:00 | 41 | 0.46
Edenderry | ED1 | 118 | 2025-05-26 23:00 | 2025-05-29 07:00 | F | 2.33
EWIC | EW1 | 500 | 2025-05-27 07:00 | 2025-05-30 | F | 2.67
Shannonbridge | SQ1 | 262 | 2025-05-27 08:00 | 2025-05-27 17:00 | 224 | 0.33
Kilroot | NIKGT6 | 350 | 2025-05-27 08:00 | 2025-05-30 20:00 | F | 3.5
Shannonbridge | SQ1 | 262 | 2025-05-28 08:00 | 2025-05-28 17:00 | 224 | 0.33
Huntstown | HN2 | 402 | 2025-05-28 23:00 | 2025-06-25 17:00 | F | 27.75
Shannonbridge | SQ1 | 262 | 2025-05-29 08:00 | 2025-05-29 17:00 | 224 | 0.33
Shannonbridge | SQ1 | 262 | 2025-05-30 08:00 | 2025-05-30 17:00 | 224 | 0.33
Turlough Hill | TH1 | 73 | 2025-05-30 14:00 | 2025-05-30 16:00 | F | 0.08
Edenderry | ED1 | 118 | 2025-05-30 20:30 | 2025-06-03 08:00 | 90 | 3.46
Kilroot | NIKGT3 | 42 | 2025-06-02 06:00 | 2025-06-06 14:00 | F | 4.33
Lee | LE3 | 8 | 2025-06-02 07:30 | 2025-10-01 16:00 | F | 121.33
Shannonbridge | SQ1 | 262 | 2025-06-02 08:00 | 2025-06-02 17:00 | 224 | 0.33
Lee | LE1 | 15 | 2025-06-03 08:00 | 2025-06-13 20:00 | S | 10.5
Shannonbridge | SQ1 | 262 | 2025-06-03 08:00 | 2025-06-03 17:00 | 224 | 0.33
Irishtown | IS2 | 30 | 2025-06-03 14:00 | 2025-06-03 15:00 | F | 0
Poolbeg | PB4 | 156 | 2025-06-03 22:00 | 2025-06-06 | F | 2.08
Poolbeg | PB6 | 168 | 2025-06-03 22:00 | 2025-06-14 18:00 | 84 | 10.83
Shannonbridge | SQ1 | 262 | 2025-06-04 08:00 | 2025-06-04 17:00 | 224 | 0.33
Lee | LE2 | 4 | 2025-06-04 08:00 | 2025-06-12 20:00 | S | 8.5
Kilroot | NIKGT4 | 42 | 2025-06-04 09:00 | 2025-06-05 17:00 | S | 1.33
Kilroot | NIKGT6 | 350 | 2025-06-04 12:00 | 2025-06-04 15:00 | F | 0.08
Shannonbridge | SQ1 | 262 | 2025-06-05 08:00 | 2025-06-05 17:00 | 224 | 0.33
Huntstown | HNC | 342 | 2025-06-05 09:00 | 2025-06-05 13:30 | 220 | 0.17
Kilroot | NIKGT4 | 42 | 2025-06-05 17:00 | 2025-06-06 12:30 | F | 0.79
Poolbeg | PB4 | 156 | 2025-06-06 | 2025-06-14 20:00 | S | 8.83
Shannonbridge | SQ1 | 262 | 2025-06-06 08:00 | 2025-06-06 17:00 | 224 | 0.33
Irishtown | IS3 | 64 | 2025-06-06 11:30 | 2025-06-09 19:00 | F | 3.29
Ardnacrusha | AA4 | 24 | 2025-06-07 11:00 | 2025-06-09 14:30 | F | 2.12
Edenderry | ED1 | 118 | 2025-06-08 04:00 | 2025-06-20 11:00 | 55 | 12.25
Seal Rock | SK4 | 83 | 2025-06-09 06:00 | 2025-06-13 18:00 | S | 4.5
Ardnacrusha | AA1 | 21 | 2025-06-09 08:00 | 2025-06-13 20:00 | F | 4.5
Shannonbridge | SQ1 | 262 | 2025-06-09 08:00 | 2025-06-09 17:00 | 224 | 0.33
Turlough Hill | TH3 | 73 | 2025-06-09 21:30 | 2025-06-10 13:00 | F | 0.62
Shannonbridge | SQ1 | 262 | 2025-06-10 08:00 | 2025-06-10 17:00 | 224 | 0.33
Ballylumford | NIB32 | 249 | 2025-06-10 19:00 | 2025-06-13 19:00 | S | 3
Shannonbridge | SQ1 | 262 | 2025-06-11 08:00 | 2025-06-11 17:00 | 224 | 0.33
Castlereagh BESS | NICSB | 50 | 2025-06-11 08:30 | 2025-06-11 11:30 | F | 0.08
Aghada | AD3 | 19 | 2025-06-11 09:30 | 2025-06-11 12:30 | F | 0.08
Aghada | AD4 | 75 | 2025-06-11 13:30 | 2025-06-11 16:30 | F | 0.08
Mullavilly BESS | NIMZ1 | 50 | 2025-06-11 16:00 | 2025-06-12 21:00 | F | 1.17
Lisahally | NILPS | 17.6 | 2025-06-11 22:00 | 2025-06-12 16:30 | F | 0.75
Moneypoint | MP3 | 285 | 2025-06-12 05:00 | 2025-06-12 10:00 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-06-12 08:00 | 2025-06-12 17:00 | 224 | 0.33
Aghada | AD5 | 75 | 2025-06-12 09:30 | 2025-06-12 12:30 | F | 0.08
Moneypoint | MP3 | 285 | 2025-06-12 10:00 | 2025-06-30 11:30 | 230 | 18.04
Moyle | MOYLE | 450 | 2025-06-12 14:30 | 2025-06-14 23:00 | F | 2.33
Rhode | RP1 | 52 | 2025-06-12 17:00 | 2025-06-14 16:00 | F | 1.92
Shannonbridge | SQ1 | 262 | 2025-06-13 08:00 | 2025-06-13 17:00 | 224 | 0.33
Tawnaghmore | TP1 | 52 | 2025-06-13 09:00 | 2025-06-27 17:00 | S | 14.33
Tawnaghmore | TP3 | 52 | 2025-06-13 09:00 | 2025-06-27 17:00 | S | 14.33
Lisahally | NILPS | 17.6 | 2025-06-13 21:00 | 2025-06-15 13:30 | F | 1.67
Rhode | RP2 | 52 | 2025-06-14 12:00 | 2025-06-14 15:00 | F | 0.08
Poolbeg | PB6 | 168 | 2025-06-14 18:00 | 2025-06-16 18:00 | F | 2
Poolbeg | PB5 | 153 | 2025-06-15 | 2025-06-28 20:00 | F | 13.83
Aghada | AD2 | 449 | 2025-06-15 18:30 | 2025-06-16 08:00 | F | 0.54
Moneypoint | MP5 | 1 | 2025-06-16 | 2025-06-19 19:00 | S | 3.75
Moneypoint | MP2 | 285 | 2025-06-16 | 2025-06-19 19:00 | F | 3.75
Dunsoghly | DG1 | 50 | 2025-06-16 08:00 | 2025-06-19 17:00 | F | 3.33
Shannonbridge | SQ1 | 262 | 2025-06-16 08:00 | 2025-06-16 17:00 | 224 | 0.33
Liffey | LI5 | 4 | 2025-06-16 08:00 | 2025-06-18 13:00 | F | 2.17
Northwall | NW8 | 199 | 2025-06-16 08:00 | 2025-06-18 18:00 | 160 | 2.42
Kilroot | NIKGT4 | 42 | 2025-06-16 08:00 | 2025-06-16 16:00 | F | 0.33
Poolbeg | PB6 | 168 | 2025-06-16 18:00 | 2025-06-20 20:00 | 84 | 4.08
Ballylumford | NIB10 | 94 | 2025-06-16 19:00 | 2025-06-19 19:00 | S | 3
Whitebank | DW1 | 61.5 | 2025-06-16 21:00 | 2025-06-17 15:00 | F | 0.75
Lisdrum | LF1 | 60 | 2025-06-17 08:00 | 2025-06-17 18:00 | 30 | 0.42
Shannonbridge | SQ1 | 262 | 2025-06-17 08:00 | 2025-06-17 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-18 08:00 | 2025-06-18 18:00 | 30 | 0.42
Shannonbridge | SQ1 | 262 | 2025-06-18 08:00 | 2025-06-18 17:00 | 224 | 0.33
Ardnacrusha | AA4 | 24 | 2025-06-18 08:00 | 2025-06-24 08:30 | F | 6
Ardnacrusha | AA3 | 19 | 2025-06-18 08:00 | 2025-06-18 16:00 | F | 0.33
Carmeen | NICMN | 20 | 2025-06-18 09:00 | 2025-06-18 15:00 | F | 0.25
Lisdrum | LF1 | 60 | 2025-06-19 08:00 | 2025-06-19 18:00 | F | 0.42
Shannonbridge | SQ1 | 262 | 2025-06-19 08:00 | 2025-06-19 17:00 | 224 | 0.33
Northwall | NW8 | 199 | 2025-06-19 08:00 | 2025-06-19 17:00 | 127 | 0.33
Moneypoint | MP2 | 285 | 2025-06-19 19:00 | 2025-06-20 | 250 | 0.17
Ballylumford | NIB10 | 94 | 2025-06-19 19:00 | 2025-06-21 15:30 | F | 1.83
Moneypoint | MP2 | 285 | 2025-06-20 | 2025-06-25 22:00 | F | 5.92
Northwall | NW8 | 199 | 2025-06-20 08:00 | 2025-06-21 18:00 | 160 | 1.42
Shannonbridge | SQ1 | 262 | 2025-06-20 08:00 | 2025-06-20 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-20 08:00 | 2025-06-20 18:00 | 30 | 0.42
Edenderry | ED1 | 118 | 2025-06-20 11:00 | 2025-07-22 08:00 | S | 31.83
Poolbeg | PB6 | 168 | 2025-06-20 20:00 | 2025-06-28 20:00 | F | 8
Irishtown | IS3 | 64 | 2025-06-21 03:30 | 2025-06-30 17:00 | F | 9.54
Lisdrum | LF1 | 60 | 2025-06-21 08:00 | 2025-06-21 18:00 | 30 | 0.42
Moyle | MOYLE | 450 | 2025-06-21 17:00 | 2025-06-21 19:00 | 250 | 0.08
Lisdrum | LF1 | 60 | 2025-06-22 08:00 | 2025-06-22 18:00 | 30 | 0.42
Aghada | AT1 | 90 | 2025-06-23 | 2025-06-27 | S | 4
Kilroot | NIKGT4 | 42 | 2025-06-23 06:00 | 2025-06-27 13:30 | F | 4.29
Northwall | NW8 | 199 | 2025-06-23 08:00 | 2025-06-25 18:00 | 160 | 2.42
Lisdrum | LF1 | 60 | 2025-06-23 08:00 | 2025-06-23 18:00 | 30 | 0.42
Shannonbridge | SQ1 | 262 | 2025-06-23 08:00 | 2025-06-23 17:00 | 224 | 0.33
Tynagh | TYC | 404 | 2025-06-23 08:00 | 2025-06-23 17:00 | F | 0.33
Ballydown BESS | NIBLD | 12 | 2025-06-23 09:30 | 2025-06-23 14:30 | F | 0.17
Ardnacrusha | AA3 | 19 | 2025-06-23 12:00 | 2025-06-30 14:30 | F | 7.08
Shannonbridge | SQ1 | 262 | 2025-06-24 08:00 | 2025-06-24 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-24 08:00 | 2025-06-24 18:00 | 30 | 0.42
Tarbert | TB5 | 160 | 2025-06-24 08:00 | 2025-06-25 17:00 | F | 1.33
Ballydown BESS | NIBLD | 12 | 2025-06-24 09:00 | 2025-06-24 19:00 | F | 0.42
Shannonbridge | SQ1 | 262 | 2025-06-25 08:00 | 2025-06-25 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-25 08:00 | 2025-06-25 18:00 | 30 | 0.42
Ballydown BESS | NIBLD | 12 | 2025-06-25 08:30 | 2025-06-25 17:30 | F | 0.33
Liffey | LI5 | 4 | 2025-06-25 09:00 | 2025-06-25 15:00 | F | 0.25
Moneypoint | MP2 | 285 | 2025-06-25 22:00 | 2025-07-05 | 250 | 9.08
Shannonbridge | SQ1 | 262 | 2025-06-26 08:00 | 2025-06-26 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-26 08:00 | 2025-06-26 18:00 | 30 | 0.42
Northwall | NW8 | 199 | 2025-06-26 08:00 | 2025-06-28 18:00 | 160 | 2.42
Whitebank | DW1 | 61.5 | 2025-06-26 21:00 | 2025-06-27 15:00 | F | 0.75
Coolkeeragh | NIC30 | 408 | 2025-06-27 | 2025-08-13 | S | 47
Shannonbridge | SQ1 | 262 | 2025-06-27 08:00 | 2025-06-27 17:00 | 224 | 0.33
Lisdrum | LF1 | 60 | 2025-06-27 08:00 | 2025-06-27 18:00 | 30 | 0.42
Aghada | AD2 | 449 | 2025-06-27 22:00 | 2025-06-29 22:00 | F | 2
Aghada | AT1 | 90 | 2025-06-28 15:00 | 2025-06-29 14:30 | F | 0.96
Ballylumford | NIB31 | 249 | 2025-06-29 05:00 | 2025-07-02 17:00 | F | 3.5
Shannonbridge | SQ1 | 262 | 2025-06-29 08:00 | 2025-06-30 08:00 | 128 | 1
Shannonbridge | SQ1 | 262 | 2025-06-30 08:00 | 2025-06-30 17:00 | 96 | 0.33
Erne | ER3 | 23 | 2025-06-30 08:00 | 2025-07-11 20:00 | S | 11.5
Northwall | NW8 | 199 | 2025-06-30 08:00 | 2025-07-02 18:00 | 160 | 2.42
Inchicore | IH1 | 30 | 2025-06-30 09:30 | 2025-06-30 11:30 | F | 0.08
Moneypoint | MP3 | 285 | 2025-06-30 11:30 | 2025-07-21 18:00 | F | 21.25
Irishtown | IS2 | 30 | 2025-06-30 12:00 | 2025-06-30 14:00 | F | 0.08
Poolbeg | PB8 | 75 | 2025-06-30 14:30 | 2025-06-30 16:30 | F | 0.08
Tynagh | TYC | 404 | 2025-06-30 15:00 | 2025-06-30 20:30 | F | 0.21
Shannonbridge | SQ1 | 262 | 2025-07-01 08:00 | 2025-07-01 17:00 | 96 | 0.33
Aghada | AT4 | 90 | 2025-07-01 18:30 | 2025-07-02 12:00 | F | 0.71
Shannonbridge | SQ1 | 262 | 2025-07-02 08:00 | 2025-07-02 17:00 | 96 | 0.33
Turlough Hill | TH1 | 73 | 2025-07-02 10:00 | 2025-07-02 15:00 | F | 0.17
Kilroot | NIKGT2 | 29 | 2025-07-02 17:30 | 2025-07-03 13:30 | F | 0.83
Ballylumford | NIB31 | 249 | 2025-07-02 20:00 | 2025-07-04 05:30 | 161 | 1.38
Shannonbridge | SQ1 | 262 | 2025-07-03 08:00 | 2025-07-03 17:00 | 96 | 0.33
Northwall | NW8 | 199 | 2025-07-03 08:00 | 2025-07-05 18:00 | 160 | 2.42
Inchicore | IH1 | 30 | 2025-07-03 09:30 | 2025-07-03 14:30 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-07-04 08:00 | 2025-07-04 17:00 | 96 | 0.33
Irishtown | IS2 | 30 | 2025-07-04 09:30 | 2025-07-04 14:30 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-07-05 08:00 | 2025-07-05 17:00 | 96 | 0.33
Moyle | MOYLE | 450 | 2025-07-06 08:00 | 2025-07-11 23:00 | S | 5.58
Great Island | GI4 | 464 | 2025-07-06 13:30 | 2025-07-06 15:30 | F | 0.08
Cloniffeen | SI1 | 50 | 2025-07-07 08:00 | 2025-07-08 17:00 | S | 1.33
Northwall | NW8 | 199 | 2025-07-07 08:00 | 2025-07-08 18:00 | F | 1.42
Shannonbridge | SQ1 | 262 | 2025-07-07 08:00 | 2025-07-07 17:00 | 96 | 0.33
Cloniffeen | SI2 | 50 | 2025-07-07 08:00 | 2025-07-08 17:00 | S | 1.33
Shannonbridge | SQ1 | 262 | 2025-07-08 08:00 | 2025-07-08 17:00 | 96 | 0.33
Shannonbridge | SQ1 | 262 | 2025-07-09 08:00 | 2025-07-09 17:00 | 96 | 0.33
Shannonbridge | SQ1 | 262 | 2025-07-10 08:00 | 2025-07-10 17:00 | 96 | 0.33
Irishtown | IS3 | 64 | 2025-07-10 14:00 | 2025-07-14 17:00 | F | 4.08
Shannonbridge | SQ1 | 262 | 2025-07-11 08:00 | 2025-07-11 17:00 | 96 | 0.33
Shannonbridge | SQ1 | 262 | 2025-07-12 08:00 | 2025-07-12 17:00 | 96 | 0.33
Seal Rock | SK3 | 83 | 2025-07-13 06:00 | 2025-07-31 18:00 | S | 18.5
Shannonbridge | SQ1 | 262 | 2025-07-13 08:00 | 2025-07-13 17:00 | 96 | 0.33
Tawnaghmore | TP1 | 52 | 2025-07-14 | 2025-07-22 | 30 | 8
Shannonbridge | SQ1 | 262 | 2025-07-14 08:00 | 2025-07-14 17:00 | 96 | 0.33
Aghada | AT4 | 90 | 2025-07-14 10:00 | 2025-07-16 22:00 | F | 2.5
Poolbeg | PB8 | 75 | 2025-07-14 11:00 | 2025-07-14 13:00 | F | 0.08
Shannonbridge | SQ1 | 262 | 2025-07-15 08:00 | 2025-07-15 17:00 | 96 | 0.33
Aghada | AD3 | 19 | 2025-07-15 09:30 | 2025-07-15 14:30 | F | 0.17
Ballylumford | NIB32 | 249 | 2025-07-15 13:30 | 2025-07-15 20:00 | F | 0.25
Shannonbridge | SQ1 | 262 | 2025-07-16 08:00 | 2025-07-16 17:00 | 96 | 0.33
Lisdrum | LF1 | 60 | 2025-07-17 07:00 | 2025-07-17 17:00 | F | 0.42
Shannonbridge | SQ1 | 262 | 2025-07-17 08:00 | 2025-07-17 17:00 | 96 | 0.33
Ballylumford | NIBGT1 | 58 | 2025-07-17 08:00 | 2025-07-17 16:00 | 29 | 0.33
Aghada | AD4 | 75 | 2025-07-17 09:30 | 2025-07-17 14:30 | S | 0.17
Shannonbridge | SQ1 | 262 | 2025-07-18 08:00 | 2025-07-18 17:00 | 96 | 0.33
Aghada | AD5 | 75 | 2025-07-18 09:30 | 2025-07-18 14:30 | F | 0.17
Ballylumford | NIB31 | 249 | 2025-07-18 14:00 | 2025-08-08 16:00 | F | 21.08
Tynagh | TYC | 404 | 2025-07-19 23:00 | 2025-07-23 23:00 | F | 4
Shannonbridge | SQ1 | 262 | 2025-07-20 08:00 | 2025-08-29 20:00 | F | 40.5
Liffey | LI5 | 4 | 2025-07-20 22:30 | 2025-07-22 08:30 | F | 1.42
Ballylumford | NIBGT1 | 58 | 2025-07-21 06:00 | 2025-07-26 13:00 | F | 5.25
Derrycarney | LU1 | 50 | 2025-07-21 08:00 | 2025-07-22 17:00 | S | 1.33
Tawnaghmore | TP3 | 52 | 2025-07-21 08:00 | 2025-07-25 17:00 | F | 4.33
Tarbert | TB5 | 160 | 2025-07-21 08:00 | 2025-07-22 17:00 | 100 | 1.33
Derrycarney | LU2 | 50 | 2025-07-21 08:00 | 2025-07-22 17:00 | S | 1.33
Aghada | AT4 | 90 | 2025-07-22 15:30 | 2025-07-23 18:00 | F | 1.08
Edenderry | ED1 | 118 | 2025-07-22 16:30 | 2025-07-22 22:30 | 41 | 0.25
Derrycarney | LU1 | 50 | 2025-07-22 17:00 | 2025-07-23 17:00 | F | 1
Derrycarney | LU2 | 50 | 2025-07-22 17:00 | 2025-07-23 17:00 | F | 1
Edenderry | ED1 | 118 | 2025-07-23 06:30 | 2025-07-24 14:00 | 41 | 1.29
Tarbert | TB5 | 160 | 2025-07-23 08:00 | 2025-07-24 17:00 | 100 | 1.33
Aghada | AD2 | 449 | 2025-07-23 20:30 | 2025-07-23 21:30 | F | 0
Kilroot | NIKGT4 | 42 | 2025-07-23 20:30 | 2025-07-23 22:00 | F | 0.04
Kilroot | NIKGT3 | 42 | 2025-07-23 20:30 | 2025-07-23 22:00 | F | 0.04
Edenderry | ED1 | 118 | 2025-07-24 14:00 | 2025-07-25 23:00 | 52 | 1.33
Tawnaghmore | TP1 | 52 | 2025-07-25 | 2025-10-01 | 30 | 68
Tarbert | TB5 | 160 | 2025-07-25 08:00 | 2025-07-26 17:00 | 100 | 1.33
Ballylumford | NIB10 | 94 | 2025-07-25 10:30 | 2025-07-25 12:30 | 40 | 0.08
Moneypoint | MP1 | 285 | 2025-07-25 22:00 | 2025-10-16 22:00 | F | 83
Edenderry | ED1 | 118 | 2025-07-25 23:00 | 2025-07-29 08:30 | 52 | 3.38
Moneypoint | MP2 | 285 | 2025-07-28 13:00 | 2025-08-01 15:00 | F | 4.08
Edenderry | ED5 | 58 | 2025-07-29 08:00 | 2025-09-01 17:00 | S | 34.33
Edenderry | ED3 | 58 | 2025-07-29 08:00 | 2025-08-28 18:00 | S | 30.42
Edenderry | ED1 | 118 | 2025-07-29 08:30 | 2025-07-30 08:30 | 80 | 1
Turlough Hill | TH1 | 73 | 2025-07-29 23:00 | 2025-07-30 17:00 | F | 0.75
Turlough Hill | TH2 | 73 | 2025-07-29 23:00 | 2025-07-30 17:00 | F | 0.75
Lisdrum | LF1 | 60 | 2025-07-30 08:00 | 2025-07-30 14:00 | F | 0.25
Edenderry | ED1 | 118 | 2025-07-30 08:30 | 2025-07-31 08:30 | 90 | 1
Turlough Hill | TH3 | 73 | 2025-07-30 09:00 | 2025-07-30 17:00 | F | 0.33
Turlough Hill | TH4 | 73 | 2025-07-30 09:00 | 2025-07-30 17:00 | F | 0.33
Edenderry | ED1 | 118 | 2025-07-31 08:30 | 2025-08-03 23:00 | 100 | 3.58
Kilroot | NIKGT1 | 29 | 2025-07-31 09:00 | 2025-07-31 10:00 | F | 0
Kilroot | NIKGT2 | 29 | 2025-07-31 11:00 | 2025-07-31 12:00 | F | 0
Seal Rock | SK3 | 83 | 2025-07-31 17:00 | 2025-08-10 10:00 | F | 9.67
Kilroot | NIKGT4 | 42 | 2025-08-01 13:00 | 2025-08-01 15:00 | F | 0.08
Dublin Bay | DB1 | 415 | 2025-08-03 15:30 | 2025-08-05 13:00 | 214 | 1.88
Edenderry | ED1 | 118 | 2025-08-04 08:00 | 2025-08-08 23:00 | 50 | 4.58
Coolkeeragh | NICGT8 | 53 | 2025-08-04 11:00 | 2025-08-05 11:30 | 26 | 1
Tarbert | TB5 | 160 | 2025-08-05 08:00 | 2025-08-06 17:00 | 100 | 1.33
Corduff | FG2 | 64 | 2025-08-06 08:00 | 2025-08-06 17:00 | F | 0.33
Edenderry | ED1 | 118 | 2025-08-08 23:00 | 2025-08-16 04:00 | 100 | 7.17
Poolbeg | PB7 | 64 | 2025-08-11 06:00 | 2025-08-16 19:00 | S | 5.5
Aghada | AT1 | 90 | 2025-08-12 | 2025-08-13 | F | 1
Ballylumford | NIBGT2 | 58 | 2025-08-12 18:30 | 2025-08-12 20:00 | F | 0.04
Ballylumford | NIBGT1 | 58 | 2025-08-12 18:30 | 2025-08-12 20:00 | F | 0.04
Ballylumford | NIBGT1 | 58 | 2025-08-12 22:30 | 2025-08-13 10:00 | F | 0.46
Ballylumford | NIBGT2 | 58 | 2025-08-12 22:30 | 2025-08-13 10:00 | F | 0.46
Coolkeeragh | NIC30 | 408 | 2025-08-13 | 2025-08-19 | F | 6
Kilroot | NIKGT6 | 350 | 2025-08-13 11:00 | 2025-08-13 15:00 | F | 0.17
Edenderry | ED1 | 118 | 2025-08-16 04:00 | 2025-08-19 18:00 | F | 3.58
Poolbeg | PB6 | 168 | 2025-08-17 05:30 | 2025-08-20 15:00 | F | 3.38
Aghada | AD2 | 449 | 2025-08-17 23:00 | 2025-08-22 | F | 4
Ardnacrusha | AA4 | 24 | 2025-08-18 08:00 | 2025-10-03 16:00 | F | 46.33
Coolkeeragh | NIC30 | 408 | 2025-08-19 | 2025-10-15 20:00 | F | 57.83
Kilroot | NIKGT4 | 42 | 2025-08-19 12:30 | 2025-08-19 18:30 | F | 0.25
Edenderry | ED1 | 118 | 2025-08-19 18:00 | 2025-08-20 07:00 | 41 | 0.5
Kilroot | NIKGT3 | 42 | 2025-08-19 23:00 | 2025-08-20 01:30 | F | 0.08
Kilroot | NIKGT4 | 42 | 2025-08-19 23:30 | 2025-08-22 13:30 | F | 2.58
Kilroot | NIKGT3 | 42 | 2025-08-20 01:30 | 2025-08-24 10:30 | F | 4.33
Edenderry | ED1 | 118 | 2025-08-20 07:00 | 2025-08-20 11:00 | 41 | 0.17
Edenderry | ED1 | 118 | 2025-08-20 11:00 | 2025-08-21 09:00 | 41 | 0.92
Edenderry | ED1 | 118 | 2025-08-21 09:00 | 2025-09-27 23:00 | 100 | 37.58
Great Island | GI4 | 464 | 2025-08-21 10:00 | 2025-09-15 | F | 24.58
Tynagh | TYC | 404 | 2025-08-22 20:00 | 2025-11-12 08:00 | F | 81.5
Whitebank | DW1 | 61.5 | 2025-08-24 22:00 | 2025-08-25 15:00 | F | 0.67
Kilroot | NIKGT6 | 350 | 2025-08-25 09:00 | 2025-08-29 18:30 | F | 4.38
Whitebank | DW1 | 61.5 | 2025-08-25 15:00 | 2025-08-30 17:00 | 26 | 5.08
Tarbert | TB5 | 160 | 2025-08-26 08:00 | 2025-08-29 18:00 | 100 | 3.42
Kilroot | NIKGT7 | 350 | 2025-08-26 10:00 | 2025-08-26 13:00 | F | 0.08
Moyle | MOYLE | 450 | 2025-08-26 16:30 | 2025-08-26 17:30 | 250 | 0
Ballylumford | NIB10 | 94 | 2025-08-27 08:00 | 2025-08-27 12:00 | F | 0.17
Erne | ER1 | 10 | 2025-08-28 15:00 | 2025-08-29 16:00 | F | 1
Turlough Hill | TH3 | 73 | 2025-08-28 18:00 | 2025-09-01 16:00 | F | 3.92
Edenderry | ED3 | 58 | 2025-08-28 18:00 | 2025-09-04 15:30 | F | 6.88
Kilroot | NIKGT3 | 42 | 2025-08-28 20:00 | 2025-08-29 18:30 | F | 0.92
Kilroot | NIKGT4 | 42 | 2025-08-28 20:00 | 2025-08-29 18:30 | F | 0.92
Shannonbridge | SQ1 | 262 | 2025-08-29 20:30 | 2025-09-05 17:00 | 128 | 6.83
Whitegate | WG1 | 444 | 2025-08-30 21:00 | 2025-09-09 21:00 | S | 10
Aghada | AT4 | 90 | 2025-09-02 10:00 | 2025-09-05 21:00 | F | 3.42
Seal Rock | SK3 | 83 | 2025-09-02 14:00 | 2025-09-03 18:00 | F | 1.17
Poolbeg | PB7 | 64 | 2025-09-02 18:00 | 2025-09-19 17:00 | F | 16.92
Poolbeg | PB7 | 64 | 2025-09-03 09:00 | 2025-10-31 18:00 | F | 58.33
Erne | ER1 | 10 | 2025-09-04 09:00 | 2025-09-04 16:00 | F | 0.25
Moneypoint | MP3 | 285 | 2025-09-04 16:00 | 2025-09-23 22:00 | F | 19.25
Liffey | LI1 | 15 | 2025-09-05 17:00 | 2025-11-21 17:00 | F | 77
Liffey | LI2 | 15 | 2025-09-05 17:00 | 2025-11-21 17:00 | F | 77
Erne | ER1 | 10 | 2025-09-08 08:00 | 2025-09-08 16:00 | F | 0.33
Shannonbridge | SQ1 | 262 | 2025-09-08 12:00 | 2025-09-08 17:00 | 96 | 0.17
Loughtown | GLK | 500 | 2025-09-08 23:00 | 2025-09-09 11:00 | F | 0.5
Shannonbridge | SQ1 | 262 | 2025-09-09 08:00 | 2025-09-09 14:00 | 96 | 0.25
Kilroot | NIKGT3 | 42 | 2025-09-09 12:00 | 2025-09-09 16:30 | F | 0.17
Shannonbridge | SQ1 | 262 | 2025-09-09 14:00 | 2025-09-09 17:00 | F | 0.08
Whitegate | WG1 | 444 | 2025-09-09 21:00 | 2025-09-16 21:00 | F | 7
Shannonbridge | SQ1 | 262 | 2025-09-10 08:00 | 2025-09-10 17:00 | 96 | 0.33
Kilroot | NIKGT4 | 42 | 2025-09-10 12:00 | 2025-09-10 17:30 | F | 0.21
Shannonbridge | SQ1 | 262 | 2025-09-11 08:00 | 2025-09-11 17:00 | 96 | 0.33
Shannonbridge | SQ1 | 262 | 2025-09-12 08:00 | 2025-09-12 17:00 | 96 | 0.33
Shannonbridge | SQ1 | 262 | 2025-09-12 17:00 | 2025-10-01 12:00 | 128 | 18.75
Poolbeg | PB5 | 153 | 2025-09-14 22:00 | 2025-09-19 20:00 | S | 4.92
Poolbeg | PB6 | 168 | 2025-09-14 22:00 | 2025-09-19 20:00 | 84 | 4.92
Aghada | AT4 | 90 | 2025-09-15 | 2025-09-17 | F | 2
Irishtown | IS3 | 64 | 2025-09-15 06:00 | 2025-09-18 16:00 | S | 3.42
Shannonbridge | SQ1 | 262 | 2025-09-15 08:00 | 2025-09-15 17:00 | 96 | 0.33
Ballylumford | NIB10 | 94 | 2025-09-15 11:30 | 2025-09-15 18:00 | F | 0.25
Lisdrum | LF1 | 60 | 2025-09-16 08:00 | 2025-09-16 18:00 | 30 | 0.42
Shannonbridge | SQ1 | 262 | 2025-09-16 08:00 | 2025-09-16 17:00 | 96 | 0.33
Ballylumford | NIB10 | 94 | 2025-09-16 08:30 | 2025-09-16 11:30 | F | 0.08
Lisdrum | LF1 | 60 | 2025-09-17 08:00 | 2025-09-17 09:30 | 30 | 0.04
Shannonbridge | SQ1 | 262 | 2025-09-17 08:00 | 2025-09-17 17:00 | 96 | 0.33
Lisdrum | LF1 | 60 | 2025-09-17 09:30 | 2025-09-17 12:00 | F | 0.08
Lisdrum | LF1 | 60 | 2025-09-17 12:00 | 2025-09-17 18:00 | 30 | 0.25
EWIC | EW1 | 500 | 2025-09-18 07:00 | 2025-09-19 07:00 | F | 1
Huntstown | HN2 | 402 | 2025-09-19 07:30 | 2025-09-19 18:00 | F | 0.42
Tawnaghmore | TP3 | 52 | 2025-09-19 12:00 | 2025-09-30 17:00 | 30 | 11.17
Ardnacrusha | AA2 | 22 | 2025-09-19 20:00 | 2025-10-20 20:00 | F | 31
Poolbeg | PB6 | 168 | 2025-09-19 20:00 | 2025-09-25 13:30 | 84 | 5.71
Cloniffeen | SI1 | 50 | 2025-09-22 08:00 | 2025-09-22 17:00 | F | 0.33
Cloniffeen | SI2 | 50 | 2025-09-22 08:00 | 2025-09-22 17:00 | F | 0.33
Tarbert | TB5 | 160 | 2025-09-22 17:00 | 2025-10-07 17:00 | 50 | 15
Corduff | FG2 | 64 | 2025-09-23 03:30 | 2025-09-23 17:00 | F | 0.54
Lisdrum | LF1 | 60 | 2025-09-23 08:00 | 2025-09-25 17:00 | S | 2.33
Aghada | AD2 | 449 | 2025-09-23 22:00 | 2025-10-16 | F | 22.08
Shannonbridge | SQ1 | 262 | 2025-09-24 08:00 | 2025-09-24 17:00 | 96 | 0.33
Whitebank | DW1 | 61.5 | 2025-09-24 10:30 | 2025-09-24 14:30 | 30 | 0.17
Shannonbridge | SQ1 | 262 | 2025-09-25 08:00 | 2025-09-25 17:00 | F | 0.33
Whitebank | DW1 | 61.5 | 2025-09-25 20:00 | 2025-09-25 22:00 | 50 | 0.08
Moneypoint | MP3 | 285 | 2025-09-26 12:00 | 2025-09-26 23:00 | F | 0.42
Edenderry | ED1 | 118 | 2025-09-27 23:00 | 2025-10-02 | F | 4
Corduff | FG2 | 64 | 2025-09-29 06:00 | 2025-10-04 19:00 | S | 5.5
Shannonbridge | SQ1 | 262 | 2025-09-30 09:00 | 2025-09-30 17:00 | F | 0.33
Turlough Hill | TH3 | 73 | 2025-10-01 10:00 | 2025-10-01 16:00 | F | 0.25
Turlough Hill | TH4 | 73 | 2025-10-01 10:00 | 2025-10-01 16:00 | F | 0.25
Turlough Hill | TH2 | 73 | 2025-10-01 10:00 | 2025-10-01 16:00 | F | 0.25
Turlough Hill | TH1 | 73 | 2025-10-01 10:00 | 2025-10-01 16:00 | F | 0.25
Edenderry | ED1 | 118 | 2025-10-02 | 2025-10-02 23:00 | 41 | 0.92
Kilroot | NIKGT2 | 29 | 2025-10-07 19:00 | 2025-10-08 19:00 | F | 1
Gorman | GF1 | 50 | 2025-10-09 09:00 | 2025-10-09 17:00 | F | 0.33
Inchicore | IH1 | 30 | 2025-10-10 13:00 | 2025-10-13 07:00 | 20 | 2.75
Whitebank | DW1 | 61.5 | 2025-10-12 | 2025-10-16 | 26 | 4
Inchicore | IH1 | 30 | 2025-10-13 07:00 | 2025-10-18 19:00 | S | 5.5
Aghada | AD4 | 75 | 2025-10-13 07:00 | 2025-10-18 19:00 | F | 5.5
Kells BESS | NIKEB | 50 | 2025-10-13 09:00 | 2025-10-14 16:00 | S | 1.25
Kells BESS | NIKEB | 50 | 2025-10-14 16:00 | 2025-10-17 17:00 | S | 3
Aghada | AD5 | 75 | 2025-10-17 13:00 | 2025-10-23 13:00 | F | 6
Aghada | AD4 | 75 | 2025-10-18 19:00 | 2025-10-23 19:00 | 25 | 5
Ballylumford | NIB32 | 249 | 2025-10-18 19:00 | 2025-10-26 19:00 | F | 8
Tarbert | TB5 | 160 | 2025-10-20 08:00 | 2025-10-23 17:00 | 100 | 3.33
Castlereagh BESS | NICSB | 50 | 2025-10-20 09:00 | 2025-10-20 17:00 | 40 | 0.33
Turlough Hill | TH4 | 73 | 2025-10-21 09:00 | 2025-10-21 14:00 | F | 0.17
Turlough Hill | TH3 | 73 | 2025-10-21 09:00 | 2025-10-21 14:00 | F | 0.17
Turlough Hill | TH1 | 73 | 2025-10-21 09:00 | 2025-10-21 14:00 | F | 0.17
Turlough Hill | TH2 | 73 | 2025-10-21 09:00 | 2025-10-21 14:00 | F | 0.17
Aghada | AD5 | 75 | 2025-10-23 13:00 | 2025-11-02 19:30 | 50 | 10.25
Tarbert | TB5 | 160 | 2025-10-24 08:00 | 2025-10-27 17:00 | 100 | 3.33
Tarbert | TB5 | 160 | 2025-10-28 08:00 | 2025-10-31 17:00 | 100 | 3.33
Mullavilly BESS | NIMZ1 | 50 | 2025-11-01 | 2025-11-03 01:00 | S | 2
Drumkee BESS | NIDK1 | 50 | 2025-11-01 | 2025-11-04 | S | 3
Seal Rock | SK4 | 83 | 2025-11-03 06:00 | 2025-11-05 18:00 | S | 2.5
Dublin Bay | DB1 | 415 | 2025-11-14 22:00 | 2025-11-21 20:00 | F | 6.92
Poolbeg | PB8 | 75 | 2025-11-17 06:00 | 2025-11-28 19:00 | S | 11.5
Poolbeg | PB7 | 64 | 2025-11-24 06:00 | 2025-11-28 19:00 | S | 4.5
Seal Rock | SK3 | 83 | 2025-12-08 06:00 | 2025-12-10 18:00 | S | 2.5
Coolkeeragh | NIC30 | 408 | 2025-12-09 12:00 | 2025-12-12 22:00 | S | 3.42
Edenderry | ED1 | 118 | 2025-12-26 12:00 | 2026-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10