## Outage Plan EirGrid
2028 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2028 | [5 empty] | Feb '2028 |  |  |  | Mar '2028 |  |  |  | Apr '2028 |  |  |  | May '2028 |  |  |  |  | Jun '2028 |  |  |  | Jul '2028 |  |  |  |  | Aug '2028 |  |  |  | Sep '2028 |  |  |  | Oct '2028 |  |  |  |  | Nov '2028 |  |  |  | Dec '2028
|  | Week | 52 '2027 | 1 '2028 | 2 '2028 | 3 '2028 | 4 '2028 | 5 '2028 | 6 '2028 | 7 '2028 | 8 '2028 | 9 '2028 | 10 '2028 | 11 '2028 | 12 '2028 | 13 '2028 | 14 '2028 | 15 '2028 | 16 '2028 | 17 '2028 | 18 '2028 | 19 '2028 | 20 '2028 | 21 '2028 | 22 '2028 | 23 '2028 | 24 '2028 | 25 '2028 | 26 '2028 | 27 '2028 | 28 '2028 | 29 '2028 | 30 '2028 | 31 '2028 | 32 '2028 | 33 '2028 | 34 '2028 | 35 '2028 | 36 '2028 | 37 '2028 | 38 '2028 | 39 '2028 | 40 '2028 | 41 '2028 | 42 '2028 | 43 '2028 | 44 '2028 | 45 '2028 | 46 '2028 | 47 '2028 | 48 '2028 | 49 '2028 | 50 '2028 | 51 '2028 | 52 '2028
Station | Unit | NPR
Aghada | AD2 | 449 | [23 empty] | S | S
Aghada | AD3 | 19 | [14 empty] | S
Aghada | AD4 | 75 | [15 empty] | S | S | [24 empty] | S | S
Aghada | AD5 | 75 | [16 empty] | S | S | [24 empty] | S | S
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA2 | 22 | [20 empty] | S
Ardnacrusha | AA3 | 19 | [24 empty] | S
Ardnacrusha | AA4 | 24 | [37 empty] | S
Aughinish Alumina | EB1 | 25
Ballymakaily | IL1 | 18
Ballymakaily | IL2 | 18
Ballymakaily | IL3 | 18
Ballymakaily | IL4 | 18
Ballymakaily | IL5 | 18
Ballymakaily | IL6 | 18
Banoge | OD1 | 9
Castlelost | LZ1 | 55
Castlelost | LZ2 | 55
Castlelost | LZ3 | 55
Castlelost | LZ4 | 55
Castlelost | LZ5 | 55
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [39 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17
Dublin Bay | DB1 | 415 | [44 empty] | S
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | [21 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Endeco Technologies | EC1 | 53
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 17
Endeco Technologies | EC6 | 4
Enel X | AE1 | 80
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 23
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 5
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [14 empty] | S
Erne | ER2 | 10 | [20 empty] | S
Erne | ER3 | 23 | [24 empty] | S
Erne | ER4 | 23 | [29 empty] | S
EWIC | EW1 | 500 | [14 empty] | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464 | [22 empty] | S | S | S | S
Huntstown | HN2 | 402 | [31 empty] | S | S | S | S | S | S | S | S | S | S | S | S
Huntstown | HNC | 342 | [12 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Inchicore | IH1 | 30 | [41 empty] | S
Irishtown | IS2 | 30 | [20 empty] | S
Irishtown | IS3 | 64 | [37 empty] | S
Kilcumber | OE2 | 25
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [19 empty] | S | S
Lee | LE2 | 4 | [12 empty] | S | S
Lee | LE3 | 8 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Liffey | LI1 | 15 | [19 empty] | S | S
Liffey | LI2 | 15 | [19 empty] | S | S
Liffey | LI4 | 4 | [25 empty] | S | S
Liffey | LI5 | 4 | [22 empty] | S | S
Lisdrum | LF1 | 60
Loughtown | GLK | 500
Moneypoint | MP1 | 285 | [15 empty] | S | S
Moneypoint | MP2 | 285 | [19 empty] | S | S
Moneypoint | MP3 | 285 | [31 empty] | S | S | S
Moneypoint | MP5 | 1 | [24 empty] | S
Northwall | NW8 | 199
Poolbeg | PB4 | 156 | [31 empty] | S | S | S | S | S | S | S | S | S
Poolbeg | PB5 | 153 | [23 empty] | S
Poolbeg | PB6 | 168
Poolbeg | PB7 | 64 | [32 empty] | S
Poolbeg | PB8 | 75 | [18 empty] | S | S | [26 empty] | S | S
Powerhouse Generation | PG1 | 10
Powerhouse Generation | PG2 | 4
Powerhouse Generation | PG6 | 4
Raghra | RG1 | 63
Raghra | RG2 | 1
Rhode | RP1 | 52 | [21 empty] | S | S
Rhode | RP2 | 52 | [21 empty] | S | S
Seal Rock | SK3 | 83 | [27 empty] | S
Seal Rock | SK4 | 83 | [22 empty] | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [25 empty] | S | S
Tawnaghmore | TP3 | 52 | [25 empty] | S | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [13 empty] | S | S | S
Turlough Hill | TH2 | 73 | [13 empty] | S | S | S
Turlough Hill | TH3 | 73 | [13 empty] | S | S | S
Turlough Hill | TH4 | 73 | [13 empty] | S | S | S
Tynagh | TYC | 404 | [35 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 8
Veolia Alternative Energy | DP2 | 21
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 59
VIOTAS | EE2 | 25
VIOTAS | EE3 | 13
VIOTAS | EE4 | 15
VIOTAS | EE5 | 25
VIOTAS | EE6 | 14
VIOTAS | EE7 | 37
VIOTAS | EE8 | 5
VIOTAS | EE9 | 5
VIOTAS | VS1 | 5
VIOTAS | VS2 | 6
VIOTAS | VS6 | 5
Whitebank | DW1 | 62 | [15 empty] | S
Whitegate | WG1 | 444 | [35 empty] | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2027-12-26 12:00 | 2028-01-01 08:00 | S | 5.83
Seal Rock | SK4 | 83 | 2028-02-07 06:00 | 2028-02-09 18:00 | S | 2.5
Seal Rock | SK3 | 83 | 2028-03-06 06:00 | 2028-03-08 18:00 | S | 2.5
Huntstown | HNC | 342 | 2028-03-20 | 2028-07-06 00:30 | S | 108
Lee | LE2 | 4 | 2028-03-20 08:00 | 2028-03-31 20:00 | S | 11.5
Turlough Hill | TH1 | 73 | 2028-03-26 | 2028-04-13 00:30 | S | 18
Turlough Hill | TH2 | 73 | 2028-03-26 | 2028-04-13 00:30 | S | 18
Turlough Hill | TH3 | 73 | 2028-03-26 08:00 | 2028-04-13 18:00 | S | 18.42
Turlough Hill | TH4 | 73 | 2028-03-26 08:00 | 2028-04-13 18:00 | S | 18.42
Aghada | AD3 | 19 | 2028-04-03 | 2028-04-08 00:30 | S | 5
Whitebank | DW1 | 61.5 | 2028-04-03 | 2028-04-08 00:30 | 26 | 5
Lee | LE3 | 8 | 2028-04-03 08:00 | 2028-12-01 20:00 | S | 242.5
Erne | ER1 | 10 | 2028-04-03 08:00 | 2028-04-07 20:00 | S | 4.5
EWIC | EW1 | 500 | 2028-04-03 09:00 | 2028-04-03 21:00 | S | 0.5
EWIC | EW1 | 500 | 2028-04-03 21:00 | 2028-04-07 23:00 | S | 4.08
Ardnacrusha | AA1 | 21 | 2028-04-04 08:00 | 2028-09-29 20:00 | S | 178.5
Aghada | AT1 | 90 | 2028-04-07 | 2028-04-11 20:00 | S | 4.83
Moneypoint | MP1 | 285 | 2028-04-07 | 2028-04-23 00:30 | S | 16
Whitebank | DW1 | 61.5 | 2028-04-08 | 2028-04-18 00:30 | S | 10
Inchicore | IH1 | 30 | 2028-04-10 | 2028-04-13 00:30 | S | 3
Aghada | AD4 | 75 | 2028-04-10 | 2028-04-20 00:30 | S | 10
Edenderry | ED1 | 118 | 2028-04-13 17:00 | 2028-04-19 08:00 | S | 5.58
Aghada | AT2 | 90 | 2028-04-14 | 2028-04-18 00:30 | S | 4
Whitebank | DW1 | 61.5 | 2028-04-18 | 2028-04-23 00:30 | 26 | 5
Aghada | AD5 | 75 | 2028-04-20 | 2028-04-30 00:30 | S | 10
Aghada | AT4 | 90 | 2028-04-21 | 2028-04-25 00:30 | S | 4
Poolbeg | PB8 | 75 | 2028-05-01 | 2028-05-11 00:30 | S | 10
Moneypoint | MP2 | 285 | 2028-05-05 | 2028-05-21 00:30 | S | 16
Poolbeg | PB6 | 168 | 2028-05-05 | 2028-06-03 00:30 | 84 | 29
Liffey | LI1 | 15 | 2028-05-08 | 2028-05-19 00:30 | S | 11
Liffey | LI2 | 15 | 2028-05-08 | 2028-05-19 00:30 | S | 11
Lee | LE1 | 15 | 2028-05-08 08:00 | 2028-05-19 20:00 | S | 11.5
Seal Rock | SK3 | 83 | 2028-05-08 18:00 | 2028-05-11 18:00 | S | 3
Seal Rock | SK4 | 83 | 2028-05-09 | 2028-05-11 12:00 | S | 2.5
Irishtown | IS2 | 30 | 2028-05-15 | 2028-05-20 00:30 | S | 5
Ardnacrusha | AA2 | 22 | 2028-05-15 08:00 | 2028-05-19 20:00 | S | 4.5
Erne | ER2 | 10 | 2028-05-15 08:00 | 2028-05-19 20:00 | S | 4.5
Rhode | RP1 | 52 | 2028-05-19 | 2028-06-02 00:30 | S | 14
Rhode | RP2 | 52 | 2028-05-19 | 2028-06-02 00:30 | S | 14
Poolbeg | PB4 | 156 | 2028-05-26 | 2028-06-03 00:30 | S | 8
Poolbeg | PB6 | 168 | 2028-05-26 | 2028-06-03 00:30 | 84 | 8
Liffey | LI5 | 4 | 2028-05-29 | 2028-06-09 00:30 | S | 11
Seal Rock | SK4 | 83 | 2028-05-29 06:00 | 2028-06-02 18:00 | S | 4.5
Great Island | GI4 | 464 | 2028-06-01 | 2028-06-24 00:30 | S | 23
Poolbeg | PB5 | 153 | 2028-06-04 | 2028-06-10 00:30 | S | 6
Poolbeg | PB6 | 168 | 2028-06-04 | 2028-07-01 00:30 | 84 | 27
Aghada | AD2 | 449 | 2028-06-04 | 2028-06-19 20:00 | S | 15.83
Poolbeg | PB6 | 168 | 2028-06-04 | 2028-06-10 00:30 | 84 | 6
Moneypoint | MP5 | 1 | 2028-06-12 | 2028-06-19 00:30 | S | 7
Northwall | NW8 | 199 | 2028-06-12 08:00 | 2028-06-14 18:00 | 160 | 2.42
Ardnacrusha | AA3 | 19 | 2028-06-12 08:00 | 2028-06-16 20:00 | S | 4.5
Erne | ER3 | 23 | 2028-06-12 08:00 | 2028-06-16 20:00 | S | 4.5
Lisdrum | LF1 | 60 | 2028-06-13 | 2028-06-23 00:30 | 45 | 10
Northwall | NW8 | 199 | 2028-06-15 08:00 | 2028-06-17 18:00 | 160 | 2.42
Tawnaghmore | TP1 | 52 | 2028-06-16 | 2028-06-30 00:30 | S | 14
Tawnaghmore | TP3 | 52 | 2028-06-16 | 2028-06-30 00:30 | S | 14
Liffey | LI4 | 4 | 2028-06-19 | 2028-06-30 00:30 | S | 11
Northwall | NW8 | 199 | 2028-06-19 08:00 | 2028-06-21 18:00 | 160 | 2.42
Northwall | NW8 | 199 | 2028-06-22 08:00 | 2028-06-24 18:00 | 160 | 2.42
Northwall | NW8 | 199 | 2028-06-26 08:00 | 2028-06-28 18:00 | 160 | 2.42
Northwall | NW8 | 199 | 2028-06-29 08:00 | 2028-07-01 18:00 | 160 | 2.42
Edenderry | ED1 | 118 | 2028-06-30 12:00 | 2028-07-28 08:00 | S | 27.83
Seal Rock | SK3 | 83 | 2028-07-03 06:00 | 2028-07-07 18:00 | S | 4.5
Northwall | NW8 | 199 | 2028-07-03 08:00 | 2028-07-04 18:00 | S | 1.42
Erne | ER4 | 23 | 2028-07-17 08:00 | 2028-07-21 20:00 | S | 4.5
Huntstown | HN2 | 402 | 2028-07-28 | 2028-10-21 00:30 | S | 85
Moneypoint | MP3 | 285 | 2028-08-01 | 2028-08-17 00:30 | S | 16
Poolbeg | PB4 | 156 | 2028-08-01 | 2028-10-01 | S | 61
Poolbeg | PB6 | 168 | 2028-08-01 | 2028-10-01 | 84 | 61
Poolbeg | PB7 | 64 | 2028-08-07 | 2028-08-12 00:30 | S | 5
Whitegate | WG1 | 444 | 2028-08-26 | 2028-09-05 00:30 | S | 10
Tynagh | TYC | 404 | 2028-08-27 | 2028-09-06 00:30 | S | 10
Shannonbridge | SQ1 | 262 | 2028-09-04 | 2028-09-06 00:30 | 224 | 2
Shannonbridge | SQ1 | 262 | 2028-09-07 | 2028-09-09 17:30 | 224 | 2.71
Shannonbridge | SQ1 | 262 | 2028-09-11 | 2028-09-13 17:30 | 224 | 2.71
Irishtown | IS3 | 64 | 2028-09-11 | 2028-09-16 00:30 | S | 5
Ardnacrusha | AA4 | 24 | 2028-09-11 08:00 | 2028-09-15 20:00 | S | 4.5
Edenderry | ED3 | 58 | 2028-09-13 08:00 | 2028-09-13 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2028-09-13 08:00 | 2028-09-13 18:00 | S | 0.42
Shannonbridge | SQ1 | 262 | 2028-09-14 | 2028-09-16 00:30 | 224 | 2
Shannonbridge | SQ1 | 262 | 2028-09-16 | 2028-09-17 17:30 | 128 | 1.71
Shannonbridge | SQ1 | 262 | 2028-09-18 | 2028-09-20 00:30 | 224 | 2
Lisdrum | LF1 | 60 | 2028-09-18 | 2028-09-20 00:30 | S | 2
Shannonbridge | SQ1 | 262 | 2028-09-21 08:00 | 2028-09-23 17:30 | 224 | 2.38
Shannonbridge | SQ1 | 262 | 2028-09-25 | 2028-09-27 17:30 | 224 | 2.71
Corduff | FG2 | 64 | 2028-09-25 | 2028-09-30 00:30 | S | 5
Seal Rock | SK4 | 83 | 2028-09-25 06:00 | 2028-09-27 18:00 | S | 2.5
Shannonbridge | SQ1 | 262 | 2028-09-28 | 2028-09-30 | 128 | 2
Shannonbridge | SQ1 | 262 | 2028-09-30 | 2028-09-30 17:30 | 224 | 0.71
Whitebank | DW1 | 61.5 | 2028-10-02 | 2028-10-05 00:30 | 26 | 3
Inchicore | IH1 | 30 | 2028-10-09 | 2028-10-14 00:30 | S | 5
Aghada | AD4 | 75 | 2028-10-09 | 2028-10-19 00:30 | S | 10
Whitebank | DW1 | 61.5 | 2028-10-09 00:30 | 2028-10-12 00:30 | 26 | 3
Aghada | AD3 | 19 | 2028-10-16 | 2028-10-19 00:30 | S | 3
Aghada | AD5 | 75 | 2028-10-19 | 2028-10-29 00:30 | S | 10
Dublin Bay | DB1 | 415 | 2028-10-27 | 2028-11-06 00:30 | S | 10
Irishtown | IS2 | 30 | 2028-11-06 | 2028-11-09 00:30 | S | 3
Seal Rock | SK3 | 83 | 2028-11-06 06:00 | 2028-11-08 18:00 | S | 2.5
Poolbeg | PB8 | 75 | 2028-11-13 00:30 | 2028-11-24 00:30 | S | 11
Lisdrum | LF1 | 60 | 2028-12-05 | 2028-12-08 00:30 | 45 | 3
Lisdrum | LF1 | 60 | 2028-12-05 | 2028-12-05 17:00 | S | 0.67
Edenderry | ED1 | 118 | 2028-12-26 12:00 | 2029-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2028 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2028 | [5 empty] | Feb '2028 |  |  |  | Mar '2028 |  |  |  | Apr '2028 |  |  |  | May '2028 |  |  |  |  | Jun '2028 |  |  |  | Jul '2028 |  |  |  |  | Aug '2028 |  |  |  | Sep '2028 |  |  |  | Oct '2028 |  |  |  |  | Nov '2028 |  |  |  | Dec '2028
|  | Week | 52 '2027 | 1 '2028 | 2 '2028 | 3 '2028 | 4 '2028 | 5 '2028 | 6 '2028 | 7 '2028 | 8 '2028 | 9 '2028 | 10 '2028 | 11 '2028 | 12 '2028 | 13 '2028 | 14 '2028 | 15 '2028 | 16 '2028 | 17 '2028 | 18 '2028 | 19 '2028 | 20 '2028 | 21 '2028 | 22 '2028 | 23 '2028 | 24 '2028 | 25 '2028 | 26 '2028 | 27 '2028 | 28 '2028 | 29 '2028 | 30 '2028 | 31 '2028 | 32 '2028 | 33 '2028 | 34 '2028 | 35 '2028 | 36 '2028 | 37 '2028 | 38 '2028 | 39 '2028 | 40 '2028 | 41 '2028 | 42 '2028 | 43 '2028 | 44 '2028 | 45 '2028 | 46 '2028 | 47 '2028 | 48 '2028 | 49 '2028 | 50 '2028 | 51 '2028 | 52 '2028
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2
Ballydown BESS | NIBLD | 12 | [31 empty] | S
Ballylumford | NIB10 | 94 | [17 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Ballylumford | NIB31 | 249 | [37 empty] | S | S
Ballylumford | NIB32 | 249 | [37 empty] | S | S
Ballylumford | NIBGT1 | 58 | [34 empty] | S
Ballylumford | NIBGT2 | 58
Caherty | NICHT | 5
Carmeen | NICMN | 20
Castlereagh BESS | NICSB | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [17 empty] | S | S | S | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [21 empty] | S
Drumkee BESS | NIDK1 | 50
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Kells BESS | NIKEB | 50
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42 | [27 empty] | S
Kilroot | NIKGT6 | 350 | [31 empty] | S | S | S
Kilroot | NIKGT7 | 350 | [13 empty] | S | S | S
Lisahally | NILPS | 18 | [20 empty] | S | S | S | S
Moyle | MOYLE | 450
Mullavilly BESS | NIMZ1 | 50
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Coolkeeragh | NIC30 | 408 | 2028-01-08 | 2028-01-10 | S | 2
Ballylumford | NIB31 | 249 | 2028-03-04 | 2028-03-07 | S | 3
Ballylumford | NIB32 | 249 | 2028-03-11 | 2028-03-14 | S | 3
Kilroot | NIKGT7 | 350 | 2028-03-27 | 2028-04-17 | S | 21
Mullavilly BESS | NIMZ1 | 50 | 2028-04-01 | 2028-04-04 | S | 3
Drumkee BESS | NIDK1 | 50 | 2028-04-01 | 2028-04-04 | S | 3
Castlereagh BESS | NICSB | 50 | 2028-04-17 | 2028-04-18 | S | 1
Coolkeeragh | NIC30 | 408 | 2028-04-21 | 2028-06-11 | S | 51
Ballylumford | NIB10 | 94 | 2028-04-21 | 2028-07-21 | S | 91
Lisahally | NILPS | 17.6 | 2028-05-14 | 2028-06-12 | S | 29
Coolkeeragh | NICGT8 | 53 | 2028-05-22 | 2028-05-27 | S | 5
Moyle | MOYLE | 450 | 2028-06-13 | 2028-06-16 | 250 | 3
Carmeen | NICMN | 20 | 2028-06-16 | 2028-06-21 | S | 5
Kilroot | NIKGT3 | 42 | 2028-07-01 | 2028-07-06 | S | 5
Kilroot | NIKGT4 | 42 | 2028-07-06 | 2028-07-11 | S | 5
Kilroot | NIKGT1 | 29 | 2028-07-24 | 2028-07-27 | S | 3
Ballydown BESS | NIBLD | 12 | 2028-07-27 | 2028-07-29 | 10 | 2
Kilroot | NIKGT2 | 29 | 2028-07-27 | 2028-07-30 | S | 3
Ballydown BESS | NIBLD | 12 | 2028-08-01 | 2028-08-09 | S | 8
Kilroot | NIKGT6 | 350 | 2028-08-01 | 2028-08-19 | S | 18
Castlereagh BESS | NICSB | 50 | 2028-08-07 | 2028-08-08 | S | 1
Ballylumford | NIBGT1 | 58 | 2028-08-20 | 2028-08-26 | S | 6
Ballylumford | NIBGT2 | 58 | 2028-08-26 | 2028-09-01 | S | 6
Kells BESS | NIKEB | 50 | 2028-08-28 | 2028-09-09 | 40 | 12
Ballylumford | NIB32 | 249 | 2028-09-11 | 2028-09-25 | S | 14
Ballylumford | NIB31 | 249 | 2028-09-11 | 2028-09-25 | S | 14
Coolkeeragh | NIC30 | 408 | 2028-09-13 | 2028-09-15 | S | 2
Castlereagh BESS | NICSB | 50 | 2028-10-16 | 2028-10-17 | S | 1
Mullavilly BESS | NIMZ1 | 50 | 2028-11-01 | 2028-11-04 | S | 3
Drumkee BESS | NIDK1 | 50 | 2028-11-01 | 2028-11-04 | S | 3
Coolkeeragh | NIC30 | 408 | 2028-12-14 | 2028-12-16 | S | 2
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2028 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2028 | [5 empty] | Feb '2028 |  |  |  | Mar '2028 |  |  |  | Apr '2028 |  |  |  | May '2028 |  |  |  |  | Jun '2028 |  |  |  | Jul '2028 |  |  |  |  | Aug '2028 |  |  |  | Sep '2028 |  |  |  | Oct '2028 |  |  |  |  | Nov '2028 |  |  |  | Dec '2028
|  | Week | 52 '2027 | 1 '2028 | 2 '2028 | 3 '2028 | 4 '2028 | 5 '2028 | 6 '2028 | 7 '2028 | 8 '2028 | 9 '2028 | 10 '2028 | 11 '2028 | 12 '2028 | 13 '2028 | 14 '2028 | 15 '2028 | 16 '2028 | 17 '2028 | 18 '2028 | 19 '2028 | 20 '2028 | 21 '2028 | 22 '2028 | 23 '2028 | 24 '2028 | 25 '2028 | 26 '2028 | 27 '2028 | 28 '2028 | 29 '2028 | 30 '2028 | 31 '2028 | 32 '2028 | 33 '2028 | 34 '2028 | 35 '2028 | 36 '2028 | 37 '2028 | 38 '2028 | 39 '2028 | 40 '2028 | 41 '2028 | 42 '2028 | 43 '2028 | 44 '2028 | 45 '2028 | 46 '2028 | 47 '2028 | 48 '2028 | 49 '2028 | 50 '2028 | 51 '2028 | 52 '2028
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2
Aghada | AD2 | 449 | [23 empty] | S | S
Aghada | AD3 | 19 | [14 empty] | S
Aghada | AD4 | 75 | [15 empty] | S | S | [24 empty] | S | S
Aghada | AD5 | 75 | [16 empty] | S | S | [24 empty] | S | S
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA2 | 22 | [20 empty] | S
Ardnacrusha | AA3 | 19 | [24 empty] | S
Ardnacrusha | AA4 | 24 | [37 empty] | S
Aughinish Alumina | EB1 | 25
Ballydown BESS | NIBLD | 12 | [31 empty] | S
Ballylumford | NIB10 | 94 | [17 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Ballylumford | NIB31 | 249 | [37 empty] | S | S
Ballylumford | NIB32 | 249 | [37 empty] | S | S
Ballylumford | NIBGT1 | 58 | [34 empty] | S
Ballylumford | NIBGT2 | 58
Ballymakaily | IL1 | 18
Ballymakaily | IL2 | 18
Ballymakaily | IL3 | 18
Ballymakaily | IL4 | 18
Ballymakaily | IL5 | 18
Ballymakaily | IL6 | 18
Banoge | OD1 | 9
Caherty | NICHT | 5
Carmeen | NICMN | 20
Castlelost | LZ1 | 55
Castlelost | LZ2 | 55
Castlelost | LZ3 | 55
Castlelost | LZ4 | 55
Castlelost | LZ5 | 55
Castlereagh BESS | NICSB | 50
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [17 empty] | S | S | S | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [21 empty] | S
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [39 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drumkee BESS | NIDK1 | 50
Drybridge | IW1 | 17
Dublin Bay | DB1 | 415 | [44 empty] | S
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S | [21 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | EC1 | 53
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 17
Endeco Technologies | EC6 | 4
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Enel X | AE1 | 80
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 23
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 5
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | ET1 | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
Erne | ER1 | 10 | [14 empty] | S
Erne | ER2 | 10 | [20 empty] | S
Erne | ER3 | 23 | [24 empty] | S
Erne | ER4 | 23 | [29 empty] | S
EWIC | EW1 | 500 | [14 empty] | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464 | [22 empty] | S | S | S | S
Huntstown | HN2 | 402 | [31 empty] | S | S | S | S | S | S | S | S | S | S | S | S
Huntstown | HNC | 342 | [12 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Inchicore | IH1 | 30 | [41 empty] | S
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Irishtown | IS2 | 30 | [20 empty] | S
Irishtown | IS3 | 64 | [37 empty] | S
Kells BESS | NIKEB | 50
Kilcumber | OE2 | 25
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42 | [27 empty] | S
Kilroot | NIKGT6 | 350 | [31 empty] | S | S | S
Kilroot | NIKGT7 | 350 | [13 empty] | S | S | S
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [19 empty] | S | S
Lee | LE2 | 4 | [12 empty] | S | S
Lee | LE3 | 8 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Liffey | LI1 | 15 | [19 empty] | S | S
Liffey | LI2 | 15 | [19 empty] | S | S
Liffey | LI4 | 4 | [25 empty] | S | S
Liffey | LI5 | 4 | [22 empty] | S | S
Lisahally | NILPS | 18 | [20 empty] | S | S | S | S
Lisdrum | LF1 | 60
Loughtown | GLK | 500
Moneypoint | MP1 | 285 | [15 empty] | S | S
Moneypoint | MP2 | 285 | [19 empty] | S | S
Moneypoint | MP3 | 285 | [31 empty] | S | S | S
Moneypoint | MP5 | 1 | [24 empty] | S
Moyle | MOYLE | 450
Mullavilly BESS | NIMZ1 | 50
Northwall | NW8 | 199
Poolbeg | PB4 | 156 | [31 empty] | S | S | S | S | S | S | S | S | S
Poolbeg | PB5 | 153 | [23 empty] | S
Poolbeg | PB6 | 168
Poolbeg | PB7 | 64 | [32 empty] | S
Poolbeg | PB8 | 75 | [18 empty] | S | S | [26 empty] | S | S
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14
Powerhouse Generation | PG1 | 10
Powerhouse Generation | PG2 | 4
Powerhouse Generation | PG6 | 4
Raghra | RG1 | 63
Raghra | RG2 | 1
Rhode | RP1 | 52 | [21 empty] | S | S
Rhode | RP2 | 52 | [21 empty] | S | S
Seal Rock | SK3 | 83 | [27 empty] | S
Seal Rock | SK4 | 83 | [22 empty] | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [25 empty] | S | S
Tawnaghmore | TP3 | 52 | [25 empty] | S | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [13 empty] | S | S | S
Turlough Hill | TH2 | 73 | [13 empty] | S | S | S
Turlough Hill | TH3 | 73 | [13 empty] | S | S | S
Turlough Hill | TH4 | 73 | [13 empty] | S | S | S
Tynagh | TYC | 404 | [35 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 8
Veolia Alternative Energy | DP2 | 21
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 59
VIOTAS | EE2 | 25
VIOTAS | EE3 | 13
VIOTAS | EE4 | 15
VIOTAS | EE5 | 25
VIOTAS | EE6 | 14
VIOTAS | EE7 | 37
VIOTAS | EE8 | 5
VIOTAS | EE9 | 5
VIOTAS | VS1 | 5
VIOTAS | VS2 | 6
VIOTAS | VS6 | 5
Whitebank | DW1 | 62 | [15 empty] | S
Whitegate | WG1 | 444 | [35 empty] | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2027-12-26 12:00 | 2028-01-01 08:00 | S | 5.83
Coolkeeragh | NIC30 | 408 | 2028-01-08 | 2028-01-10 | S | 2
Seal Rock | SK4 | 83 | 2028-02-07 06:00 | 2028-02-09 18:00 | S | 2.5
Ballylumford | NIB31 | 249 | 2028-03-04 | 2028-03-07 | S | 3
Seal Rock | SK3 | 83 | 2028-03-06 06:00 | 2028-03-08 18:00 | S | 2.5
Ballylumford | NIB32 | 249 | 2028-03-11 | 2028-03-14 | S | 3
Huntstown | HNC | 342 | 2028-03-20 | 2028-07-06 00:30 | S | 108
Lee | LE2 | 4 | 2028-03-20 08:00 | 2028-03-31 20:00 | S | 11.5
Turlough Hill | TH1 | 73 | 2028-03-26 | 2028-04-13 00:30 | S | 18
Turlough Hill | TH2 | 73 | 2028-03-26 | 2028-04-13 00:30 | S | 18
Turlough Hill | TH3 | 73 | 2028-03-26 08:00 | 2028-04-13 18:00 | S | 18.42
Turlough Hill | TH4 | 73 | 2028-03-26 08:00 | 2028-04-13 18:00 | S | 18.42
Kilroot | NIKGT7 | 350 | 2028-03-27 | 2028-04-17 | S | 21
Mullavilly BESS | NIMZ1 | 50 | 2028-04-01 | 2028-04-04 | S | 3
Drumkee BESS | NIDK1 | 50 | 2028-04-01 | 2028-04-04 | S | 3
Aghada | AD3 | 19 | 2028-04-03 | 2028-04-08 00:30 | S | 5
Whitebank | DW1 | 61.5 | 2028-04-03 | 2028-04-08 00:30 | 26 | 5
Lee | LE3 | 8 | 2028-04-03 08:00 | 2028-12-01 20:00 | S | 242.5
Erne | ER1 | 10 | 2028-04-03 08:00 | 2028-04-07 20:00 | S | 4.5
EWIC | EW1 | 500 | 2028-04-03 09:00 | 2028-04-03 21:00 | S | 0.5
EWIC | EW1 | 500 | 2028-04-03 21:00 | 2028-04-07 23:00 | S | 4.08
Ardnacrusha | AA1 | 21 | 2028-04-04 08:00 | 2028-09-29 20:00 | S | 178.5
Aghada | AT1 | 90 | 2028-04-07 | 2028-04-11 20:00 | S | 4.83
Moneypoint | MP1 | 285 | 2028-04-07 | 2028-04-23 00:30 | S | 16
Whitebank | DW1 | 61.5 | 2028-04-08 | 2028-04-18 00:30 | S | 10
Inchicore | IH1 | 30 | 2028-04-10 | 2028-04-13 00:30 | S | 3
Aghada | AD4 | 75 | 2028-04-10 | 2028-04-20 00:30 | S | 10
Edenderry | ED1 | 118 | 2028-04-13 17:00 | 2028-04-19 08:00 | S | 5.58
Aghada | AT2 | 90 | 2028-04-14 | 2028-04-18 00:30 | S | 4
Castlereagh BESS | NICSB | 50 | 2028-04-17 | 2028-04-18 | S | 1
Whitebank | DW1 | 61.5 | 2028-04-18 | 2028-04-23 00:30 | 26 | 5
Aghada | AD5 | 75 | 2028-04-20 | 2028-04-30 00:30 | S | 10
Aghada | AT4 | 90 | 2028-04-21 | 2028-04-25 00:30 | S | 4
Coolkeeragh | NIC30 | 408 | 2028-04-21 | 2028-06-11 | S | 51
Ballylumford | NIB10 | 94 | 2028-04-21 | 2028-07-21 | S | 91
Poolbeg | PB8 | 75 | 2028-05-01 | 2028-05-11 00:30 | S | 10
Moneypoint | MP2 | 285 | 2028-05-05 | 2028-05-21 00:30 | S | 16
Poolbeg | PB6 | 168 | 2028-05-05 | 2028-06-03 00:30 | 84 | 29
Liffey | LI1 | 15 | 2028-05-08 | 2028-05-19 00:30 | S | 11
Liffey | LI2 | 15 | 2028-05-08 | 2028-05-19 00:30 | S | 11
Lee | LE1 | 15 | 2028-05-08 08:00 | 2028-05-19 20:00 | S | 11.5
Seal Rock | SK3 | 83 | 2028-05-08 18:00 | 2028-05-11 18:00 | S | 3
Seal Rock | SK4 | 83 | 2028-05-09 | 2028-05-11 12:00 | S | 2.5
Lisahally | NILPS | 17.6 | 2028-05-14 | 2028-06-12 | S | 29
Irishtown | IS2 | 30 | 2028-05-15 | 2028-05-20 00:30 | S | 5
Ardnacrusha | AA2 | 22 | 2028-05-15 08:00 | 2028-05-19 20:00 | S | 4.5
Erne | ER2 | 10 | 2028-05-15 08:00 | 2028-05-19 20:00 | S | 4.5
Rhode | RP1 | 52 | 2028-05-19 | 2028-06-02 00:30 | S | 14
Rhode | RP2 | 52 | 2028-05-19 | 2028-06-02 00:30 | S | 14
Coolkeeragh | NICGT8 | 53 | 2028-05-22 | 2028-05-27 | S | 5
Poolbeg | PB4 | 156 | 2028-05-26 | 2028-06-03 00:30 | S | 8
Poolbeg | PB6 | 168 | 2028-05-26 | 2028-06-03 00:30 | 84 | 8
Liffey | LI5 | 4 | 2028-05-29 | 2028-06-09 00:30 | S | 11
Seal Rock | SK4 | 83 | 2028-05-29 06:00 | 2028-06-02 18:00 | S | 4.5
Great Island | GI4 | 464 | 2028-06-01 | 2028-06-24 00:30 | S | 23
Poolbeg | PB5 | 153 | 2028-06-04 | 2028-06-10 00:30 | S | 6
Poolbeg | PB6 | 168 | 2028-06-04 | 2028-07-01 00:30 | 84 | 27
Aghada | AD2 | 449 | 2028-06-04 | 2028-06-19 20:00 | S | 15.83
Poolbeg | PB6 | 168 | 2028-06-04 | 2028-06-10 00:30 | 84 | 6
Moneypoint | MP5 | 1 | 2028-06-12 | 2028-06-19 00:30 | S | 7
Northwall | NW8 | 199 | 2028-06-12 08:00 | 2028-06-14 18:00 | 160 | 2.42
Ardnacrusha | AA3 | 19 | 2028-06-12 08:00 | 2028-06-16 20:00 | S | 4.5
Erne | ER3 | 23 | 2028-06-12 08:00 | 2028-06-16 20:00 | S | 4.5
Lisdrum | LF1 | 60 | 2028-06-13 | 2028-06-23 00:30 | 45 | 10
Moyle | MOYLE | 450 | 2028-06-13 | 2028-06-16 | 250 | 3
Northwall | NW8 | 199 | 2028-06-15 08:00 | 2028-06-17 18:00 | 160 | 2.42
Tawnaghmore | TP1 | 52 | 2028-06-16 | 2028-06-30 00:30 | S | 14
Tawnaghmore | TP3 | 52 | 2028-06-16 | 2028-06-30 00:30 | S | 14
Carmeen | NICMN | 20 | 2028-06-16 | 2028-06-21 | S | 5
Liffey | LI4 | 4 | 2028-06-19 | 2028-06-30 00:30 | S | 11
Northwall | NW8 | 199 | 2028-06-19 08:00 | 2028-06-21 18:00 | 160 | 2.42
Northwall | NW8 | 199 | 2028-06-22 08:00 | 2028-06-24 18:00 | 160 | 2.42
Northwall | NW8 | 199 | 2028-06-26 08:00 | 2028-06-28 18:00 | 160 | 2.42
Northwall | NW8 | 199 | 2028-06-29 08:00 | 2028-07-01 18:00 | 160 | 2.42
Edenderry | ED1 | 118 | 2028-06-30 12:00 | 2028-07-28 08:00 | S | 27.83
Kilroot | NIKGT3 | 42 | 2028-07-01 | 2028-07-06 | S | 5
Seal Rock | SK3 | 83 | 2028-07-03 06:00 | 2028-07-07 18:00 | S | 4.5
Northwall | NW8 | 199 | 2028-07-03 08:00 | 2028-07-04 18:00 | S | 1.42
Kilroot | NIKGT4 | 42 | 2028-07-06 | 2028-07-11 | S | 5
Erne | ER4 | 23 | 2028-07-17 08:00 | 2028-07-21 20:00 | S | 4.5
Kilroot | NIKGT1 | 29 | 2028-07-24 | 2028-07-27 | S | 3
Ballydown BESS | NIBLD | 12 | 2028-07-27 | 2028-07-29 | 10 | 2
Kilroot | NIKGT2 | 29 | 2028-07-27 | 2028-07-30 | S | 3
Huntstown | HN2 | 402 | 2028-07-28 | 2028-10-21 00:30 | S | 85
Moneypoint | MP3 | 285 | 2028-08-01 | 2028-08-17 00:30 | S | 16
Poolbeg | PB4 | 156 | 2028-08-01 | 2028-10-01 | S | 61
Poolbeg | PB6 | 168 | 2028-08-01 | 2028-10-01 | 84 | 61
Ballydown BESS | NIBLD | 12 | 2028-08-01 | 2028-08-09 | S | 8
Kilroot | NIKGT6 | 350 | 2028-08-01 | 2028-08-19 | S | 18
Poolbeg | PB7 | 64 | 2028-08-07 | 2028-08-12 00:30 | S | 5
Castlereagh BESS | NICSB | 50 | 2028-08-07 | 2028-08-08 | S | 1
Ballylumford | NIBGT1 | 58 | 2028-08-20 | 2028-08-26 | S | 6
Whitegate | WG1 | 444 | 2028-08-26 | 2028-09-05 00:30 | S | 10
Ballylumford | NIBGT2 | 58 | 2028-08-26 | 2028-09-01 | S | 6
Tynagh | TYC | 404 | 2028-08-27 | 2028-09-06 00:30 | S | 10
Kells BESS | NIKEB | 50 | 2028-08-28 | 2028-09-09 | 40 | 12
Shannonbridge | SQ1 | 262 | 2028-09-04 | 2028-09-06 00:30 | 224 | 2
Shannonbridge | SQ1 | 262 | 2028-09-07 | 2028-09-09 17:30 | 224 | 2.71
Shannonbridge | SQ1 | 262 | 2028-09-11 | 2028-09-13 17:30 | 224 | 2.71
Irishtown | IS3 | 64 | 2028-09-11 | 2028-09-16 00:30 | S | 5
Ballylumford | NIB32 | 249 | 2028-09-11 | 2028-09-25 | S | 14
Ballylumford | NIB31 | 249 | 2028-09-11 | 2028-09-25 | S | 14
Ardnacrusha | AA4 | 24 | 2028-09-11 08:00 | 2028-09-15 20:00 | S | 4.5
Coolkeeragh | NIC30 | 408 | 2028-09-13 | 2028-09-15 | S | 2
Edenderry | ED3 | 58 | 2028-09-13 08:00 | 2028-09-13 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2028-09-13 08:00 | 2028-09-13 18:00 | S | 0.42
Shannonbridge | SQ1 | 262 | 2028-09-14 | 2028-09-16 00:30 | 224 | 2
Shannonbridge | SQ1 | 262 | 2028-09-16 | 2028-09-17 17:30 | 128 | 1.71
Shannonbridge | SQ1 | 262 | 2028-09-18 | 2028-09-20 00:30 | 224 | 2
Lisdrum | LF1 | 60 | 2028-09-18 | 2028-09-20 00:30 | S | 2
Shannonbridge | SQ1 | 262 | 2028-09-21 08:00 | 2028-09-23 17:30 | 224 | 2.38
Shannonbridge | SQ1 | 262 | 2028-09-25 | 2028-09-27 17:30 | 224 | 2.71
Corduff | FG2 | 64 | 2028-09-25 | 2028-09-30 00:30 | S | 5
Seal Rock | SK4 | 83 | 2028-09-25 06:00 | 2028-09-27 18:00 | S | 2.5
Shannonbridge | SQ1 | 262 | 2028-09-28 | 2028-09-30 | 128 | 2
Shannonbridge | SQ1 | 262 | 2028-09-30 | 2028-09-30 17:30 | 224 | 0.71
Whitebank | DW1 | 61.5 | 2028-10-02 | 2028-10-05 00:30 | 26 | 3
Inchicore | IH1 | 30 | 2028-10-09 | 2028-10-14 00:30 | S | 5
Aghada | AD4 | 75 | 2028-10-09 | 2028-10-19 00:30 | S | 10
Whitebank | DW1 | 61.5 | 2028-10-09 00:30 | 2028-10-12 00:30 | 26 | 3
Aghada | AD3 | 19 | 2028-10-16 | 2028-10-19 00:30 | S | 3
Castlereagh BESS | NICSB | 50 | 2028-10-16 | 2028-10-17 | S | 1
Aghada | AD5 | 75 | 2028-10-19 | 2028-10-29 00:30 | S | 10
Dublin Bay | DB1 | 415 | 2028-10-27 | 2028-11-06 00:30 | S | 10
Mullavilly BESS | NIMZ1 | 50 | 2028-11-01 | 2028-11-04 | S | 3
Drumkee BESS | NIDK1 | 50 | 2028-11-01 | 2028-11-04 | S | 3
Irishtown | IS2 | 30 | 2028-11-06 | 2028-11-09 00:30 | S | 3
Seal Rock | SK3 | 83 | 2028-11-06 06:00 | 2028-11-08 18:00 | S | 2.5
Poolbeg | PB8 | 75 | 2028-11-13 00:30 | 2028-11-24 00:30 | S | 11
Lisdrum | LF1 | 60 | 2028-12-05 | 2028-12-08 00:30 | 45 | 3
Lisdrum | LF1 | 60 | 2028-12-05 | 2028-12-05 17:00 | S | 0.67
Coolkeeragh | NIC30 | 408 | 2028-12-14 | 2028-12-16 | S | 2
Edenderry | ED1 | 118 | 2028-12-26 12:00 | 2029-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10