## Outage Plan EirGrid
2027 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2027 |  |  |  |  | Feb '2027 |  |  |  | Mar '2027 |  |  |  |  | Apr '2027 |  |  |  | May '2027 |  |  |  |  | Jun '2027 |  |  |  | Jul '2027 |  |  |  | Aug '2027 |  |  |  |  | Sep '2027 |  |  |  | Oct '2027 |  |  |  | Nov '2027 |  |  |  |  | Dec '2027
|  | Week | 53 '2027 | 1 '2027 | 2 '2027 | 3 '2027 | 4 '2027 | 5 '2027 | 6 '2027 | 7 '2027 | 8 '2027 | 9 '2027 | 10 '2027 | 11 '2027 | 12 '2027 | 13 '2027 | 14 '2027 | 15 '2027 | 16 '2027 | 17 '2027 | 18 '2027 | 19 '2027 | 20 '2027 | 21 '2027 | 22 '2027 | 23 '2027 | 24 '2027 | 25 '2027 | 26 '2027 | 27 '2027 | 28 '2027 | 29 '2027 | 30 '2027 | 31 '2027 | 32 '2027 | 33 '2027 | 34 '2027 | 35 '2027 | 36 '2027 | 37 '2027 | 38 '2027 | 39 '2027 | 40 '2027 | 41 '2027 | 42 '2027 | 43 '2027 | 44 '2027 | 45 '2027 | 46 '2027 | 47 '2027 | 48 '2027 | 49 '2027 | 50 '2027 | 51 '2027 | 52 '2027
Station | Unit | NPR
Aghada | AD2 | 449 | [24 empty] | S | S
Aghada | AD3 | 19 | [14 empty] | S
Aghada | AD4 | 75 | [15 empty] | S | S
Aghada | AD5 | 75 | [16 empty] | S | S
Aghada | AT1 | 90 | [12 empty] | S | S |  | S
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [14 empty] | S
Ardnacrusha | AA2 | 22 | [16 empty] | S
Ardnacrusha | AA3 | 19 | [37 empty] | S
Ardnacrusha | AA4 | 24 | [19 empty] | S | S | S | S | S | S | S
Aughinish Alumina | EB1 | 25
Ballymakaily | IL1 | 18
Ballymakaily | IL2 | 18
Ballymakaily | IL3 | 18
Ballymakaily | IL4 | 18
Ballymakaily | IL5 | 18
Ballymakaily | IL6 | 18
Banoge | OD1 | 9
Castlelost | LZ1 | 55
Castlelost | LZ2 | 55
Castlelost | LZ3 | 55
Castlelost | LZ4 | 55
Castlelost | LZ5 | 55
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [38 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17 | [15 empty] | S | S
Dublin Bay | DB1 | 415
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [23 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | [13 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Endeco Technologies | EC1 | 53
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 17
Endeco Technologies | EC6 | 4
Enel X | AE1 | 80
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 23
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 5
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [36 empty] | S | S | S
Erne | ER2 | 10 | [30 empty] | S
Erne | ER3 | 23 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Erne | ER4 | 23 |  | S | S | S | S | [23 empty] | S
EWIC | EW1 | 500 | [16 empty] | S | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Gorman | GF1 | 50
Great Island | GI4 | 464
Huntstown | HN2 | 402 | [14 empty] | S | S | S | S
Huntstown | HNC | 342 | [25 empty] | S | S | S
Inchicore | IH1 | 30 | [41 empty] | S
Irishtown | IS2 | 30 | [20 empty] | S
Irishtown | IS3 | 64 | [37 empty] | S
Kilcumber | OE2 | 25
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S
Lee | LE2 | 4 | [13 empty] | S | S | S | S | S | S
Lee | LE3 | 8 | [21 empty] | S | S
Liffey | LI1 | 15 | [19 empty] | S | S
Liffey | LI2 | 15 | [19 empty] | S | S
Liffey | LI4 | 4 | [19 empty] | S | S
Liffey | LI5 | 4 | [22 empty] | S | S
Lisdrum | LF1 | 60 | [24 empty] | S | S | [12 empty] | S
Loughtown | GLK | 500
Moneypoint | MP1 | 285 | [15 empty] | S | S
Moneypoint | MP2 | 285 | [20 empty] | S | S
Moneypoint | MP3 | 285 | [32 empty] | S | S | S
Moneypoint | MP5 | 1 | [24 empty] | S | S
Northwall | NW8 | 199
Poolbeg | PB4 | 156 | [32 empty] | S | S | [14 empty] | S | S
Poolbeg | PB5 | 153 | [32 empty] | S | S | [14 empty] | S | S
Poolbeg | PB6 | 168 | [32 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB7 | 64 | [36 empty] | S
Poolbeg | PB8 | 75 | [46 empty] | S | S
Powerhouse Generation | PG1 | 10
Powerhouse Generation | PG2 | 4
Powerhouse Generation | PG6 | 4
Raghra | RG1 | 63 | [39 empty] | S
Raghra | RG2 | 1 | [39 empty] | S
Rhode | RP1 | 52 | [20 empty] | S | S
Rhode | RP2 | 52 | [20 empty] | S | S
Seal Rock | SK3 | 83 | [29 empty] | S
Seal Rock | SK4 | 83 | [22 empty] | S | S | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160 | [9 empty] | S | S
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [24 empty] | S | S
Tawnaghmore | TP3 | 52 | [24 empty] | S | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [9 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Turlough Hill | TH2 | 73 | [9 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Turlough Hill | TH3 | 73 | [9 empty] | S | S | S | S | S | S | S | S | S
Turlough Hill | TH4 | 73 | [9 empty] | S | S | S | S | S | S | S | S | S
Tynagh | TYC | 404 | [28 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 8
Veolia Alternative Energy | DP2 | 21
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 59
VIOTAS | EE2 | 25
VIOTAS | EE3 | 13
VIOTAS | EE4 | 15
VIOTAS | EE5 | 25
VIOTAS | EE6 | 14
VIOTAS | EE7 | 37
VIOTAS | EE8 | 5
VIOTAS | EE9 | 5
VIOTAS | VS1 | 5
VIOTAS | VS2 | 6
VIOTAS | VS6 | 5
Whitebank | DW1 | 62 | [15 empty] | S
Whitegate | WG1 | 444 | [9 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Golagh | GO2 | 3 | 2023-04-17 15:30 | 2031-01-01 | F | 2815.33
Edenderry | ED1 | 118 | 2026-12-26 12:00 | 2027-01-01 08:00 | S | 5.83
Erne | ER4 | 23 | 2027-01-01 08:00 | 2027-01-31 20:00 | S | 30.5
Seal Rock | SK4 | 83 | 2027-02-15 06:00 | 2027-02-17 18:00 | S | 2.5
Turlough Hill | TH3 | 73 | 2027-03-01 06:00 | 2027-04-30 18:00 | S | 60.5
Turlough Hill | TH4 | 73 | 2027-03-01 06:00 | 2027-04-30 18:00 | S | 60.5
Turlough Hill | TH1 | 73 | 2027-03-01 06:00 | 2027-11-30 18:00 | S | 274.5
Turlough Hill | TH2 | 73 | 2027-03-01 06:00 | 2027-11-30 18:00 | S | 274.5
Tarbert | TB5 | 160 | 2027-03-01 08:00 | 2027-03-13 17:00 | S | 12.33
Whitegate | WG1 | 444 | 2027-03-01 21:00 | 2027-05-31 21:00 | S | 91
Seal Rock | SK3 | 83 | 2027-03-22 06:00 | 2027-03-24 18:00 | S | 2.5
Aghada | AT1 | 90 | 2027-03-22 08:00 | 2027-04-05 20:00 | S | 14.5
Edenderry | ED1 | 118 | 2027-03-25 17:00 | 2027-03-31 08:00 | S | 5.58
Lee | LE2 | 4 | 2027-03-30 08:00 | 2027-05-07 20:00 | S | 38.5
Huntstown | HN2 | 402 | 2027-04-04 21:00 | 2027-04-29 21:00 | S | 25
Loughtown | GLK | 500 | 2027-04-05 06:00 | 2027-04-08 23:00 | S | 3.67
Aghada | AD3 | 19 | 2027-04-05 07:00 | 2027-04-10 19:00 | S | 5.5
Ardnacrusha | AA1 | 21 | 2027-04-05 08:00 | 2027-04-09 20:00 | S | 4.5
Erne | ER3 | 23 | 2027-04-05 08:00 | 2027-07-04 20:00 | S | 90.5
Whitebank | DW1 | 61.5 | 2027-04-05 23:00 | 2027-04-10 23:00 | 26 | 5
Moneypoint | MP1 | 285 | 2027-04-09 07:00 | 2027-04-27 19:00 | S | 18.5
Drybridge | IW1 | 17 | 2027-04-10 | 2027-04-23 | S | 13
Whitebank | DW1 | 61.5 | 2027-04-10 23:00 | 2027-04-20 23:00 | S | 10
Inchicore | IH1 | 30 | 2027-04-12 07:00 | 2027-04-15 19:00 | 25 | 3.5
Aghada | AD4 | 75 | 2027-04-12 07:00 | 2027-04-22 19:00 | S | 10.5
Aghada | AT1 | 90 | 2027-04-14 08:00 | 2027-04-18 20:00 | S | 4.5
Ardnacrusha | AA2 | 22 | 2027-04-19 08:00 | 2027-04-23 20:00 | S | 4.5
EWIC | EW1 | 500 | 2027-04-19 09:00 | 2027-04-19 21:00 | S | 0.5
EWIC | EW1 | 500 | 2027-04-19 21:00 | 2027-05-01 23:00 | S | 12.08
Whitebank | DW1 | 61.5 | 2027-04-20 23:00 | 2027-04-25 23:00 | 26 | 5
Aghada | AD5 | 75 | 2027-04-22 07:00 | 2027-05-05 19:00 | S | 13.5
Poolbeg | PB8 | 75 | 2027-05-03 07:00 | 2027-05-13 19:00 | 60 | 10.5
Lee | LE1 | 15 | 2027-05-04 08:00 | 2027-05-14 20:00 | S | 10.5
Liffey | LI4 | 4 | 2027-05-10 | 2027-05-22 | S | 12
Liffey | LI1 | 15 | 2027-05-10 08:00 | 2027-05-21 17:00 | S | 11.33
Liffey | LI2 | 15 | 2027-05-10 08:00 | 2027-05-21 18:00 | S | 11.42
Ardnacrusha | AA4 | 24 | 2027-05-10 08:00 | 2027-06-28 20:00 | S | 49.5
Seal Rock | SK3 | 83 | 2027-05-10 18:00 | 2027-05-13 18:00 | S | 3
Seal Rock | SK4 | 83 | 2027-05-11 | 2027-05-13 12:00 | S | 2.5
Moneypoint | MP2 | 285 | 2027-05-14 | 2027-05-30 19:00 | S | 16.75
Rhode | RP1 | 52 | 2027-05-14 09:00 | 2027-05-28 17:00 | S | 14.33
Rhode | RP2 | 52 | 2027-05-14 09:00 | 2027-05-28 17:00 | S | 14.33
Irishtown | IS2 | 30 | 2027-05-17 07:00 | 2027-05-22 19:00 | S | 5.5
Aghada | AT2 | 90 | 2027-05-21 08:00 | 2027-05-25 20:00 | S | 4.5
Lee | LE3 | 8 | 2027-05-25 08:00 | 2027-06-04 20:00 | S | 10.5
Aghada | AT4 | 90 | 2027-05-28 08:00 | 2027-06-01 20:00 | S | 4.5
Seal Rock | SK4 | 83 | 2027-05-30 06:00 | 2027-06-21 18:00 | S | 22.5
Liffey | LI5 | 4 | 2027-05-31 08:00 | 2027-06-11 17:00 | S | 11.33
Edenderry | ED1 | 118 | 2027-06-04 12:00 | 2027-09-28 08:00 | S | 115.83
Tawnaghmore | TP1 | 52 | 2027-06-11 09:00 | 2027-06-25 17:00 | S | 14.33
Tawnaghmore | TP3 | 52 | 2027-06-11 09:00 | 2027-06-25 17:00 | S | 14.33
Aghada | AD2 | 449 | 2027-06-14 | 2027-06-26 20:00 | S | 12.83
Moneypoint | MP5 | 1 | 2027-06-14 | 2027-06-24 19:00 | S | 10.75
Lisdrum | LF1 | 60 | 2027-06-14 08:00 | 2027-06-25 17:00 | S | 11.33
Huntstown | HNC | 342 | 2027-06-18 21:00 | 2027-07-08 21:00 | S | 20
Cloniffeen | SI1 | 50 | 2027-07-06 08:00 | 2027-07-07 17:00 | S | 1.33
Cloniffeen | SI2 | 50 | 2027-07-06 08:00 | 2027-07-07 17:00 | S | 1.33
Erne | ER4 | 23 | 2027-07-12 08:00 | 2027-07-16 20:00 | S | 4.5
Tynagh | TYC | 404 | 2027-07-12 20:00 | 2027-12-07 22:00 | S | 148.08
Seal Rock | SK3 | 83 | 2027-07-19 06:00 | 2027-07-23 18:00 | S | 4.5
Derrycarney | LU1 | 50 | 2027-07-20 08:00 | 2027-07-21 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2027-07-20 08:00 | 2027-07-21 17:00 | S | 1.33
Erne | ER2 | 10 | 2027-07-26 08:00 | 2027-07-30 20:00 | S | 4.5
Poolbeg | PB6 | 168 | 2027-08-04 | 2027-08-07 | S | 3
Moneypoint | MP3 | 285 | 2027-08-06 22:00 | 2027-08-31 22:00 | S | 25
Poolbeg | PB5 | 153 | 2027-08-07 | 2027-08-26 | S | 19
Poolbeg | PB6 | 168 | 2027-08-07 | 2027-08-26 | S | 19
Poolbeg | PB4 | 156 | 2027-08-07 | 2027-08-26 | S | 19
Poolbeg | PB6 | 168 | 2027-08-26 | 2027-11-27 | S | 93
Poolbeg | PB7 | 64 | 2027-09-06 | 2027-09-11 19:00 | S | 5.75
Shannonbridge | SQ1 | 262 | 2027-09-06 08:00 | 2027-09-08 20:00 | 224 | 2.5
Erne | ER1 | 10 | 2027-09-06 08:00 | 2027-09-24 20:00 | S | 18.5
Shannonbridge | SQ1 | 262 | 2027-09-09 08:00 | 2027-09-11 20:00 | 224 | 2.5
Irishtown | IS3 | 64 | 2027-09-13 | 2027-09-18 19:00 | S | 5.75
Ardnacrusha | AA3 | 19 | 2027-09-13 08:00 | 2027-09-17 20:00 | S | 4.5
Shannonbridge | SQ1 | 262 | 2027-09-13 08:00 | 2027-09-15 20:00 | 224 | 2.5
Shannonbridge | SQ1 | 262 | 2027-09-16 08:00 | 2027-09-18 20:00 | 224 | 2.5
Shannonbridge | SQ1 | 262 | 2027-09-16 08:00 | 2027-09-17 20:00 | 128 | 1.5
Corduff | FG2 | 64 | 2027-09-20 | 2027-09-25 19:00 | S | 5.75
Shannonbridge | SQ1 | 262 | 2027-09-20 08:00 | 2027-09-22 20:00 | 224 | 2.5
Lisdrum | LF1 | 60 | 2027-09-20 08:00 | 2027-09-24 17:00 | S | 4.33
Shannonbridge | SQ1 | 262 | 2027-09-23 08:00 | 2027-09-25 20:00 | 224 | 2.5
Raghra | RG1 | 63.2 | 2027-09-27 | 2027-10-02 | S | 5
Raghra | RG2 | 1 | 2027-09-27 | 2027-10-02 | S | 5
Shannonbridge | SQ1 | 262 | 2027-09-27 08:00 | 2027-09-29 20:00 | 224 | 2.5
Shannonbridge | SQ1 | 262 | 2027-09-30 08:00 | 2027-10-01 20:00 | 128 | 1.5
Shannonbridge | SQ1 | 262 | 2027-09-30 17:00 | 2027-10-02 17:00 | 224 | 2
Whitebank | DW1 | 61.5 | 2027-10-04 23:00 | 2027-10-07 23:00 | 26 | 3
Edenderry | ED3 | 58 | 2027-10-05 08:00 | 2027-10-05 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2027-10-05 08:00 | 2027-10-05 18:00 | S | 0.42
Seal Rock | SK4 | 83 | 2027-10-11 06:00 | 2027-10-13 18:00 | S | 2.5
Inchicore | IH1 | 30 | 2027-10-11 07:00 | 2027-10-16 19:00 | S | 5.5
Aghada | AD4 | 75 | 2027-10-11 07:00 | 2027-10-19 19:00 | 60 | 8.5
Whitebank | DW1 | 61.5 | 2027-10-11 23:00 | 2027-10-14 23:00 | 26 | 3
Dublin Bay | DB1 | 415 | 2027-10-15 12:00 | 2027-10-22 18:00 | S | 7.25
Aghada | AD3 | 19 | 2027-10-18 07:00 | 2027-10-20 19:00 | 14 | 2.5
Aghada | AD5 | 75 | 2027-10-20 07:00 | 2027-10-28 19:00 | 60 | 8.5
Seal Rock | SK3 | 83 | 2027-11-08 06:00 | 2027-11-10 18:00 | S | 2.5
Irishtown | IS2 | 30 | 2027-11-08 07:00 | 2027-11-11 19:00 | 25 | 3.5
Poolbeg | PB8 | 75 | 2027-11-15 07:00 | 2027-11-26 19:00 | S | 11.5
Poolbeg | PB6 | 168 | 2027-11-27 | 2027-12-16 | S | 19
Poolbeg | PB4 | 156 | 2027-11-27 | 2027-12-16 | S | 19
Poolbeg | PB5 | 153 | 2027-11-27 | 2027-12-16 | S | 19
Lisdrum | LF1 | 60 | 2027-12-06 | 2027-12-06 18:00 | S | 0.75
Lisdrum | LF1 | 60 | 2027-12-07 08:00 | 2027-12-10 18:00 | S | 3.42
Edenderry | ED1 | 118 | 2027-12-26 12:00 | 2028-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2027 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2027 |  |  |  |  | Feb '2027 |  |  |  | Mar '2027 |  |  |  |  | Apr '2027 |  |  |  | May '2027 |  |  |  |  | Jun '2027 |  |  |  | Jul '2027 |  |  |  | Aug '2027 |  |  |  |  | Sep '2027 |  |  |  | Oct '2027 |  |  |  | Nov '2027 |  |  |  |  | Dec '2027
|  | Week | 53 '2027 | 1 '2027 | 2 '2027 | 3 '2027 | 4 '2027 | 5 '2027 | 6 '2027 | 7 '2027 | 8 '2027 | 9 '2027 | 10 '2027 | 11 '2027 | 12 '2027 | 13 '2027 | 14 '2027 | 15 '2027 | 16 '2027 | 17 '2027 | 18 '2027 | 19 '2027 | 20 '2027 | 21 '2027 | 22 '2027 | 23 '2027 | 24 '2027 | 25 '2027 | 26 '2027 | 27 '2027 | 28 '2027 | 29 '2027 | 30 '2027 | 31 '2027 | 32 '2027 | 33 '2027 | 34 '2027 | 35 '2027 | 36 '2027 | 37 '2027 | 38 '2027 | 39 '2027 | 40 '2027 | 41 '2027 | 42 '2027 | 43 '2027 | 44 '2027 | 45 '2027 | 46 '2027 | 47 '2027 | 48 '2027 | 49 '2027 | 50 '2027 | 51 '2027 | 52 '2027
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2
Ballydown BESS | NIBLD | 12
Ballylumford | NIB10 | 94 | [29 empty] | S | S
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249 | [10 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58 | [26 empty] | S
Caherty | NICHT | 5
Carmeen | NICMN | 20 | [24 empty] | S
Castlereagh BESS | NICSB | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [40 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [18 empty] | S | S | S | S | S | S
Drumkee BESS | NIDK1 | 50
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Kells BESS | NIKEB | 50
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42
Kilroot | NIKGT6 | 350 | [23 empty] | S | S | S
Kilroot | NIKGT7 | 350
Lisahally | NILPS | 18 | [20 empty] | S | S
Moyle | MOYLE | 450
Mullavilly BESS | NIMZ1 | 50
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Coolkeeragh | NIC30 | 408 | 2027-02-06 | 2027-02-08 | S | 2
Ballylumford | NIB10 | 94 | 2027-03-05 | 2027-03-09 | S | 4
Ballylumford | NIB32 | 249 | 2027-03-09 | 2027-05-08 | S | 60
Ballylumford | NIB31 | 249 | 2027-03-19 | 2027-03-21 00:30 | S | 2
Mullavilly BESS | NIMZ1 | 50 | 2027-04-01 | 2027-04-04 | S | 3
Drumkee BESS | NIDK1 | 50 | 2027-04-01 | 2027-04-04 | S | 3
Castlereagh BESS | NICSB | 50 | 2027-04-19 | 2027-04-20 | S | 1
Coolkeeragh | NICGT8 | 53 | 2027-05-03 | 2027-06-13 | S | 41
Lisahally | NILPS | 17.6 | 2027-05-16 | 2027-05-31 | S | 15
Kilroot | NIKGT1 | 29 | 2027-06-01 | 2027-06-04 | S | 3
Kilroot | NIKGT2 | 29 | 2027-06-04 | 2027-06-07 | S | 3
Kilroot | NIKGT6 | 350 | 2027-06-10 | 2027-07-01 | S | 21
Moyle | MOYLE | 450 | 2027-06-15 | 2027-06-18 | 250 | 3
Carmeen | NICMN | 20 | 2027-06-16 | 2027-06-21 | S | 5
Ballylumford | NIBGT1 | 58 | 2027-06-25 | 2027-07-01 | S | 6
Coolkeeragh | NIC30 | 408 | 2027-06-26 | 2027-06-28 | S | 2
Ballylumford | NIBGT2 | 58 | 2027-07-01 | 2027-07-07 | S | 6
Ballylumford | NIB31 | 249 | 2027-07-18 | 2027-07-22 | S | 4
Ballylumford | NIB32 | 249 | 2027-07-18 | 2027-07-22 | S | 4
Ballylumford | NIB10 | 94 | 2027-07-18 | 2027-08-01 | S | 14
Ballylumford | NIB31 | 249 | 2027-07-22 | 2027-09-28 | 161 | 68
Ballylumford | NIB32 | 249 | 2027-07-22 | 2027-09-25 | 161 | 65
Kilroot | NIKGT3 | 42 | 2027-08-01 | 2027-08-06 | S | 5
Ballydown BESS | NIBLD | 12 | 2027-08-02 | 2027-08-04 | 10 | 2
Castlereagh BESS | NICSB | 50 | 2027-08-02 | 2027-08-03 | S | 1
Kilroot | NIKGT4 | 42 | 2027-08-06 | 2027-08-11 | S | 5
Kells BESS | NIKEB | 50 | 2027-08-30 | 2027-09-11 | 40 | 12
Ballylumford | NIB32 | 249 | 2027-09-25 | 2027-09-28 | S | 3
Ballylumford | NIB32 | 249 | 2027-09-28 | 2027-10-01 | 161 | 3
Ballylumford | NIB31 | 249 | 2027-09-28 | 2027-10-01 | S | 3
Coolkeeragh | NIC30 | 408 | 2027-10-04 | 2027-10-16 | S | 12
Castlereagh BESS | NICSB | 50 | 2027-10-18 | 2027-10-19 | S | 1
Mullavilly BESS | NIMZ1 | 50 | 2027-11-01 | 2027-11-04 | S | 3
Drumkee BESS | NIDK1 | 50 | 2027-11-01 | 2027-11-04 | S | 3
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2027 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2027 |  |  |  |  | Feb '2027 |  |  |  | Mar '2027 |  |  |  |  | Apr '2027 |  |  |  | May '2027 |  |  |  |  | Jun '2027 |  |  |  | Jul '2027 |  |  |  | Aug '2027 |  |  |  |  | Sep '2027 |  |  |  | Oct '2027 |  |  |  | Nov '2027 |  |  |  |  | Dec '2027
|  | Week | 53 '2027 | 1 '2027 | 2 '2027 | 3 '2027 | 4 '2027 | 5 '2027 | 6 '2027 | 7 '2027 | 8 '2027 | 9 '2027 | 10 '2027 | 11 '2027 | 12 '2027 | 13 '2027 | 14 '2027 | 15 '2027 | 16 '2027 | 17 '2027 | 18 '2027 | 19 '2027 | 20 '2027 | 21 '2027 | 22 '2027 | 23 '2027 | 24 '2027 | 25 '2027 | 26 '2027 | 27 '2027 | 28 '2027 | 29 '2027 | 30 '2027 | 31 '2027 | 32 '2027 | 33 '2027 | 34 '2027 | 35 '2027 | 36 '2027 | 37 '2027 | 38 '2027 | 39 '2027 | 40 '2027 | 41 '2027 | 42 '2027 | 43 '2027 | 44 '2027 | 45 '2027 | 46 '2027 | 47 '2027 | 48 '2027 | 49 '2027 | 50 '2027 | 51 '2027 | 52 '2027
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2
Aghada | AD2 | 449 | [24 empty] | S | S
Aghada | AD3 | 19 | [14 empty] | S
Aghada | AD4 | 75 | [15 empty] | S | S
Aghada | AD5 | 75 | [16 empty] | S | S
Aghada | AT1 | 90 | [12 empty] | S | S |  | S
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [14 empty] | S
Ardnacrusha | AA2 | 22 | [16 empty] | S
Ardnacrusha | AA3 | 19 | [37 empty] | S
Ardnacrusha | AA4 | 24 | [19 empty] | S | S | S | S | S | S | S
Aughinish Alumina | EB1 | 25
Ballydown BESS | NIBLD | 12
Ballylumford | NIB10 | 94 | [29 empty] | S | S
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249 | [10 empty] | S | S | S | S | S | S | S | S | S
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58 | [26 empty] | S
Ballymakaily | IL1 | 18
Ballymakaily | IL2 | 18
Ballymakaily | IL3 | 18
Ballymakaily | IL4 | 18
Ballymakaily | IL5 | 18
Ballymakaily | IL6 | 18
Banoge | OD1 | 9
Caherty | NICHT | 5
Carmeen | NICMN | 20 | [24 empty] | S
Castlelost | LZ1 | 55
Castlelost | LZ2 | 55
Castlelost | LZ3 | 55
Castlelost | LZ4 | 55
Castlelost | LZ5 | 55
Castlereagh BESS | NICSB | 50
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [40 empty] | S | S
Coolkeeragh | NICGT8 | 53 | [18 empty] | S | S | S | S | S | S
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [38 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drumkee BESS | NIDK1 | 50
Drybridge | IW1 | 17 | [15 empty] | S | S
Dublin Bay | DB1 | 415
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [23 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | [13 empty] | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | EC1 | 53
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 17
Endeco Technologies | EC6 | 4
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Enel X | AE1 | 80
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 23
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 5
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | ET1 | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
Erne | ER1 | 10 | [36 empty] | S | S | S
Erne | ER2 | 10 | [30 empty] | S
Erne | ER3 | 23 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Erne | ER4 | 23 |  | S | S | S | S | [23 empty] | S
EWIC | EW1 | 500 | [16 empty] | S | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Gorman | GF1 | 50
Great Island | GI4 | 464
Huntstown | HN2 | 402 | [14 empty] | S | S | S | S
Huntstown | HNC | 342 | [25 empty] | S | S | S
Inchicore | IH1 | 30 | [41 empty] | S
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Irishtown | IS2 | 30 | [20 empty] | S
Irishtown | IS3 | 64 | [37 empty] | S
Kells BESS | NIKEB | 50
Kilcumber | OE2 | 25
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42
Kilroot | NIKGT6 | 350 | [23 empty] | S | S | S
Kilroot | NIKGT7 | 350
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S
Lee | LE2 | 4 | [13 empty] | S | S | S | S | S | S
Lee | LE3 | 8 | [21 empty] | S | S
Liffey | LI1 | 15 | [19 empty] | S | S
Liffey | LI2 | 15 | [19 empty] | S | S
Liffey | LI4 | 4 | [19 empty] | S | S
Liffey | LI5 | 4 | [22 empty] | S | S
Lisahally | NILPS | 18 | [20 empty] | S | S
Lisdrum | LF1 | 60 | [24 empty] | S | S | [12 empty] | S
Loughtown | GLK | 500
Moneypoint | MP1 | 285 | [15 empty] | S | S
Moneypoint | MP2 | 285 | [20 empty] | S | S
Moneypoint | MP3 | 285 | [32 empty] | S | S | S
Moneypoint | MP5 | 1 | [24 empty] | S | S
Moyle | MOYLE | 450
Mullavilly BESS | NIMZ1 | 50
Northwall | NW8 | 199
Poolbeg | PB4 | 156 | [32 empty] | S | S | [14 empty] | S | S
Poolbeg | PB5 | 153 | [32 empty] | S | S | [14 empty] | S | S
Poolbeg | PB6 | 168 | [32 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Poolbeg | PB7 | 64 | [36 empty] | S
Poolbeg | PB8 | 75 | [46 empty] | S | S
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14
Powerhouse Generation | PG1 | 10
Powerhouse Generation | PG2 | 4
Powerhouse Generation | PG6 | 4
Raghra | RG1 | 63 | [39 empty] | S
Raghra | RG2 | 1 | [39 empty] | S
Rhode | RP1 | 52 | [20 empty] | S | S
Rhode | RP2 | 52 | [20 empty] | S | S
Seal Rock | SK3 | 83 | [29 empty] | S
Seal Rock | SK4 | 83 | [22 empty] | S | S | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160 | [9 empty] | S | S
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [24 empty] | S | S
Tawnaghmore | TP3 | 52 | [24 empty] | S | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [9 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Turlough Hill | TH2 | 73 | [9 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Turlough Hill | TH3 | 73 | [9 empty] | S | S | S | S | S | S | S | S | S
Turlough Hill | TH4 | 73 | [9 empty] | S | S | S | S | S | S | S | S | S
Tynagh | TYC | 404 | [28 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 8
Veolia Alternative Energy | DP2 | 21
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 59
VIOTAS | EE2 | 25
VIOTAS | EE3 | 13
VIOTAS | EE4 | 15
VIOTAS | EE5 | 25
VIOTAS | EE6 | 14
VIOTAS | EE7 | 37
VIOTAS | EE8 | 5
VIOTAS | EE9 | 5
VIOTAS | VS1 | 5
VIOTAS | VS2 | 6
VIOTAS | VS6 | 5
Whitebank | DW1 | 62 | [15 empty] | S
Whitegate | WG1 | 444 | [9 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Golagh | GO2 | 3 | 2023-04-17 15:30 | 2031-01-01 | F | 2815.33
Edenderry | ED1 | 118 | 2026-12-26 12:00 | 2027-01-01 08:00 | S | 5.83
Erne | ER4 | 23 | 2027-01-01 08:00 | 2027-01-31 20:00 | S | 30.5
Coolkeeragh | NIC30 | 408 | 2027-02-06 | 2027-02-08 | S | 2
Seal Rock | SK4 | 83 | 2027-02-15 06:00 | 2027-02-17 18:00 | S | 2.5
Turlough Hill | TH3 | 73 | 2027-03-01 06:00 | 2027-04-30 18:00 | S | 60.5
Turlough Hill | TH4 | 73 | 2027-03-01 06:00 | 2027-04-30 18:00 | S | 60.5
Turlough Hill | TH1 | 73 | 2027-03-01 06:00 | 2027-11-30 18:00 | S | 274.5
Turlough Hill | TH2 | 73 | 2027-03-01 06:00 | 2027-11-30 18:00 | S | 274.5
Tarbert | TB5 | 160 | 2027-03-01 08:00 | 2027-03-13 17:00 | S | 12.33
Whitegate | WG1 | 444 | 2027-03-01 21:00 | 2027-05-31 21:00 | S | 91
Ballylumford | NIB10 | 94 | 2027-03-05 | 2027-03-09 | S | 4
Ballylumford | NIB32 | 249 | 2027-03-09 | 2027-05-08 | S | 60
Ballylumford | NIB31 | 249 | 2027-03-19 | 2027-03-21 00:30 | S | 2
Seal Rock | SK3 | 83 | 2027-03-22 06:00 | 2027-03-24 18:00 | S | 2.5
Aghada | AT1 | 90 | 2027-03-22 08:00 | 2027-04-05 20:00 | S | 14.5
Edenderry | ED1 | 118 | 2027-03-25 17:00 | 2027-03-31 08:00 | S | 5.58
Lee | LE2 | 4 | 2027-03-30 08:00 | 2027-05-07 20:00 | S | 38.5
Mullavilly BESS | NIMZ1 | 50 | 2027-04-01 | 2027-04-04 | S | 3
Drumkee BESS | NIDK1 | 50 | 2027-04-01 | 2027-04-04 | S | 3
Huntstown | HN2 | 402 | 2027-04-04 21:00 | 2027-04-29 21:00 | S | 25
Loughtown | GLK | 500 | 2027-04-05 06:00 | 2027-04-08 23:00 | S | 3.67
Aghada | AD3 | 19 | 2027-04-05 07:00 | 2027-04-10 19:00 | S | 5.5
Ardnacrusha | AA1 | 21 | 2027-04-05 08:00 | 2027-04-09 20:00 | S | 4.5
Erne | ER3 | 23 | 2027-04-05 08:00 | 2027-07-04 20:00 | S | 90.5
Whitebank | DW1 | 61.5 | 2027-04-05 23:00 | 2027-04-10 23:00 | 26 | 5
Moneypoint | MP1 | 285 | 2027-04-09 07:00 | 2027-04-27 19:00 | S | 18.5
Drybridge | IW1 | 17 | 2027-04-10 | 2027-04-23 | S | 13
Whitebank | DW1 | 61.5 | 2027-04-10 23:00 | 2027-04-20 23:00 | S | 10
Inchicore | IH1 | 30 | 2027-04-12 07:00 | 2027-04-15 19:00 | 25 | 3.5
Aghada | AD4 | 75 | 2027-04-12 07:00 | 2027-04-22 19:00 | S | 10.5
Aghada | AT1 | 90 | 2027-04-14 08:00 | 2027-04-18 20:00 | S | 4.5
Castlereagh BESS | NICSB | 50 | 2027-04-19 | 2027-04-20 | S | 1
Ardnacrusha | AA2 | 22 | 2027-04-19 08:00 | 2027-04-23 20:00 | S | 4.5
EWIC | EW1 | 500 | 2027-04-19 09:00 | 2027-04-19 21:00 | S | 0.5
EWIC | EW1 | 500 | 2027-04-19 21:00 | 2027-05-01 23:00 | S | 12.08
Whitebank | DW1 | 61.5 | 2027-04-20 23:00 | 2027-04-25 23:00 | 26 | 5
Aghada | AD5 | 75 | 2027-04-22 07:00 | 2027-05-05 19:00 | S | 13.5
Coolkeeragh | NICGT8 | 53 | 2027-05-03 | 2027-06-13 | S | 41
Poolbeg | PB8 | 75 | 2027-05-03 07:00 | 2027-05-13 19:00 | 60 | 10.5
Lee | LE1 | 15 | 2027-05-04 08:00 | 2027-05-14 20:00 | S | 10.5
Liffey | LI4 | 4 | 2027-05-10 | 2027-05-22 | S | 12
Liffey | LI1 | 15 | 2027-05-10 08:00 | 2027-05-21 17:00 | S | 11.33
Liffey | LI2 | 15 | 2027-05-10 08:00 | 2027-05-21 18:00 | S | 11.42
Ardnacrusha | AA4 | 24 | 2027-05-10 08:00 | 2027-06-28 20:00 | S | 49.5
Seal Rock | SK3 | 83 | 2027-05-10 18:00 | 2027-05-13 18:00 | S | 3
Seal Rock | SK4 | 83 | 2027-05-11 | 2027-05-13 12:00 | S | 2.5
Moneypoint | MP2 | 285 | 2027-05-14 | 2027-05-30 19:00 | S | 16.75
Rhode | RP1 | 52 | 2027-05-14 09:00 | 2027-05-28 17:00 | S | 14.33
Rhode | RP2 | 52 | 2027-05-14 09:00 | 2027-05-28 17:00 | S | 14.33
Lisahally | NILPS | 17.6 | 2027-05-16 | 2027-05-31 | S | 15
Irishtown | IS2 | 30 | 2027-05-17 07:00 | 2027-05-22 19:00 | S | 5.5
Aghada | AT2 | 90 | 2027-05-21 08:00 | 2027-05-25 20:00 | S | 4.5
Lee | LE3 | 8 | 2027-05-25 08:00 | 2027-06-04 20:00 | S | 10.5
Aghada | AT4 | 90 | 2027-05-28 08:00 | 2027-06-01 20:00 | S | 4.5
Seal Rock | SK4 | 83 | 2027-05-30 06:00 | 2027-06-21 18:00 | S | 22.5
Liffey | LI5 | 4 | 2027-05-31 08:00 | 2027-06-11 17:00 | S | 11.33
Kilroot | NIKGT1 | 29 | 2027-06-01 | 2027-06-04 | S | 3
Kilroot | NIKGT2 | 29 | 2027-06-04 | 2027-06-07 | S | 3
Edenderry | ED1 | 118 | 2027-06-04 12:00 | 2027-09-28 08:00 | S | 115.83
Kilroot | NIKGT6 | 350 | 2027-06-10 | 2027-07-01 | S | 21
Tawnaghmore | TP1 | 52 | 2027-06-11 09:00 | 2027-06-25 17:00 | S | 14.33
Tawnaghmore | TP3 | 52 | 2027-06-11 09:00 | 2027-06-25 17:00 | S | 14.33
Aghada | AD2 | 449 | 2027-06-14 | 2027-06-26 20:00 | S | 12.83
Moneypoint | MP5 | 1 | 2027-06-14 | 2027-06-24 19:00 | S | 10.75
Lisdrum | LF1 | 60 | 2027-06-14 08:00 | 2027-06-25 17:00 | S | 11.33
Moyle | MOYLE | 450 | 2027-06-15 | 2027-06-18 | 250 | 3
Carmeen | NICMN | 20 | 2027-06-16 | 2027-06-21 | S | 5
Huntstown | HNC | 342 | 2027-06-18 21:00 | 2027-07-08 21:00 | S | 20
Ballylumford | NIBGT1 | 58 | 2027-06-25 | 2027-07-01 | S | 6
Coolkeeragh | NIC30 | 408 | 2027-06-26 | 2027-06-28 | S | 2
Ballylumford | NIBGT2 | 58 | 2027-07-01 | 2027-07-07 | S | 6
Cloniffeen | SI1 | 50 | 2027-07-06 08:00 | 2027-07-07 17:00 | S | 1.33
Cloniffeen | SI2 | 50 | 2027-07-06 08:00 | 2027-07-07 17:00 | S | 1.33
Erne | ER4 | 23 | 2027-07-12 08:00 | 2027-07-16 20:00 | S | 4.5
Tynagh | TYC | 404 | 2027-07-12 20:00 | 2027-12-07 22:00 | S | 148.08
Ballylumford | NIB31 | 249 | 2027-07-18 | 2027-07-22 | S | 4
Ballylumford | NIB32 | 249 | 2027-07-18 | 2027-07-22 | S | 4
Ballylumford | NIB10 | 94 | 2027-07-18 | 2027-08-01 | S | 14
Seal Rock | SK3 | 83 | 2027-07-19 06:00 | 2027-07-23 18:00 | S | 4.5
Derrycarney | LU1 | 50 | 2027-07-20 08:00 | 2027-07-21 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2027-07-20 08:00 | 2027-07-21 17:00 | S | 1.33
Ballylumford | NIB31 | 249 | 2027-07-22 | 2027-09-28 | 161 | 68
Ballylumford | NIB32 | 249 | 2027-07-22 | 2027-09-25 | 161 | 65
Erne | ER2 | 10 | 2027-07-26 08:00 | 2027-07-30 20:00 | S | 4.5
Kilroot | NIKGT3 | 42 | 2027-08-01 | 2027-08-06 | S | 5
Ballydown BESS | NIBLD | 12 | 2027-08-02 | 2027-08-04 | 10 | 2
Castlereagh BESS | NICSB | 50 | 2027-08-02 | 2027-08-03 | S | 1
Poolbeg | PB6 | 168 | 2027-08-04 | 2027-08-07 | S | 3
Kilroot | NIKGT4 | 42 | 2027-08-06 | 2027-08-11 | S | 5
Moneypoint | MP3 | 285 | 2027-08-06 22:00 | 2027-08-31 22:00 | S | 25
Poolbeg | PB5 | 153 | 2027-08-07 | 2027-08-26 | S | 19
Poolbeg | PB6 | 168 | 2027-08-07 | 2027-08-26 | S | 19
Poolbeg | PB4 | 156 | 2027-08-07 | 2027-08-26 | S | 19
Poolbeg | PB6 | 168 | 2027-08-26 | 2027-11-27 | S | 93
Kells BESS | NIKEB | 50 | 2027-08-30 | 2027-09-11 | 40 | 12
Poolbeg | PB7 | 64 | 2027-09-06 | 2027-09-11 19:00 | S | 5.75
Shannonbridge | SQ1 | 262 | 2027-09-06 08:00 | 2027-09-08 20:00 | 224 | 2.5
Erne | ER1 | 10 | 2027-09-06 08:00 | 2027-09-24 20:00 | S | 18.5
Shannonbridge | SQ1 | 262 | 2027-09-09 08:00 | 2027-09-11 20:00 | 224 | 2.5
Irishtown | IS3 | 64 | 2027-09-13 | 2027-09-18 19:00 | S | 5.75
Ardnacrusha | AA3 | 19 | 2027-09-13 08:00 | 2027-09-17 20:00 | S | 4.5
Shannonbridge | SQ1 | 262 | 2027-09-13 08:00 | 2027-09-15 20:00 | 224 | 2.5
Shannonbridge | SQ1 | 262 | 2027-09-16 08:00 | 2027-09-18 20:00 | 224 | 2.5
Shannonbridge | SQ1 | 262 | 2027-09-16 08:00 | 2027-09-17 20:00 | 128 | 1.5
Corduff | FG2 | 64 | 2027-09-20 | 2027-09-25 19:00 | S | 5.75
Shannonbridge | SQ1 | 262 | 2027-09-20 08:00 | 2027-09-22 20:00 | 224 | 2.5
Lisdrum | LF1 | 60 | 2027-09-20 08:00 | 2027-09-24 17:00 | S | 4.33
Shannonbridge | SQ1 | 262 | 2027-09-23 08:00 | 2027-09-25 20:00 | 224 | 2.5
Ballylumford | NIB32 | 249 | 2027-09-25 | 2027-09-28 | S | 3
Raghra | RG1 | 63.2 | 2027-09-27 | 2027-10-02 | S | 5
Raghra | RG2 | 1 | 2027-09-27 | 2027-10-02 | S | 5
Shannonbridge | SQ1 | 262 | 2027-09-27 08:00 | 2027-09-29 20:00 | 224 | 2.5
Ballylumford | NIB32 | 249 | 2027-09-28 | 2027-10-01 | 161 | 3
Ballylumford | NIB31 | 249 | 2027-09-28 | 2027-10-01 | S | 3
Shannonbridge | SQ1 | 262 | 2027-09-30 08:00 | 2027-10-01 20:00 | 128 | 1.5
Shannonbridge | SQ1 | 262 | 2027-09-30 17:00 | 2027-10-02 17:00 | 224 | 2
Coolkeeragh | NIC30 | 408 | 2027-10-04 | 2027-10-16 | S | 12
Whitebank | DW1 | 61.5 | 2027-10-04 23:00 | 2027-10-07 23:00 | 26 | 3
Edenderry | ED3 | 58 | 2027-10-05 08:00 | 2027-10-05 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2027-10-05 08:00 | 2027-10-05 18:00 | S | 0.42
Seal Rock | SK4 | 83 | 2027-10-11 06:00 | 2027-10-13 18:00 | S | 2.5
Inchicore | IH1 | 30 | 2027-10-11 07:00 | 2027-10-16 19:00 | S | 5.5
Aghada | AD4 | 75 | 2027-10-11 07:00 | 2027-10-19 19:00 | 60 | 8.5
Whitebank | DW1 | 61.5 | 2027-10-11 23:00 | 2027-10-14 23:00 | 26 | 3
Dublin Bay | DB1 | 415 | 2027-10-15 12:00 | 2027-10-22 18:00 | S | 7.25
Castlereagh BESS | NICSB | 50 | 2027-10-18 | 2027-10-19 | S | 1
Aghada | AD3 | 19 | 2027-10-18 07:00 | 2027-10-20 19:00 | 14 | 2.5
Aghada | AD5 | 75 | 2027-10-20 07:00 | 2027-10-28 19:00 | 60 | 8.5
Mullavilly BESS | NIMZ1 | 50 | 2027-11-01 | 2027-11-04 | S | 3
Drumkee BESS | NIDK1 | 50 | 2027-11-01 | 2027-11-04 | S | 3
Seal Rock | SK3 | 83 | 2027-11-08 06:00 | 2027-11-10 18:00 | S | 2.5
Irishtown | IS2 | 30 | 2027-11-08 07:00 | 2027-11-11 19:00 | 25 | 3.5
Poolbeg | PB8 | 75 | 2027-11-15 07:00 | 2027-11-26 19:00 | S | 11.5
Poolbeg | PB6 | 168 | 2027-11-27 | 2027-12-16 | S | 19
Poolbeg | PB4 | 156 | 2027-11-27 | 2027-12-16 | S | 19
Poolbeg | PB5 | 153 | 2027-11-27 | 2027-12-16 | S | 19
Lisdrum | LF1 | 60 | 2027-12-06 | 2027-12-06 18:00 | S | 0.75
Lisdrum | LF1 | 60 | 2027-12-07 08:00 | 2027-12-10 18:00 | S | 3.42
Edenderry | ED1 | 118 | 2027-12-26 12:00 | 2028-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10