## Outage Plan EirGrid
2029 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2029 |  |  |  |  | Feb '2029 |  |  |  | Mar '2029 |  |  |  | Apr '2029 |  |  |  |  | May '2029 |  |  |  | Jun '2029 |  |  |  | Jul '2029 |  |  |  |  | Aug '2029 |  |  |  | Sep '2029 |  |  |  | Oct '2029 |  |  |  |  | Nov '2029 |  |  |  | Dec '2029
|  | Week | 1 '2029 | 2 '2029 | 3 '2029 | 4 '2029 | 5 '2029 | 6 '2029 | 7 '2029 | 8 '2029 | 9 '2029 | 10 '2029 | 11 '2029 | 12 '2029 | 13 '2029 | 14 '2029 | 15 '2029 | 16 '2029 | 17 '2029 | 18 '2029 | 19 '2029 | 20 '2029 | 21 '2029 | 22 '2029 | 23 '2029 | 24 '2029 | 25 '2029 | 26 '2029 | 27 '2029 | 28 '2029 | 29 '2029 | 30 '2029 | 31 '2029 | 32 '2029 | 33 '2029 | 34 '2029 | 35 '2029 | 36 '2029 | 37 '2029 | 38 '2029 | 39 '2029 | 40 '2029 | 41 '2029 | 42 '2029 | 43 '2029 | 44 '2029 | 45 '2029 | 46 '2029 | 47 '2029 | 48 '2029 | 49 '2029 | 50 '2029 | 51 '2029 | 52 '2029 | 53 '2029
Station | Unit | NPR
Aghada | AD2 | 449 | [31 empty] | S | S
Aghada | AD3 | 19 | [13 empty] | S
Aghada | AD4 | 75 | [14 empty] | S | S
Aghada | AD5 | 75 | [15 empty] | S | S
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [19 empty] | S
Ardnacrusha | AA2 | 22 | [13 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA3 | 19 | [23 empty] | S
Ardnacrusha | AA4 | 24 | [36 empty] | S
Aughinish Alumina | EB1 | 25
Ballymakaily | IL1 | 18
Ballymakaily | IL2 | 18
Ballymakaily | IL3 | 18
Ballymakaily | IL4 | 18
Ballymakaily | IL5 | 18
Ballymakaily | IL6 | 18
Banoge | OD1 | 9
Castlelost | LZ1 | 55
Castlelost | LZ2 | 55
Castlelost | LZ3 | 55
Castlelost | LZ4 | 55
Castlelost | LZ5 | 55
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [37 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17 | [14 empty] | S | S
Dublin Bay | DB1 | 415
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [26 empty] | S | S | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Endeco Technologies | EC1 | 53
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 17
Endeco Technologies | EC6 | 4
Enel X | AE1 | 80
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 23
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 5
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [19 empty] | S
Erne | ER2 | 10 | [14 empty] | S | S | S
Erne | ER3 | 23 | [23 empty] | S
Erne | ER4 | 23 | [27 empty] | S
EWIC | EW1 | 500 | [14 empty] | S | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Gorman | GF1 | 50
Great Island | GI4 | 464
Huntstown | HN2 | 402
Huntstown | HNC | 342 | [39 empty] | S | S | S
Inchicore | IH1 | 30 | [40 empty] | S
Irishtown | IS2 | 30 | [19 empty] | S
Irishtown | IS3 | 64 | [36 empty] | S
Kilcumber | OE2 | 25
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Lee | LE2 | 4 | [11 empty] | S | S
Lee | LE3 | 8 | [14 empty] | S | S
Liffey | LI1 | 15 | [17 empty] | S | S | S | S | S | S | S | S | S
Liffey | LI2 | 15 | [17 empty] | S | S | S | S | S | S | S | S | S
Liffey | LI4 | 4 | [28 empty] | S | S
Liffey | LI5 | 4 | [32 empty] | S | S
Lisdrum | LF1 | 60 | [24 empty] | S | S | [11 empty] | S | [10 empty] | S
Loughtown | GLK | 500
Moneypoint | MP1 | 285
Moneypoint | MP2 | 285
Moneypoint | MP3 | 285
Moneypoint | MP5 | 1 | [23 empty] | S
Northwall | NW8 | 199
Poolbeg | PB4 | 156
Poolbeg | PB5 | 153 | [21 empty] | S | S | S | S | S | S | S
Poolbeg | PB6 | 168
Poolbeg | PB7 | 64 | [35 empty] | S
Poolbeg | PB8 | 75 | [45 empty] | S | S
Powerhouse Generation | PG1 | 10
Powerhouse Generation | PG2 | 4
Powerhouse Generation | PG6 | 4
Raghra | RG1 | 63
Raghra | RG2 | 1
Rhode | RP1 | 52 | [19 empty] | S | S
Rhode | RP2 | 52 | [19 empty] | S | S
Seal Rock | SK3 | 83 | [24 empty] | S | S | S | S
Seal Rock | SK4 | 83 | [32 empty] | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [23 empty] | S | S
Tawnaghmore | TP3 | 52 | [23 empty] | S | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [12 empty] | S | S | S
Turlough Hill | TH2 | 73 | [12 empty] | S | S | S
Turlough Hill | TH3 | 73 | [12 empty] | S | S | S
Turlough Hill | TH4 | 73 | [12 empty] | S | S | S
Tynagh | TYC | 404 | [29 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 8
Veolia Alternative Energy | DP2 | 21
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 59
VIOTAS | EE2 | 25
VIOTAS | EE3 | 13
VIOTAS | EE4 | 15
VIOTAS | EE5 | 25
VIOTAS | EE6 | 14
VIOTAS | EE7 | 37
VIOTAS | EE8 | 5
VIOTAS | EE9 | 5
VIOTAS | VS1 | 5
VIOTAS | VS2 | 6
VIOTAS | VS6 | 5
Whitebank | DW1 | 62 | [14 empty] | S | S
Whitegate | WG1 | 444 | [34 empty] | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Golagh | GO2 | 3 | 2023-04-17 15:30 | 2031-01-01 | F | 2815.33
Edenderry | ED1 | 118 | 2028-12-26 12:00 | 2029-01-01 08:00 | S | 5.83
Seal Rock | SK4 | 83 | 2029-01-22 06:00 | 2029-01-24 18:00 | S | 2.5
Seal Rock | SK3 | 83 | 2029-02-26 06:00 | 2029-02-28 18:00 | S | 2.5
Lee | LE2 | 4 | 2029-03-20 08:00 | 2029-03-30 20:00 | S | 10.5
Turlough Hill | TH3 | 73 | 2029-03-25 | 2029-04-14 | S | 20
Turlough Hill | TH4 | 73 | 2029-03-25 | 2029-04-14 | S | 20
Turlough Hill | TH1 | 73 | 2029-03-25 | 2029-04-14 | S | 20
Turlough Hill | TH2 | 73 | 2029-03-25 | 2029-04-14 | S | 20
Edenderry | ED1 | 118 | 2029-03-29 17:00 | 2029-04-04 08:00 | S | 5.58
Aghada | AD3 | 19 | 2029-04-02 08:00 | 2029-04-07 20:00 | S | 5.5
Ardnacrusha | AA2 | 22 | 2029-04-04 | 2029-10-30 | S | 209
Whitebank | DW1 | 61.5 | 2029-04-05 | 2029-04-11 | 26 | 6
Aghada | AT1 | 90 | 2029-04-07 | 2029-04-11 20:00 | S | 4.83
Drybridge | IW1 | 17 | 2029-04-08 | 2029-04-21 | S | 13
Loughtown | GLK | 500 | 2029-04-09 06:00 | 2029-04-12 23:00 | S | 3.67
Inchicore | IH1 | 30 | 2029-04-09 08:00 | 2029-04-12 20:00 | 25 | 3.5
Aghada | AD4 | 75 | 2029-04-09 08:00 | 2029-04-19 20:00 | S | 10.5
Lee | LE3 | 8 | 2029-04-09 08:00 | 2029-04-20 20:00 | S | 11.5
Erne | ER2 | 10 | 2029-04-09 08:00 | 2029-04-27 20:00 | S | 18.5
EWIC | EW1 | 500 | 2029-04-09 09:00 | 2029-04-09 21:00 | S | 0.5
EWIC | EW1 | 500 | 2029-04-09 21:00 | 2029-04-23 23:00 | S | 14.08
Whitebank | DW1 | 61.5 | 2029-04-10 | 2029-04-21 | S | 11
Aghada | AT2 | 90 | 2029-04-14 08:00 | 2029-04-18 20:00 | S | 4.5
Aghada | AD5 | 75 | 2029-04-19 | 2029-04-29 20:00 | S | 10.83
Whitebank | DW1 | 61.5 | 2029-04-20 | 2029-04-26 | 26 | 6
Aghada | AT4 | 90 | 2029-04-21 | 2029-04-25 20:00 | S | 4.83
Seal Rock | SK4 | 83 | 2029-04-23 06:00 | 2029-04-25 18:00 | S | 2.5
Liffey | LI1 | 15 | 2029-04-30 | 2029-06-30 | S | 61
Liffey | LI2 | 15 | 2029-04-30 | 2029-06-30 | S | 61
Poolbeg | PB8 | 75 | 2029-04-30 08:00 | 2029-05-10 20:00 | 60 | 10.5
Lee | LE1 | 15 | 2029-05-08 08:00 | 2029-09-07 20:00 | S | 122.5
Rhode | RP2 | 52 | 2029-05-11 | 2029-05-26 | S | 15
Rhode | RP1 | 52 | 2029-05-11 | 2029-05-26 | S | 15
Erne | ER1 | 10 | 2029-05-14 | 2029-05-19 | S | 5
Irishtown | IS2 | 30 | 2029-05-14 08:00 | 2029-05-19 20:00 | S | 5.5
Seal Rock | SK3 | 83 | 2029-05-14 18:00 | 2029-05-17 18:00 | S | 3
Seal Rock | SK4 | 83 | 2029-05-15 | 2029-05-17 12:00 | S | 2.5
Ardnacrusha | AA1 | 21 | 2029-05-15 | 2029-05-20 | S | 5
Poolbeg | PB6 | 168 | 2029-05-25 | 2029-07-15 | 84 | 51
Poolbeg | PB5 | 153 | 2029-05-25 | 2029-07-15 | S | 51
Tawnaghmore | TP3 | 52 | 2029-06-08 | 2029-06-23 | S | 15
Tawnaghmore | TP1 | 52 | 2029-06-08 | 2029-06-23 | S | 15
Erne | ER3 | 23 | 2029-06-11 08:00 | 2029-06-15 20:00 | S | 4.5
Moneypoint | MP5 | 1 | 2029-06-11 08:00 | 2029-06-16 20:00 | S | 5.5
Ardnacrusha | AA3 | 19 | 2029-06-12 | 2029-06-17 | S | 5
Seal Rock | SK3 | 83 | 2029-06-17 06:00 | 2029-07-17 06:00 | S | 30
Lisdrum | LF1 | 60 | 2029-06-18 | 2029-06-30 | S | 12
Edenderry | ED1 | 118 | 2029-06-29 11:00 | 2029-07-31 08:00 | S | 31.83
Erne | ER4 | 23 | 2029-07-09 08:00 | 2029-07-13 20:00 | S | 4.5
Liffey | LI4 | 4 | 2029-07-16 | 2029-07-27 23:30 | S | 11.96
Tynagh | TYC | 404 | 2029-07-20 | 2029-07-31 | S | 11
Aghada | AD2 | 449 | 2029-08-04 | 2029-08-16 20:00 | S | 12.83
Liffey | LI5 | 4 | 2029-08-13 | 2029-08-25 | S | 12
Seal Rock | SK4 | 83 | 2029-08-13 06:00 | 2029-08-17 18:00 | S | 4.5
Whitegate | WG1 | 444 | 2029-08-25 | 2029-09-04 00:30 | S | 10
Poolbeg | PB7 | 64 | 2029-09-03 08:00 | 2029-09-08 20:00 | S | 5.5
Shannonbridge | SQ1 | 262 | 2029-09-03 08:00 | 2029-09-06 | 224 | 2.67
Shannonbridge | SQ1 | 262 | 2029-09-06 08:00 | 2029-09-08 20:00 | 224 | 2.5
Shannonbridge | SQ1 | 262 | 2029-09-10 08:00 | 2029-09-12 20:00 | 224 | 2.5
Irishtown | IS3 | 64 | 2029-09-10 08:00 | 2029-09-15 20:00 | S | 5.5
Ardnacrusha | AA4 | 24 | 2029-09-11 | 2029-09-16 | S | 5
Shannonbridge | SQ1 | 262 | 2029-09-13 | 2029-09-14 20:00 | 128 | 1.83
Shannonbridge | SQ1 | 262 | 2029-09-13 08:00 | 2029-09-15 20:00 | 224 | 2.5
Lisdrum | LF1 | 60 | 2029-09-17 | 2029-09-21 | S | 4
Shannonbridge | SQ1 | 262 | 2029-09-17 08:00 | 2029-09-19 20:00 | 224 | 2.5
Corduff | FG2 | 64 | 2029-09-17 08:00 | 2029-09-22 20:00 | S | 5.5
Edenderry | ED3 | 58 | 2029-09-18 08:00 | 2029-09-18 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2029-09-18 08:00 | 2029-09-18 18:00 | S | 0.42
Shannonbridge | SQ1 | 262 | 2029-09-20 08:00 | 2029-09-22 20:00 | 224 | 2.5
Shannonbridge | SQ1 | 262 | 2029-09-24 08:00 | 2029-09-26 20:00 | 224 | 2.5
Shannonbridge | SQ1 | 262 | 2029-09-27 08:00 | 2029-09-28 20:00 | 128 | 1.5
Shannonbridge | SQ1 | 262 | 2029-09-27 08:00 | 2029-09-29 20:00 | 224 | 2.5
Huntstown | HNC | 342 | 2029-10-01 | 2029-10-22 | S | 21
Whitebank | DW1 | 61.5 | 2029-10-02 | 2029-10-06 | 26 | 4
Aghada | AD4 | 75 | 2029-10-08 08:00 | 2029-10-18 20:00 | 60 | 10.5
Inchicore | IH1 | 30 | 2029-10-08 08:00 | 2029-10-13 20:00 | S | 5.5
Whitebank | DW1 | 61.5 | 2029-10-09 | 2029-10-13 | 26 | 4
Aghada | AD3 | 19 | 2029-10-15 08:00 | 2029-10-18 20:00 | 14 | 3.5
Aghada | AD5 | 75 | 2029-10-18 | 2029-10-28 20:00 | 60 | 10.83
Seal Rock | SK3 | 83 | 2029-11-05 06:00 | 2029-11-07 18:00 | S | 2.5
Irishtown | IS2 | 30 | 2029-11-05 08:00 | 2029-11-08 20:00 | 25 | 3.5
Poolbeg | PB8 | 75 | 2029-11-12 08:00 | 2029-11-23 20:00 | S | 11.5
Lisdrum | LF1 | 60 | 2029-12-03 | 2029-12-04 | S | 1
Seal Rock | SK4 | 83 | 2029-12-03 06:00 | 2029-12-05 18:00 | S | 2.5
Lisdrum | LF1 | 60 | 2029-12-04 | 2029-12-08 | S | 4
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2029 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2029 |  |  |  |  | Feb '2029 |  |  |  | Mar '2029 |  |  |  | Apr '2029 |  |  |  |  | May '2029 |  |  |  | Jun '2029 |  |  |  | Jul '2029 |  |  |  |  | Aug '2029 |  |  |  | Sep '2029 |  |  |  | Oct '2029 |  |  |  |  | Nov '2029 |  |  |  | Dec '2029
|  | Week | 1 '2029 | 2 '2029 | 3 '2029 | 4 '2029 | 5 '2029 | 6 '2029 | 7 '2029 | 8 '2029 | 9 '2029 | 10 '2029 | 11 '2029 | 12 '2029 | 13 '2029 | 14 '2029 | 15 '2029 | 16 '2029 | 17 '2029 | 18 '2029 | 19 '2029 | 20 '2029 | 21 '2029 | 22 '2029 | 23 '2029 | 24 '2029 | 25 '2029 | 26 '2029 | 27 '2029 | 28 '2029 | 29 '2029 | 30 '2029 | 31 '2029 | 32 '2029 | 33 '2029 | 34 '2029 | 35 '2029 | 36 '2029 | 37 '2029 | 38 '2029 | 39 '2029 | 40 '2029 | 41 '2029 | 42 '2029 | 43 '2029 | 44 '2029 | 45 '2029 | 46 '2029 | 47 '2029 | 48 '2029 | 49 '2029 | 50 '2029 | 51 '2029 | 52 '2029 | 53 '2029
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2
Ballydown BESS | NIBLD | 12
Ballylumford | NIB10 | 94 | [35 empty] | S | S
Ballylumford | NIB31 | 249 | [17 empty] | S | S | S | S
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58
Caherty | NICHT | 5
Carmeen | NICMN | 20
Castlereagh BESS | NICSB | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [35 empty] | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
Drumkee BESS | NIDK1 | 50
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Kells BESS | NIKEB | 50
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [28 empty] | S | S | S | S | S | S | S
Kilroot | NIKGT4 | 42
Kilroot | NIKGT6 | 350
Kilroot | NIKGT7 | 350 | [14 empty] | S | S | S
Lisahally | NILPS | 18 | [19 empty] | S | S
Moyle | MOYLE | 450
Mullavilly BESS | NIMZ1 | 50
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Coolkeeragh | NIC30 | 408 | 2029-01-06 | 2029-01-07 00:30 | S | 1
Ballylumford | NIB10 | 94 | 2029-02-09 | 2029-02-13 | S | 4
Ballylumford | NIB31 | 249 | 2029-03-02 | 2029-03-05 | S | 3
Drumkee BESS | NIDK1 | 50 | 2029-04-01 | 2029-04-05 00:30 | S | 4
Mullavilly BESS | NIMZ1 | 50 | 2029-04-01 | 2029-04-06 | S | 5
Kilroot | NIKGT7 | 350 | 2029-04-09 | 2029-04-27 | S | 18
Castlereagh BESS | NICSB | 50 | 2029-04-16 | 2029-04-17 | 40 | 1
Ballylumford | NIB31 | 249 | 2029-05-01 | 2029-05-30 | S | 29
Lisahally | NILPS | 17.6 | 2029-05-13 | 2029-05-28 | S | 15
Coolkeeragh | NICGT8 | 53 | 2029-05-14 | 2029-05-18 00:30 | S | 4
Kilroot | NIKGT6 | 350 | 2029-06-01 | 2029-06-06 | S | 5
Kilroot | NIKGT4 | 42 | 2029-06-01 | 2029-06-06 | S | 5
Moyle | MOYLE | 450 | 2029-06-12 | 2029-06-15 | 250 | 3
Carmeen | NICMN | 20 | 2029-06-16 | 2029-06-21 | S | 5
Kilroot | NIKGT1 | 29 | 2029-06-18 | 2029-06-21 | S | 3
Kilroot | NIKGT2 | 29 | 2029-06-21 | 2029-06-24 | S | 3
Kilroot | NIKGT3 | 42 | 2029-07-13 | 2029-09-01 | S | 50
Castlereagh BESS | NICSB | 50 | 2029-07-30 | 2029-08-01 00:30 | S | 2
Ballydown BESS | NIBLD | 12 | 2029-08-01 | 2029-08-02 00:30 | 10 | 1
Ballylumford | NIB10 | 94 | 2029-09-01 | 2029-09-15 | S | 14
Coolkeeragh | NIC30 | 408 | 2029-09-03 | 2029-09-29 00:30 | S | 26
Kells BESS | NIKEB | 50 | 2029-09-03 | 2029-09-15 | 40 | 12
Ballylumford | NIB31 | 249 | 2029-09-17 | 2029-10-01 | 161 | 14
Castlereagh BESS | NICSB | 50 | 2029-10-22 | 2029-10-23 | 40 | 1
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2029 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2029 |  |  |  |  | Feb '2029 |  |  |  | Mar '2029 |  |  |  | Apr '2029 |  |  |  |  | May '2029 |  |  |  | Jun '2029 |  |  |  | Jul '2029 |  |  |  |  | Aug '2029 |  |  |  | Sep '2029 |  |  |  | Oct '2029 |  |  |  |  | Nov '2029 |  |  |  | Dec '2029
|  | Week | 1 '2029 | 2 '2029 | 3 '2029 | 4 '2029 | 5 '2029 | 6 '2029 | 7 '2029 | 8 '2029 | 9 '2029 | 10 '2029 | 11 '2029 | 12 '2029 | 13 '2029 | 14 '2029 | 15 '2029 | 16 '2029 | 17 '2029 | 18 '2029 | 19 '2029 | 20 '2029 | 21 '2029 | 22 '2029 | 23 '2029 | 24 '2029 | 25 '2029 | 26 '2029 | 27 '2029 | 28 '2029 | 29 '2029 | 30 '2029 | 31 '2029 | 32 '2029 | 33 '2029 | 34 '2029 | 35 '2029 | 36 '2029 | 37 '2029 | 38 '2029 | 39 '2029 | 40 '2029 | 41 '2029 | 42 '2029 | 43 '2029 | 44 '2029 | 45 '2029 | 46 '2029 | 47 '2029 | 48 '2029 | 49 '2029 | 50 '2029 | 51 '2029 | 52 '2029 | 53 '2029
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 2
Aghada | AD2 | 449 | [31 empty] | S | S
Aghada | AD3 | 19 | [13 empty] | S
Aghada | AD4 | 75 | [14 empty] | S | S
Aghada | AD5 | 75 | [15 empty] | S | S
Aghada | AT1 | 90
Aghada | AT2 | 90
Aghada | AT4 | 90
Ardnacrusha | AA1 | 21 | [19 empty] | S
Ardnacrusha | AA2 | 22 | [13 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA3 | 19 | [23 empty] | S
Ardnacrusha | AA4 | 24 | [36 empty] | S
Aughinish Alumina | EB1 | 25
Ballydown BESS | NIBLD | 12
Ballylumford | NIB10 | 94 | [35 empty] | S | S
Ballylumford | NIB31 | 249 | [17 empty] | S | S | S | S
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58
Ballylumford | NIBGT2 | 58
Ballymakaily | IL1 | 18
Ballymakaily | IL2 | 18
Ballymakaily | IL3 | 18
Ballymakaily | IL4 | 18
Ballymakaily | IL5 | 18
Ballymakaily | IL6 | 18
Banoge | OD1 | 9
Caherty | NICHT | 5
Carmeen | NICMN | 20
Castlelost | LZ1 | 55
Castlelost | LZ2 | 55
Castlelost | LZ3 | 55
Castlelost | LZ4 | 55
Castlelost | LZ5 | 55
Castlereagh BESS | NICSB | 50
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [35 empty] | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Corduff | FG2 | 64 | [37 empty] | S
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drumkee BESS | NIDK1 | 50
Drybridge | IW1 | 17 | [14 empty] | S | S
Dublin Bay | DB1 | 415
Dunsoghly | DG1 | 50
Edenderry | ED1 | 118 | [26 empty] | S | S | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electricity Exchange | NIVN1 | 8
Empower | NIEMP | 13
Endeco Technologies | EC1 | 53
Endeco Technologies | EC2 | 13
Endeco Technologies | EC3 | 6
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 17
Endeco Technologies | EC6 | 4
Endeco Technologies | NIECA | 25
Endeco Technologies | NIECB | 9
Enel X | AE1 | 80
Enel X | AE2 | 12
Enel X | AE3 | 14
Enel X | AE4 | 23
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 5
Enel X | EN6 | 31
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading | NIETB | 6
Energy Trading | NIETD | 5
Energy Trading | NIETR | 5
Energy Trading Ireland | ET1 | 5
Energy Trading Ireland | NIETC | 5
Energy Trading Ireland | NIETE | 6
Energy Trading Ireland | NIETF | 6
Erne | ER1 | 10 | [19 empty] | S
Erne | ER2 | 10 | [14 empty] | S | S | S
Erne | ER3 | 23 | [23 empty] | S
Erne | ER4 | 23 | [27 empty] | S
EWIC | EW1 | 500 | [14 empty] | S | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3 | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F
Gorman | GF1 | 50
Great Island | GI4 | 464
Huntstown | HN2 | 402
Huntstown | HNC | 342 | [39 empty] | S | S | S
Inchicore | IH1 | 30 | [40 empty] | S
iPower | NIAGU | 63
iPower | NIID1 | 5
iPower | NIID2 | 6
iPower | NIID3 | 10
Irishtown | IS2 | 30 | [19 empty] | S
Irishtown | IS3 | 64 | [36 empty] | S
Kells BESS | NIKEB | 50
Kilcumber | OE2 | 25
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42 | [28 empty] | S | S | S | S | S | S | S
Kilroot | NIKGT4 | 42
Kilroot | NIKGT6 | 350
Kilroot | NIKGT7 | 350 | [14 empty] | S | S | S
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [18 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Lee | LE2 | 4 | [11 empty] | S | S
Lee | LE3 | 8 | [14 empty] | S | S
Liffey | LI1 | 15 | [17 empty] | S | S | S | S | S | S | S | S | S
Liffey | LI2 | 15 | [17 empty] | S | S | S | S | S | S | S | S | S
Liffey | LI4 | 4 | [28 empty] | S | S
Liffey | LI5 | 4 | [32 empty] | S | S
Lisahally | NILPS | 18 | [19 empty] | S | S
Lisdrum | LF1 | 60 | [24 empty] | S | S | [11 empty] | S | [10 empty] | S
Loughtown | GLK | 500
Moneypoint | MP1 | 285
Moneypoint | MP2 | 285
Moneypoint | MP3 | 285
Moneypoint | MP5 | 1 | [23 empty] | S
Moyle | MOYLE | 450
Mullavilly BESS | NIMZ1 | 50
Northwall | NW8 | 199
Poolbeg | PB4 | 156
Poolbeg | PB5 | 153 | [21 empty] | S | S | S | S | S | S | S
Poolbeg | PB6 | 168
Poolbeg | PB7 | 64 | [35 empty] | S
Poolbeg | PB8 | 75 | [45 empty] | S | S
PowerHouse | NIPH2 | 14
Powerhouse Generation | NIPH1 | 14
Powerhouse Generation | PG1 | 10
Powerhouse Generation | PG2 | 4
Powerhouse Generation | PG6 | 4
Raghra | RG1 | 63
Raghra | RG2 | 1
Rhode | RP1 | 52 | [19 empty] | S | S
Rhode | RP2 | 52 | [19 empty] | S | S
Seal Rock | SK3 | 83 | [24 empty] | S | S | S | S
Seal Rock | SK4 | 83 | [32 empty] | S
Shannonbridge | SQ1 | 262
Tarbert | TB5 | 160
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [23 empty] | S | S
Tawnaghmore | TP3 | 52 | [23 empty] | S | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [12 empty] | S | S | S
Turlough Hill | TH2 | 73 | [12 empty] | S | S | S
Turlough Hill | TH3 | 73 | [12 empty] | S | S | S
Turlough Hill | TH4 | 73 | [12 empty] | S | S | S
Tynagh | TYC | 404 | [29 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 8
Veolia Alternative Energy | DP2 | 21
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 59
VIOTAS | EE2 | 25
VIOTAS | EE3 | 13
VIOTAS | EE4 | 15
VIOTAS | EE5 | 25
VIOTAS | EE6 | 14
VIOTAS | EE7 | 37
VIOTAS | EE8 | 5
VIOTAS | EE9 | 5
VIOTAS | VS1 | 5
VIOTAS | VS2 | 6
VIOTAS | VS6 | 5
Whitebank | DW1 | 62 | [14 empty] | S | S
Whitegate | WG1 | 444 | [34 empty] | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Golagh | GO2 | 3 | 2023-04-17 15:30 | 2031-01-01 | F | 2815.33
Edenderry | ED1 | 118 | 2028-12-26 12:00 | 2029-01-01 08:00 | S | 5.83
Coolkeeragh | NIC30 | 408 | 2029-01-06 | 2029-01-07 00:30 | S | 1
Seal Rock | SK4 | 83 | 2029-01-22 06:00 | 2029-01-24 18:00 | S | 2.5
Ballylumford | NIB10 | 94 | 2029-02-09 | 2029-02-13 | S | 4
Seal Rock | SK3 | 83 | 2029-02-26 06:00 | 2029-02-28 18:00 | S | 2.5
Ballylumford | NIB31 | 249 | 2029-03-02 | 2029-03-05 | S | 3
Lee | LE2 | 4 | 2029-03-20 08:00 | 2029-03-30 20:00 | S | 10.5
Turlough Hill | TH3 | 73 | 2029-03-25 | 2029-04-14 | S | 20
Turlough Hill | TH4 | 73 | 2029-03-25 | 2029-04-14 | S | 20
Turlough Hill | TH1 | 73 | 2029-03-25 | 2029-04-14 | S | 20
Turlough Hill | TH2 | 73 | 2029-03-25 | 2029-04-14 | S | 20
Edenderry | ED1 | 118 | 2029-03-29 17:00 | 2029-04-04 08:00 | S | 5.58
Drumkee BESS | NIDK1 | 50 | 2029-04-01 | 2029-04-05 00:30 | S | 4
Mullavilly BESS | NIMZ1 | 50 | 2029-04-01 | 2029-04-06 | S | 5
Aghada | AD3 | 19 | 2029-04-02 08:00 | 2029-04-07 20:00 | S | 5.5
Ardnacrusha | AA2 | 22 | 2029-04-04 | 2029-10-30 | S | 209
Whitebank | DW1 | 61.5 | 2029-04-05 | 2029-04-11 | 26 | 6
Aghada | AT1 | 90 | 2029-04-07 | 2029-04-11 20:00 | S | 4.83
Drybridge | IW1 | 17 | 2029-04-08 | 2029-04-21 | S | 13
Kilroot | NIKGT7 | 350 | 2029-04-09 | 2029-04-27 | S | 18
Loughtown | GLK | 500 | 2029-04-09 06:00 | 2029-04-12 23:00 | S | 3.67
Inchicore | IH1 | 30 | 2029-04-09 08:00 | 2029-04-12 20:00 | 25 | 3.5
Aghada | AD4 | 75 | 2029-04-09 08:00 | 2029-04-19 20:00 | S | 10.5
Lee | LE3 | 8 | 2029-04-09 08:00 | 2029-04-20 20:00 | S | 11.5
Erne | ER2 | 10 | 2029-04-09 08:00 | 2029-04-27 20:00 | S | 18.5
EWIC | EW1 | 500 | 2029-04-09 09:00 | 2029-04-09 21:00 | S | 0.5
EWIC | EW1 | 500 | 2029-04-09 21:00 | 2029-04-23 23:00 | S | 14.08
Whitebank | DW1 | 61.5 | 2029-04-10 | 2029-04-21 | S | 11
Aghada | AT2 | 90 | 2029-04-14 08:00 | 2029-04-18 20:00 | S | 4.5
Castlereagh BESS | NICSB | 50 | 2029-04-16 | 2029-04-17 | 40 | 1
Aghada | AD5 | 75 | 2029-04-19 | 2029-04-29 20:00 | S | 10.83
Whitebank | DW1 | 61.5 | 2029-04-20 | 2029-04-26 | 26 | 6
Aghada | AT4 | 90 | 2029-04-21 | 2029-04-25 20:00 | S | 4.83
Seal Rock | SK4 | 83 | 2029-04-23 06:00 | 2029-04-25 18:00 | S | 2.5
Liffey | LI1 | 15 | 2029-04-30 | 2029-06-30 | S | 61
Liffey | LI2 | 15 | 2029-04-30 | 2029-06-30 | S | 61
Poolbeg | PB8 | 75 | 2029-04-30 08:00 | 2029-05-10 20:00 | 60 | 10.5
Ballylumford | NIB31 | 249 | 2029-05-01 | 2029-05-30 | S | 29
Lee | LE1 | 15 | 2029-05-08 08:00 | 2029-09-07 20:00 | S | 122.5
Rhode | RP2 | 52 | 2029-05-11 | 2029-05-26 | S | 15
Rhode | RP1 | 52 | 2029-05-11 | 2029-05-26 | S | 15
Lisahally | NILPS | 17.6 | 2029-05-13 | 2029-05-28 | S | 15
Erne | ER1 | 10 | 2029-05-14 | 2029-05-19 | S | 5
Coolkeeragh | NICGT8 | 53 | 2029-05-14 | 2029-05-18 00:30 | S | 4
Irishtown | IS2 | 30 | 2029-05-14 08:00 | 2029-05-19 20:00 | S | 5.5
Seal Rock | SK3 | 83 | 2029-05-14 18:00 | 2029-05-17 18:00 | S | 3
Seal Rock | SK4 | 83 | 2029-05-15 | 2029-05-17 12:00 | S | 2.5
Ardnacrusha | AA1 | 21 | 2029-05-15 | 2029-05-20 | S | 5
Poolbeg | PB6 | 168 | 2029-05-25 | 2029-07-15 | 84 | 51
Poolbeg | PB5 | 153 | 2029-05-25 | 2029-07-15 | S | 51
Kilroot | NIKGT6 | 350 | 2029-06-01 | 2029-06-06 | S | 5
Kilroot | NIKGT4 | 42 | 2029-06-01 | 2029-06-06 | S | 5
Tawnaghmore | TP3 | 52 | 2029-06-08 | 2029-06-23 | S | 15
Tawnaghmore | TP1 | 52 | 2029-06-08 | 2029-06-23 | S | 15
Erne | ER3 | 23 | 2029-06-11 08:00 | 2029-06-15 20:00 | S | 4.5
Moneypoint | MP5 | 1 | 2029-06-11 08:00 | 2029-06-16 20:00 | S | 5.5
Ardnacrusha | AA3 | 19 | 2029-06-12 | 2029-06-17 | S | 5
Moyle | MOYLE | 450 | 2029-06-12 | 2029-06-15 | 250 | 3
Carmeen | NICMN | 20 | 2029-06-16 | 2029-06-21 | S | 5
Seal Rock | SK3 | 83 | 2029-06-17 06:00 | 2029-07-17 06:00 | S | 30
Lisdrum | LF1 | 60 | 2029-06-18 | 2029-06-30 | S | 12
Kilroot | NIKGT1 | 29 | 2029-06-18 | 2029-06-21 | S | 3
Kilroot | NIKGT2 | 29 | 2029-06-21 | 2029-06-24 | S | 3
Edenderry | ED1 | 118 | 2029-06-29 11:00 | 2029-07-31 08:00 | S | 31.83
Erne | ER4 | 23 | 2029-07-09 08:00 | 2029-07-13 20:00 | S | 4.5
Kilroot | NIKGT3 | 42 | 2029-07-13 | 2029-09-01 | S | 50
Liffey | LI4 | 4 | 2029-07-16 | 2029-07-27 23:30 | S | 11.96
Tynagh | TYC | 404 | 2029-07-20 | 2029-07-31 | S | 11
Castlereagh BESS | NICSB | 50 | 2029-07-30 | 2029-08-01 00:30 | S | 2
Ballydown BESS | NIBLD | 12 | 2029-08-01 | 2029-08-02 00:30 | 10 | 1
Aghada | AD2 | 449 | 2029-08-04 | 2029-08-16 20:00 | S | 12.83
Liffey | LI5 | 4 | 2029-08-13 | 2029-08-25 | S | 12
Seal Rock | SK4 | 83 | 2029-08-13 06:00 | 2029-08-17 18:00 | S | 4.5
Whitegate | WG1 | 444 | 2029-08-25 | 2029-09-04 00:30 | S | 10
Ballylumford | NIB10 | 94 | 2029-09-01 | 2029-09-15 | S | 14
Coolkeeragh | NIC30 | 408 | 2029-09-03 | 2029-09-29 00:30 | S | 26
Kells BESS | NIKEB | 50 | 2029-09-03 | 2029-09-15 | 40 | 12
Poolbeg | PB7 | 64 | 2029-09-03 08:00 | 2029-09-08 20:00 | S | 5.5
Shannonbridge | SQ1 | 262 | 2029-09-03 08:00 | 2029-09-06 | 224 | 2.67
Shannonbridge | SQ1 | 262 | 2029-09-06 08:00 | 2029-09-08 20:00 | 224 | 2.5
Shannonbridge | SQ1 | 262 | 2029-09-10 08:00 | 2029-09-12 20:00 | 224 | 2.5
Irishtown | IS3 | 64 | 2029-09-10 08:00 | 2029-09-15 20:00 | S | 5.5
Ardnacrusha | AA4 | 24 | 2029-09-11 | 2029-09-16 | S | 5
Shannonbridge | SQ1 | 262 | 2029-09-13 | 2029-09-14 20:00 | 128 | 1.83
Shannonbridge | SQ1 | 262 | 2029-09-13 08:00 | 2029-09-15 20:00 | 224 | 2.5
Lisdrum | LF1 | 60 | 2029-09-17 | 2029-09-21 | S | 4
Ballylumford | NIB31 | 249 | 2029-09-17 | 2029-10-01 | 161 | 14
Shannonbridge | SQ1 | 262 | 2029-09-17 08:00 | 2029-09-19 20:00 | 224 | 2.5
Corduff | FG2 | 64 | 2029-09-17 08:00 | 2029-09-22 20:00 | S | 5.5
Edenderry | ED3 | 58 | 2029-09-18 08:00 | 2029-09-18 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2029-09-18 08:00 | 2029-09-18 18:00 | S | 0.42
Shannonbridge | SQ1 | 262 | 2029-09-20 08:00 | 2029-09-22 20:00 | 224 | 2.5
Shannonbridge | SQ1 | 262 | 2029-09-24 08:00 | 2029-09-26 20:00 | 224 | 2.5
Shannonbridge | SQ1 | 262 | 2029-09-27 08:00 | 2029-09-28 20:00 | 128 | 1.5
Shannonbridge | SQ1 | 262 | 2029-09-27 08:00 | 2029-09-29 20:00 | 224 | 2.5
Huntstown | HNC | 342 | 2029-10-01 | 2029-10-22 | S | 21
Whitebank | DW1 | 61.5 | 2029-10-02 | 2029-10-06 | 26 | 4
Aghada | AD4 | 75 | 2029-10-08 08:00 | 2029-10-18 20:00 | 60 | 10.5
Inchicore | IH1 | 30 | 2029-10-08 08:00 | 2029-10-13 20:00 | S | 5.5
Whitebank | DW1 | 61.5 | 2029-10-09 | 2029-10-13 | 26 | 4
Aghada | AD3 | 19 | 2029-10-15 08:00 | 2029-10-18 20:00 | 14 | 3.5
Aghada | AD5 | 75 | 2029-10-18 | 2029-10-28 20:00 | 60 | 10.83
Castlereagh BESS | NICSB | 50 | 2029-10-22 | 2029-10-23 | 40 | 1
Seal Rock | SK3 | 83 | 2029-11-05 06:00 | 2029-11-07 18:00 | S | 2.5
Irishtown | IS2 | 30 | 2029-11-05 08:00 | 2029-11-08 20:00 | 25 | 3.5
Poolbeg | PB8 | 75 | 2029-11-12 08:00 | 2029-11-23 20:00 | S | 11.5
Lisdrum | LF1 | 60 | 2029-12-03 | 2029-12-04 | S | 1
Seal Rock | SK4 | 83 | 2029-12-03 06:00 | 2029-12-05 18:00 | S | 2.5
Lisdrum | LF1 | 60 | 2029-12-04 | 2029-12-08 | S | 4
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10