## Outage Plan EirGrid
2024 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2024 |  |  |  |  | Feb '2024 |  |  |  | Mar '2024 |  |  |  | Apr '2024 |  |  |  |  | May '2024 |  |  |  | Jun '2024 |  |  |  | Jul '2024 |  |  |  |  | Aug '2024 |  |  |  | Sep '2024 |  |  |  |  | Oct '2024 |  |  |  | Nov '2024 |  |  |  | Dec '2024
|  | Week | 1 '2024 | 2 '2024 | 3 '2024 | 4 '2024 | 5 '2024 | 6 '2024 | 7 '2024 | 8 '2024 | 9 '2024 | 10 '2024 | 11 '2024 | 12 '2024 | 13 '2024 | 14 '2024 | 15 '2024 | 16 '2024 | 17 '2024 | 18 '2024 | 19 '2024 | 20 '2024 | 21 '2024 | 22 '2024 | 23 '2024 | 24 '2024 | 25 '2024 | 26 '2024 | 27 '2024 | 28 '2024 | 29 '2024 | 30 '2024 | 31 '2024 | 32 '2024 | 33 '2024 | 34 '2024 | 35 '2024 | 36 '2024 | 37 '2024 | 38 '2024 | 39 '2024 | 40 '2024 | 41 '2024 | 42 '2024 | 43 '2024 | 44 '2024 | 45 '2024 | 46 '2024 | 47 '2024 | 48 '2024 | 49 '2024 | 50 '2024 | 51 '2024 | 52 '2024 | 53 '2024
Station | Unit | NPR
Aghada | AD2 | 449
Aghada | AD3 | 19 | [13 empty] | S
Aghada | AT1 | 90 | [13 empty] | S | S | S | S | [35 empty] | S
Aghada | AT2 | 90 | [15 empty] | S | S | [18 empty] | S
Aghada | AT4 | 90 | [17 empty] | S | S | [17 empty] | S
Ardnacrusha | AA1 | 21 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA2 | 22 | [23 empty] | S
Ardnacrusha | AA3 | 19 | [36 empty] | S
Ardnacrusha | AA4 | 24 | [18 empty] | S | S | S
Banoge | OD1 | 9
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17 | [15 empty] | S | S
Dublin Bay | DB1 | 415 | [14 empty] | S | S | S
Edenderry | ED1 | 118 | [26 empty] | S | S | S | S | S | S | S | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 17
Endeco Technologies | EC1 | 52
Endeco Technologies | EC2 | 12
Endeco Technologies | EC3 | 5
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 21
Enel X | AE1 | 87
Enel X | AE2 | 13
Enel X | AE3 | 14
Enel X | AE4 | 16
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 6
Enel X | EN6 | 11
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [14 empty] | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 23 | [23 empty] | S
Erne | ER4 | 23 | [31 empty] | S | S | S | S | S | S | S | S
EWIC | EW1 | 500 | [15 empty] | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464 | [20 empty] | S | S | S
Huntstown | HN2 | 402 | [40 empty] | S | S | S
Huntstown | HNC | 342 | [17 empty] | S | S | S
Inchicore | IH1 | 30 | [14 empty] | S
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [19 empty] | S | S
Lee | LE2 | 4 | [11 empty] | S | S
Lee | LE3 | 8 | [14 empty] | S | S
Liffey | LI1 | 15 | [18 empty] | S | S | S | S | S | S | S | S
Liffey | LI2 | 15 | [18 empty] | S | S | S | S | S | S | S | S
Liffey | LI4 | 4 | [22 empty] | S | S | S | S
Liffey | LI5 | 4 | [27 empty] | S
Lisdrum | LF1 | 60
Moneypoint | MP1 | 285 | [19 empty] | S | S
Moneypoint | MP2 | 285 | [20 empty] | S | S
Moneypoint | MP3 | 285 | [35 empty] | S | S | S | S | S | S | S | S
Moneypoint | MP5 | 1
Poolbeg | PB4 | 148
Poolbeg | PB5 | 148 | [22 empty] | S | S
Poolbeg | PB6 | 168 | [37 empty] | S | S | S | S | S
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 83 | [29 empty] | S
Seal Rock | SK4 | 83 | [15 empty] | S | S | S | S | S | S | S | S | S | S | S | S
Tarbert | TB1 | 54 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tarbert | TB2 | 54 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tarbert | TB3 | 241 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tarbert | TB4 | 241 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [26 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Tawnaghmore | TP3 | 52 | [26 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [9 empty] | S | S
Turlough Hill | TH2 | 73 | [9 empty] | S | S
Turlough Hill | TH3 | 73 | [9 empty] | S | S
Turlough Hill | TH4 | 73 | [9 empty] | S | S
Tynagh | TYC | 404 | [25 empty] | S | S | S | S | S | S | S | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 5
Veolia Alternative Energy | DP2 | 30
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 65
VIOTAS | EE2 | 30
VIOTAS | EE3 | 11
VIOTAS | EE4 | 13
VIOTAS | EE5 | 17
VIOTAS | EE6 | 14
VIOTAS | EE7 | 7
VIOTAS | EE8 | 12
VIOTAS | EE9 | 11
Whitebank | DW1 | 62 | [14 empty] | S
Whitegate | WG1 | 444

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2023-12-26 12:00 | 2024-01-02 08:00 | S | 6.83
Tarbert | TB1 | 54 | 2024-01-01 | 2025-01-01 | S | 366
Tarbert | TB2 | 54 | 2024-01-01 | 2025-01-01 | S | 366
Tarbert | TB3 | 241 | 2024-01-01 | 2025-01-01 | S | 366
Tarbert | TB4 | 241 | 2024-01-01 | 2025-01-01 | S | 366
Moneypoint | MP1 | 285 | 2024-01-01 | 2024-05-10 22:00 | 260 | 130.92
Moneypoint | MP2 | 285 | 2024-01-01 | 2024-05-17 22:00 | 235 | 137.92
Moneypoint | MP3 | 285 | 2024-01-01 | 2024-08-30 22:00 | 260 | 242.92
Edenderry | ED1 | 118 | 2024-01-02 08:00 | 2024-03-28 17:00 | 95 | 86.33
Turlough Hill | TH2 | 73 | 2024-03-03 06:00 | 2024-03-15 18:00 | S | 12.5
Turlough Hill | TH3 | 73 | 2024-03-03 06:00 | 2024-03-15 18:00 | S | 12.5
Turlough Hill | TH4 | 73 | 2024-03-03 06:00 | 2024-03-15 18:00 | S | 12.5
Turlough Hill | TH1 | 73 | 2024-03-03 06:00 | 2024-03-15 18:00 | S | 12.5
Aghada | AD2 | 449 | 2024-03-15 | 2024-03-22 23:00 | S | 7.92
Lee | LE2 | 4 | 2024-03-19 08:00 | 2024-03-29 20:00 | S | 10.5
Seal Rock | SK3 | 83 | 2024-03-25 06:00 | 2024-03-27 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2024-03-28 17:00 | 2024-04-03 08:00 | S | 5.58
Whitebank | DW1 | 61.5 | 2024-04-01 | 2024-04-07 | 26 | 6
Aghada | AT1 | 90 | 2024-04-01 | 2024-04-30 | S | 29
Moneypoint | MP5 | 1 | 2024-04-01 07:00 | 2024-04-03 19:00 | S | 2.5
Aghada | AD3 | 19 | 2024-04-01 07:00 | 2024-04-06 19:00 | S | 5.5
Edenderry | ED1 | 118 | 2024-04-03 08:00 | 2024-06-28 12:00 | 95 | 86.17
Dublin Bay | DB1 | 415 | 2024-04-05 12:00 | 2024-04-29 18:00 | S | 24.25
Whitebank | DW1 | 61.5 | 2024-04-06 | 2024-04-17 | S | 11
Inchicore | IH1 | 30 | 2024-04-08 07:00 | 2024-04-13 19:00 | S | 5.5
Lee | LE3 | 8 | 2024-04-08 08:00 | 2024-04-19 20:00 | S | 11.5
Ardnacrusha | AA1 | 21 | 2024-04-08 08:00 | 2024-09-13 18:00 | S | 158.42
Erne | ER1 | 10 | 2024-04-08 08:00 | 2024-04-12 20:00 | S | 4.5
Drybridge | IW1 | 17 | 2024-04-14 | 2024-05-01 | S | 17
Aghada | AT2 | 90 | 2024-04-15 | 2024-04-30 | S | 15
Seal Rock | SK4 | 83 | 2024-04-15 06:00 | 2024-07-09 18:00 | S | 85.5
EWIC | EW1 | 500 | 2024-04-15 09:00 | 2024-04-15 21:00 | S | 0.5
EWIC | EW1 | 500 | 2024-04-15 21:00 | 2024-04-19 23:00 | S | 4.08
Whitebank | DW1 | 61.5 | 2024-04-16 | 2024-04-22 | 26 | 6
Aghada | AT4 | 90 | 2024-04-26 | 2024-05-10 | S | 14
Huntstown | HNC | 342 | 2024-04-26 21:00 | 2024-05-16 21:00 | S | 20
Liffey | LI1 | 15 | 2024-05-07 08:00 | 2024-06-28 20:00 | S | 52.5
Ardnacrusha | AA4 | 24 | 2024-05-07 08:00 | 2024-05-24 20:00 | S | 17.5
Liffey | LI2 | 15 | 2024-05-07 08:00 | 2024-06-28 20:00 | S | 52.5
Moneypoint | MP1 | 285 | 2024-05-10 22:00 | 2024-05-26 22:00 | S | 16
Erne | ER2 | 10 | 2024-05-13 08:00 | 2024-05-17 20:00 | S | 4.5
Lee | LE1 | 15 | 2024-05-13 08:00 | 2024-05-24 20:00 | S | 11.5
Seal Rock | SK4 | 83 | 2024-05-13 18:00 | 2024-05-16 18:00 | S | 3
Seal Rock | SK3 | 83 | 2024-05-14 | 2024-05-16 12:00 | S | 2.5
Great Island | GI4 | 464 | 2024-05-17 | 2024-06-10 | S | 24
Moneypoint | MP2 | 285 | 2024-05-17 22:00 | 2024-06-02 22:00 | S | 16
Rhode | RP1 | 52 | 2024-05-25 08:00 | 2024-05-31 16:00 | S | 6.33
Rhode | RP2 | 52 | 2024-05-25 08:00 | 2024-05-31 16:00 | S | 6.33
Moneypoint | MP1 | 285 | 2024-05-26 22:00 | 2025-01-01 | 260 | 219.08
Poolbeg | PB5 | 148 | 2024-06-02 | 2024-06-15 20:00 | S | 13.83
Poolbeg | PB6 | 168 | 2024-06-02 | 2024-06-15 20:00 | 84 | 13.83
Moneypoint | MP2 | 285 | 2024-06-02 22:00 | 2025-01-01 | 235 | 212.08
Liffey | LI4 | 4 | 2024-06-06 08:00 | 2024-06-28 20:00 | S | 22.5
Erne | ER3 | 23 | 2024-06-10 08:00 | 2024-06-14 20:00 | S | 4.5
Ardnacrusha | AA2 | 22 | 2024-06-10 08:00 | 2024-06-14 20:00 | S | 4.5
Tynagh | TYC | 404 | 2024-06-21 20:00 | 2024-08-15 20:00 | S | 55
Edenderry | ED1 | 118 | 2024-06-28 12:00 | 2024-09-02 08:00 | S | 65.83
Tawnaghmore | TP1 | 52 | 2024-06-29 09:00 | 2024-09-28 17:00 | S | 91.33
Tawnaghmore | TP3 | 52 | 2024-06-29 09:00 | 2024-09-28 17:00 | S | 91.33
Cloniffeen | SI1 | 50 | 2024-07-08 08:00 | 2024-07-09 17:00 | S | 1.33
Liffey | LI5 | 4 | 2024-07-08 08:00 | 2024-07-13 20:00 | S | 5.5
Cloniffeen | SI2 | 50 | 2024-07-08 08:00 | 2024-07-09 17:00 | S | 1.33
Seal Rock | SK3 | 83 | 2024-07-22 06:00 | 2024-07-26 18:00 | S | 4.5
Derrycarney | LU1 | 50 | 2024-07-22 08:00 | 2024-07-23 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2024-07-22 08:00 | 2024-07-23 17:00 | S | 1.33
Erne | ER4 | 23 | 2024-08-06 08:00 | 2024-09-27 20:00 | S | 52.5
Whitegate | WG1 | 444 | 2024-08-23 21:00 | 2024-08-30 21:00 | S | 7
Moneypoint | MP3 | 285 | 2024-08-30 22:00 | 2024-10-25 22:00 | S | 56
Edenderry | ED1 | 118 | 2024-09-02 08:00 | 2024-12-26 12:00 | 95 | 115.17
Aghada | AT2 | 90 | 2024-09-04 | 2024-09-08 | S | 4
Edenderry | ED3 | 58 | 2024-09-06 08:00 | 2024-09-06 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2024-09-06 08:00 | 2024-09-06 18:00 | S | 0.42
Ardnacrusha | AA3 | 19 | 2024-09-09 08:00 | 2024-09-13 20:00 | S | 4.5
Aghada | AT4 | 90 | 2024-09-11 | 2024-09-15 | S | 4
Poolbeg | PB6 | 168 | 2024-09-16 | 2024-10-20 20:00 | S | 34.83
Aghada | AD2 | 449 | 2024-09-27 | 2024-10-02 23:00 | S | 5.92
Seal Rock | SK4 | 83 | 2024-09-30 06:00 | 2024-10-02 18:00 | S | 2.5
Huntstown | HN2 | 402 | 2024-10-04 21:00 | 2024-10-29 21:00 | S | 25
Whitebank | DW1 | 61.5 | 2024-10-07 | 2024-10-11 | 26 | 4
Aghada | AD3 | 19 | 2024-10-07 07:00 | 2024-10-10 19:00 | S | 3.5
Whitebank | DW1 | 61.5 | 2024-10-14 | 2024-10-18 | 26 | 4
Inchicore | IH1 | 30 | 2024-10-14 07:00 | 2024-10-17 19:00 | S | 3.5
Moneypoint | MP3 | 285 | 2024-10-25 22:00 | 2025-01-01 | 260 | 67.08
Seal Rock | SK3 | 83 | 2024-11-11 06:00 | 2024-11-13 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2024-12-26 12:00 | 2025-01-01 08:00 | S | 5.83
Tarbert | TB1 | 54 | 2025-01-01 | 2026-01-01 | S | 365
Tarbert | TB2 | 54 | 2025-01-01 | 2026-01-01 | S | 365
Tarbert | TB3 | 241 | 2025-01-01 | 2026-01-01 | S | 365
Tarbert | TB4 | 241 | 2025-01-01 | 2026-01-01 | S | 365
Aghada | AT1 | 90 | 2025-01-01 | 2026-01-01 | S | 365
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2024 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2024 |  |  |  |  | Feb '2024 |  |  |  | Mar '2024 |  |  |  | Apr '2024 |  |  |  |  | May '2024 |  |  |  | Jun '2024 |  |  |  | Jul '2024 |  |  |  |  | Aug '2024 |  |  |  | Sep '2024 |  |  |  |  | Oct '2024 |  |  |  | Nov '2024 |  |  |  | Dec '2024
|  | Week | 1 '2024 | 2 '2024 | 3 '2024 | 4 '2024 | 5 '2024 | 6 '2024 | 7 '2024 | 8 '2024 | 9 '2024 | 10 '2024 | 11 '2024 | 12 '2024 | 13 '2024 | 14 '2024 | 15 '2024 | 16 '2024 | 17 '2024 | 18 '2024 | 19 '2024 | 20 '2024 | 21 '2024 | 22 '2024 | 23 '2024 | 24 '2024 | 25 '2024 | 26 '2024 | 27 '2024 | 28 '2024 | 29 '2024 | 30 '2024 | 31 '2024 | 32 '2024 | 33 '2024 | 34 '2024 | 35 '2024 | 36 '2024 | 37 '2024 | 38 '2024 | 39 '2024 | 40 '2024 | 41 '2024 | 42 '2024 | 43 '2024 | 44 '2024 | 45 '2024 | 46 '2024 | 47 '2024 | 48 '2024 | 49 '2024 | 50 '2024 | 51 '2024 | 52 '2024 | 53 '2024
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94 | [15 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Ballylumford | NIB31 | 249 | [32 empty] | S
Ballylumford | NIB32 | 249 | [33 empty] | S
Ballylumford | NIBGT1 | 58 | [41 empty] | S
Ballylumford | NIBGT2 | 58 | [29 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [35 empty] | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Kilroot | NIK2 | 258 | 2023-10-01 | 2025-01-01 | S | 458
Kilroot | NIK1 | 256 | 2023-10-01 | 2025-01-01 | S | 458
Ballylumford | NIB32 | 249 | 2024-04-02 | 2024-04-05 | S | 3
Kilroot | NIKGT4 | 42 | 2024-04-05 | 2024-04-08 | S | 3
Coolkeeragh | NIC30 | 408 | 2024-04-06 | 2024-04-08 | S | 2
Ballylumford | NIB31 | 249 | 2024-04-08 | 2024-04-11 00:30 | S | 3
Ballylumford | NIB10 | 94 | 2024-04-09 20:00 | 2024-04-10 08:00 | S | 0.5
Ballylumford | NIB10 | 94 | 2024-04-12 | 2024-07-12 | S | 91
Coolkeeragh | NICGT8 | 53 | 2024-05-13 | 2024-05-23 | S | 10
Coolkeeragh | NIC30 | 408 | 2024-06-01 | 2024-06-03 | S | 2
Moyle | MOYLE | 450 | 2024-06-03 | 2024-06-09 | 250 | 6
Moyle | MOYLE | 450 | 2024-06-09 | 2024-06-15 | 250 | 6
Ballylumford | NIBGT2 | 58 | 2024-07-22 | 2024-10-21 | S | 91
Ballylumford | NIB31 | 249 | 2024-08-13 | 2024-08-20 | S | 7
Ballylumford | NIB32 | 249 | 2024-08-13 | 2024-08-20 | 161 | 7
Ballylumford | NIB31 | 249 | 2024-08-20 | 2024-08-28 | 161 | 8
Ballylumford | NIB32 | 249 | 2024-08-20 | 2024-08-24 | S | 4
Ballylumford | NIB32 | 249 | 2024-08-24 | 2024-08-28 | 161 | 4
Coolkeeragh | NIC30 | 408 | 2024-09-02 | 2024-09-30 | S | 28
Ballylumford | NIBGT1 | 58 | 2024-10-15 | 2024-10-21 | S | 6
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2024 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2024 |  |  |  |  | Feb '2024 |  |  |  | Mar '2024 |  |  |  | Apr '2024 |  |  |  |  | May '2024 |  |  |  | Jun '2024 |  |  |  | Jul '2024 |  |  |  |  | Aug '2024 |  |  |  | Sep '2024 |  |  |  |  | Oct '2024 |  |  |  | Nov '2024 |  |  |  | Dec '2024
|  | Week | 1 '2024 | 2 '2024 | 3 '2024 | 4 '2024 | 5 '2024 | 6 '2024 | 7 '2024 | 8 '2024 | 9 '2024 | 10 '2024 | 11 '2024 | 12 '2024 | 13 '2024 | 14 '2024 | 15 '2024 | 16 '2024 | 17 '2024 | 18 '2024 | 19 '2024 | 20 '2024 | 21 '2024 | 22 '2024 | 23 '2024 | 24 '2024 | 25 '2024 | 26 '2024 | 27 '2024 | 28 '2024 | 29 '2024 | 30 '2024 | 31 '2024 | 32 '2024 | 33 '2024 | 34 '2024 | 35 '2024 | 36 '2024 | 37 '2024 | 38 '2024 | 39 '2024 | 40 '2024 | 41 '2024 | 42 '2024 | 43 '2024 | 44 '2024 | 45 '2024 | 46 '2024 | 47 '2024 | 48 '2024 | 49 '2024 | 50 '2024 | 51 '2024 | 52 '2024 | 53 '2024
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Aghada | AD2 | 449
Aghada | AD3 | 19 | [13 empty] | S
Aghada | AT1 | 90 | [13 empty] | S | S | S | S | [35 empty] | S
Aghada | AT2 | 90 | [15 empty] | S | S | [18 empty] | S
Aghada | AT4 | 90 | [17 empty] | S | S | [17 empty] | S
Ardnacrusha | AA1 | 21 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA2 | 22 | [23 empty] | S
Ardnacrusha | AA3 | 19 | [36 empty] | S
Ardnacrusha | AA4 | 24 | [18 empty] | S | S | S
Ballylumford | NIB10 | 94 | [15 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Ballylumford | NIB31 | 249 | [32 empty] | S
Ballylumford | NIB32 | 249 | [33 empty] | S
Ballylumford | NIBGT1 | 58 | [41 empty] | S
Ballylumford | NIBGT2 | 58 | [29 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Banoge | OD1 | 9
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [35 empty] | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17 | [15 empty] | S | S
Dublin Bay | DB1 | 415 | [14 empty] | S | S | S
Edenderry | ED1 | 118 | [26 empty] | S | S | S | S | S | S | S | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 17
Empower | NIEMP | 3
Endeco Technologies | EC1 | 52
Endeco Technologies | EC2 | 12
Endeco Technologies | EC3 | 5
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 21
Endeco Technologies | NIECA | 13
Enel X | AE1 | 87
Enel X | AE2 | 13
Enel X | AE3 | 14
Enel X | AE4 | 16
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 6
Enel X | EN6 | 11
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [14 empty] | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 23 | [23 empty] | S
Erne | ER4 | 23 | [31 empty] | S | S | S | S | S | S | S | S
EWIC | EW1 | 500 | [15 empty] | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464 | [20 empty] | S | S | S
Huntstown | HN2 | 402 | [40 empty] | S | S | S
Huntstown | HNC | 342 | [17 empty] | S | S | S
Inchicore | IH1 | 30 | [14 empty] | S
iPower | NIAGU | 74
Kilroot | NIK1 | 256 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIK2 | 258 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [19 empty] | S | S
Lee | LE2 | 4 | [11 empty] | S | S
Lee | LE3 | 8 | [14 empty] | S | S
Liffey | LI1 | 15 | [18 empty] | S | S | S | S | S | S | S | S
Liffey | LI2 | 15 | [18 empty] | S | S | S | S | S | S | S | S
Liffey | LI4 | 4 | [22 empty] | S | S | S | S
Liffey | LI5 | 4 | [27 empty] | S
Lisahally | NILPS | 18
Lisdrum | LF1 | 60
Moneypoint | MP1 | 285 | [19 empty] | S | S
Moneypoint | MP2 | 285 | [20 empty] | S | S
Moneypoint | MP3 | 285 | [35 empty] | S | S | S | S | S | S | S | S
Moneypoint | MP5 | 1
Moyle | MOYLE | 450
Poolbeg | PB4 | 148
Poolbeg | PB5 | 148 | [22 empty] | S | S
Poolbeg | PB6 | 168 | [37 empty] | S | S | S | S | S
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 83 | [29 empty] | S
Seal Rock | SK4 | 83 | [15 empty] | S | S | S | S | S | S | S | S | S | S | S | S
Tarbert | TB1 | 54 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tarbert | TB2 | 54 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tarbert | TB3 | 241 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tarbert | TB4 | 241 | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52 | [26 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Tawnaghmore | TP3 | 52 | [26 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [9 empty] | S | S
Turlough Hill | TH2 | 73 | [9 empty] | S | S
Turlough Hill | TH3 | 73 | [9 empty] | S | S
Turlough Hill | TH4 | 73 | [9 empty] | S | S
Tynagh | TYC | 404 | [25 empty] | S | S | S | S | S | S | S | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 5
Veolia Alternative Energy | DP2 | 30
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 65
VIOTAS | EE2 | 30
VIOTAS | EE3 | 11
VIOTAS | EE4 | 13
VIOTAS | EE5 | 17
VIOTAS | EE6 | 14
VIOTAS | EE7 | 7
VIOTAS | EE8 | 12
VIOTAS | EE9 | 11
Whitebank | DW1 | 62 | [14 empty] | S
Whitegate | WG1 | 444

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Kilroot | NIK2 | 258 | 2023-10-01 | 2025-01-01 | S | 458
Kilroot | NIK1 | 256 | 2023-10-01 | 2025-01-01 | S | 458
Edenderry | ED1 | 118 | 2023-12-26 12:00 | 2024-01-02 08:00 | S | 6.83
Tarbert | TB1 | 54 | 2024-01-01 | 2025-01-01 | S | 366
Tarbert | TB2 | 54 | 2024-01-01 | 2025-01-01 | S | 366
Tarbert | TB3 | 241 | 2024-01-01 | 2025-01-01 | S | 366
Tarbert | TB4 | 241 | 2024-01-01 | 2025-01-01 | S | 366
Moneypoint | MP1 | 285 | 2024-01-01 | 2024-05-10 22:00 | 260 | 130.92
Moneypoint | MP2 | 285 | 2024-01-01 | 2024-05-17 22:00 | 235 | 137.92
Moneypoint | MP3 | 285 | 2024-01-01 | 2024-08-30 22:00 | 260 | 242.92
Edenderry | ED1 | 118 | 2024-01-02 08:00 | 2024-03-28 17:00 | 95 | 86.33
Turlough Hill | TH2 | 73 | 2024-03-03 06:00 | 2024-03-15 18:00 | S | 12.5
Turlough Hill | TH3 | 73 | 2024-03-03 06:00 | 2024-03-15 18:00 | S | 12.5
Turlough Hill | TH4 | 73 | 2024-03-03 06:00 | 2024-03-15 18:00 | S | 12.5
Turlough Hill | TH1 | 73 | 2024-03-03 06:00 | 2024-03-15 18:00 | S | 12.5
Aghada | AD2 | 449 | 2024-03-15 | 2024-03-22 23:00 | S | 7.92
Lee | LE2 | 4 | 2024-03-19 08:00 | 2024-03-29 20:00 | S | 10.5
Seal Rock | SK3 | 83 | 2024-03-25 06:00 | 2024-03-27 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2024-03-28 17:00 | 2024-04-03 08:00 | S | 5.58
Whitebank | DW1 | 61.5 | 2024-04-01 | 2024-04-07 | 26 | 6
Aghada | AT1 | 90 | 2024-04-01 | 2024-04-30 | S | 29
Moneypoint | MP5 | 1 | 2024-04-01 07:00 | 2024-04-03 19:00 | S | 2.5
Aghada | AD3 | 19 | 2024-04-01 07:00 | 2024-04-06 19:00 | S | 5.5
Ballylumford | NIB32 | 249 | 2024-04-02 | 2024-04-05 | S | 3
Edenderry | ED1 | 118 | 2024-04-03 08:00 | 2024-06-28 12:00 | 95 | 86.17
Kilroot | NIKGT4 | 42 | 2024-04-05 | 2024-04-08 | S | 3
Dublin Bay | DB1 | 415 | 2024-04-05 12:00 | 2024-04-29 18:00 | S | 24.25
Whitebank | DW1 | 61.5 | 2024-04-06 | 2024-04-17 | S | 11
Coolkeeragh | NIC30 | 408 | 2024-04-06 | 2024-04-08 | S | 2
Ballylumford | NIB31 | 249 | 2024-04-08 | 2024-04-11 00:30 | S | 3
Inchicore | IH1 | 30 | 2024-04-08 07:00 | 2024-04-13 19:00 | S | 5.5
Lee | LE3 | 8 | 2024-04-08 08:00 | 2024-04-19 20:00 | S | 11.5
Ardnacrusha | AA1 | 21 | 2024-04-08 08:00 | 2024-09-13 18:00 | S | 158.42
Erne | ER1 | 10 | 2024-04-08 08:00 | 2024-04-12 20:00 | S | 4.5
Ballylumford | NIB10 | 94 | 2024-04-09 20:00 | 2024-04-10 08:00 | S | 0.5
Ballylumford | NIB10 | 94 | 2024-04-12 | 2024-07-12 | S | 91
Drybridge | IW1 | 17 | 2024-04-14 | 2024-05-01 | S | 17
Aghada | AT2 | 90 | 2024-04-15 | 2024-04-30 | S | 15
Seal Rock | SK4 | 83 | 2024-04-15 06:00 | 2024-07-09 18:00 | S | 85.5
EWIC | EW1 | 500 | 2024-04-15 09:00 | 2024-04-15 21:00 | S | 0.5
EWIC | EW1 | 500 | 2024-04-15 21:00 | 2024-04-19 23:00 | S | 4.08
Whitebank | DW1 | 61.5 | 2024-04-16 | 2024-04-22 | 26 | 6
Aghada | AT4 | 90 | 2024-04-26 | 2024-05-10 | S | 14
Huntstown | HNC | 342 | 2024-04-26 21:00 | 2024-05-16 21:00 | S | 20
Liffey | LI1 | 15 | 2024-05-07 08:00 | 2024-06-28 20:00 | S | 52.5
Ardnacrusha | AA4 | 24 | 2024-05-07 08:00 | 2024-05-24 20:00 | S | 17.5
Liffey | LI2 | 15 | 2024-05-07 08:00 | 2024-06-28 20:00 | S | 52.5
Moneypoint | MP1 | 285 | 2024-05-10 22:00 | 2024-05-26 22:00 | S | 16
Coolkeeragh | NICGT8 | 53 | 2024-05-13 | 2024-05-23 | S | 10
Erne | ER2 | 10 | 2024-05-13 08:00 | 2024-05-17 20:00 | S | 4.5
Lee | LE1 | 15 | 2024-05-13 08:00 | 2024-05-24 20:00 | S | 11.5
Seal Rock | SK4 | 83 | 2024-05-13 18:00 | 2024-05-16 18:00 | S | 3
Seal Rock | SK3 | 83 | 2024-05-14 | 2024-05-16 12:00 | S | 2.5
Great Island | GI4 | 464 | 2024-05-17 | 2024-06-10 | S | 24
Moneypoint | MP2 | 285 | 2024-05-17 22:00 | 2024-06-02 22:00 | S | 16
Rhode | RP1 | 52 | 2024-05-25 08:00 | 2024-05-31 16:00 | S | 6.33
Rhode | RP2 | 52 | 2024-05-25 08:00 | 2024-05-31 16:00 | S | 6.33
Moneypoint | MP1 | 285 | 2024-05-26 22:00 | 2025-01-01 | 260 | 219.08
Coolkeeragh | NIC30 | 408 | 2024-06-01 | 2024-06-03 | S | 2
Poolbeg | PB5 | 148 | 2024-06-02 | 2024-06-15 20:00 | S | 13.83
Poolbeg | PB6 | 168 | 2024-06-02 | 2024-06-15 20:00 | 84 | 13.83
Moneypoint | MP2 | 285 | 2024-06-02 22:00 | 2025-01-01 | 235 | 212.08
Moyle | MOYLE | 450 | 2024-06-03 | 2024-06-09 | 250 | 6
Liffey | LI4 | 4 | 2024-06-06 08:00 | 2024-06-28 20:00 | S | 22.5
Moyle | MOYLE | 450 | 2024-06-09 | 2024-06-15 | 250 | 6
Erne | ER3 | 23 | 2024-06-10 08:00 | 2024-06-14 20:00 | S | 4.5
Ardnacrusha | AA2 | 22 | 2024-06-10 08:00 | 2024-06-14 20:00 | S | 4.5
Tynagh | TYC | 404 | 2024-06-21 20:00 | 2024-08-15 20:00 | S | 55
Edenderry | ED1 | 118 | 2024-06-28 12:00 | 2024-09-02 08:00 | S | 65.83
Tawnaghmore | TP1 | 52 | 2024-06-29 09:00 | 2024-09-28 17:00 | S | 91.33
Tawnaghmore | TP3 | 52 | 2024-06-29 09:00 | 2024-09-28 17:00 | S | 91.33
Cloniffeen | SI1 | 50 | 2024-07-08 08:00 | 2024-07-09 17:00 | S | 1.33
Liffey | LI5 | 4 | 2024-07-08 08:00 | 2024-07-13 20:00 | S | 5.5
Cloniffeen | SI2 | 50 | 2024-07-08 08:00 | 2024-07-09 17:00 | S | 1.33
Ballylumford | NIBGT2 | 58 | 2024-07-22 | 2024-10-21 | S | 91
Seal Rock | SK3 | 83 | 2024-07-22 06:00 | 2024-07-26 18:00 | S | 4.5
Derrycarney | LU1 | 50 | 2024-07-22 08:00 | 2024-07-23 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2024-07-22 08:00 | 2024-07-23 17:00 | S | 1.33
Erne | ER4 | 23 | 2024-08-06 08:00 | 2024-09-27 20:00 | S | 52.5
Ballylumford | NIB31 | 249 | 2024-08-13 | 2024-08-20 | S | 7
Ballylumford | NIB32 | 249 | 2024-08-13 | 2024-08-20 | 161 | 7
Ballylumford | NIB31 | 249 | 2024-08-20 | 2024-08-28 | 161 | 8
Ballylumford | NIB32 | 249 | 2024-08-20 | 2024-08-24 | S | 4
Whitegate | WG1 | 444 | 2024-08-23 21:00 | 2024-08-30 21:00 | S | 7
Ballylumford | NIB32 | 249 | 2024-08-24 | 2024-08-28 | 161 | 4
Moneypoint | MP3 | 285 | 2024-08-30 22:00 | 2024-10-25 22:00 | S | 56
Coolkeeragh | NIC30 | 408 | 2024-09-02 | 2024-09-30 | S | 28
Edenderry | ED1 | 118 | 2024-09-02 08:00 | 2024-12-26 12:00 | 95 | 115.17
Aghada | AT2 | 90 | 2024-09-04 | 2024-09-08 | S | 4
Edenderry | ED3 | 58 | 2024-09-06 08:00 | 2024-09-06 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2024-09-06 08:00 | 2024-09-06 18:00 | S | 0.42
Ardnacrusha | AA3 | 19 | 2024-09-09 08:00 | 2024-09-13 20:00 | S | 4.5
Aghada | AT4 | 90 | 2024-09-11 | 2024-09-15 | S | 4
Poolbeg | PB6 | 168 | 2024-09-16 | 2024-10-20 20:00 | S | 34.83
Aghada | AD2 | 449 | 2024-09-27 | 2024-10-02 23:00 | S | 5.92
Seal Rock | SK4 | 83 | 2024-09-30 06:00 | 2024-10-02 18:00 | S | 2.5
Huntstown | HN2 | 402 | 2024-10-04 21:00 | 2024-10-29 21:00 | S | 25
Whitebank | DW1 | 61.5 | 2024-10-07 | 2024-10-11 | 26 | 4
Aghada | AD3 | 19 | 2024-10-07 07:00 | 2024-10-10 19:00 | S | 3.5
Whitebank | DW1 | 61.5 | 2024-10-14 | 2024-10-18 | 26 | 4
Inchicore | IH1 | 30 | 2024-10-14 07:00 | 2024-10-17 19:00 | S | 3.5
Ballylumford | NIBGT1 | 58 | 2024-10-15 | 2024-10-21 | S | 6
Moneypoint | MP3 | 285 | 2024-10-25 22:00 | 2025-01-01 | 260 | 67.08
Seal Rock | SK3 | 83 | 2024-11-11 06:00 | 2024-11-13 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2024-12-26 12:00 | 2025-01-01 08:00 | S | 5.83
Tarbert | TB1 | 54 | 2025-01-01 | 2026-01-01 | S | 365
Tarbert | TB2 | 54 | 2025-01-01 | 2026-01-01 | S | 365
Tarbert | TB3 | 241 | 2025-01-01 | 2026-01-01 | S | 365
Tarbert | TB4 | 241 | 2025-01-01 | 2026-01-01 | S | 365
Aghada | AT1 | 90 | 2025-01-01 | 2026-01-01 | S | 365
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10