## Outage Plan EirGrid
2026 GENERATION OUTAGE PLAN (EIRGRID)
|  | Month | Jan '2026 |  |  |  |  | Feb '2026 |  |  |  | Mar '2026 |  |  |  |  | Apr '2026 |  |  |  | May '2026 |  |  |  | Jun '2026 |  |  |  |  | Jul '2026 |  |  |  | Aug '2026 |  |  |  |  | Sep '2026 |  |  |  | Oct '2026 |  |  |  | Nov '2026 |  |  |  |  | Dec '2026
|  | Week | 1 '2026 | 2 '2026 | 3 '2026 | 4 '2026 | 5 '2026 | 6 '2026 | 7 '2026 | 8 '2026 | 9 '2026 | 10 '2026 | 11 '2026 | 12 '2026 | 13 '2026 | 14 '2026 | 15 '2026 | 16 '2026 | 17 '2026 | 18 '2026 | 19 '2026 | 20 '2026 | 21 '2026 | 22 '2026 | 23 '2026 | 24 '2026 | 25 '2026 | 26 '2026 | 27 '2026 | 28 '2026 | 29 '2026 | 30 '2026 | 31 '2026 | 32 '2026 | 33 '2026 | 34 '2026 | 35 '2026 | 36 '2026 | 37 '2026 | 38 '2026 | 39 '2026 | 40 '2026 | 41 '2026 | 42 '2026 | 43 '2026 | 44 '2026 | 45 '2026 | 46 '2026 | 47 '2026 | 48 '2026 | 49 '2026 | 50 '2026 | 51 '2026 | 52 '2026 | 53 '2026
Station | Unit | NPR
Aghada | AD2 | 449 | [10 empty] | S | [31 empty] | S
Aghada | AD3 | 19 | [13 empty] | S | [26 empty] | S
Aghada | AT1 | 90
Aghada | AT2 | 90 | [20 empty] | S
Aghada | AT4 | 90 | [19 empty] | S
Ardnacrusha | AA1 | 21 | [19 empty] | S
Ardnacrusha | AA2 | 22 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA3 | 19 | [21 empty] | S
Ardnacrusha | AA4 | 24 | [23 empty] | S
Banoge | OD1 | 9
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17 | [15 empty] | S | S | S
Dublin Bay | DB1 | 415
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 17
Endeco Technologies | EC1 | 52
Endeco Technologies | EC2 | 12
Endeco Technologies | EC3 | 5
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 21
Enel X | AE1 | 87
Enel X | AE2 | 13
Enel X | AE3 | 14
Enel X | AE4 | 16
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 6
Enel X | EN6 | 11
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [15 empty] | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 23 | [23 empty] | S
Erne | ER4 | 23 | [36 empty] | S
EWIC | EW1 | 500 | [15 empty] | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464 | [23 empty] | S
Huntstown | HN2 | 402 | [22 empty] | S | S | S
Huntstown | HNC | 342 | [18 empty] | S | S | S
Inchicore | IH1 | 30 | [14 empty] | S | [26 empty] | S
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [16 empty] | S | S | S | S
Lee | LE2 | 4 | [12 empty] | S | S
Lee | LE3 | 8 | [23 empty] | S | S
Liffey | LI1 | 15 | [23 empty] | S | S
Liffey | LI2 | 15 | [23 empty] | S | S
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisdrum | LF1 | 60
Moneypoint | MP1 | 285 | [19 empty] | S | S
Moneypoint | MP2 | 285 | [20 empty] | S | S
Moneypoint | MP3 | 285 | [38 empty] | S | S
Moneypoint | MP5 | 1
Poolbeg | PB4 | 148 | [35 empty] | S | S | S | S | S | S
Poolbeg | PB5 | 148 | [19 empty] | S
Poolbeg | PB6 | 168
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 83 | [17 empty] | S
Seal Rock | SK4 | 83 | [28 empty] | S
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [9 empty] | S | S
Turlough Hill | TH2 | 73 | [9 empty] | S | S
Turlough Hill | TH3 | 73 | [9 empty] | S | S
Turlough Hill | TH4 | 73 | [9 empty] | S | S
Tynagh | TYC | 404 | [39 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 5
Veolia Alternative Energy | DP2 | 30
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 65
VIOTAS | EE2 | 30
VIOTAS | EE3 | 11
VIOTAS | EE4 | 13
VIOTAS | EE5 | 17
VIOTAS | EE6 | 14
VIOTAS | EE7 | 7
VIOTAS | EE8 | 12
VIOTAS | EE9 | 11
Whitebank | DW1 | 62 | [15 empty] | S
Whitegate | WG1 | 444 | [36 empty] | S | S | S | S | S | S | S | S

## EirGrid Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2025-12-26 12:00 | 2026-01-01 08:00 | S | 5.83
Seal Rock | SK3 | 83 | 2026-01-12 06:00 | 2026-01-14 18:00 | S | 2.5
Turlough Hill | TH1 | 73 | 2026-03-01 06:00 | 2026-03-13 18:00 | S | 12.5
Turlough Hill | TH2 | 73 | 2026-03-01 06:00 | 2026-03-13 18:00 | S | 12.5
Turlough Hill | TH3 | 73 | 2026-03-01 06:00 | 2026-03-13 18:00 | S | 12.5
Turlough Hill | TH4 | 73 | 2026-03-01 06:00 | 2026-03-13 18:00 | S | 12.5
Aghada | AD2 | 449 | 2026-03-09 | 2026-03-14 23:00 | S | 5.92
Seal Rock | SK4 | 83 | 2026-03-09 06:00 | 2026-03-11 18:00 | S | 2.5
Lee | LE2 | 4 | 2026-03-23 08:00 | 2026-04-03 20:00 | S | 11.5
Moneypoint | MP5 | 1 | 2026-04-01 | 2026-04-04 | S | 3
Aghada | AD3 | 19 | 2026-04-01 | 2026-04-07 | S | 6
Whitebank | DW1 | 61.5 | 2026-04-06 | 2026-04-12 | 26 | 6
Ardnacrusha | AA2 | 22 | 2026-04-07 08:00 | 2026-09-15 20:00 | S | 161.5
Inchicore | IH1 | 30 | 2026-04-08 | 2026-04-14 | S | 6
Edenderry | ED1 | 118 | 2026-04-09 17:00 | 2026-04-15 08:00 | S | 5.58
Whitebank | DW1 | 61.5 | 2026-04-11 | 2026-04-22 | S | 11
Erne | ER1 | 10 | 2026-04-13 08:00 | 2026-04-17 20:00 | S | 4.5
EWIC | EW1 | 500 | 2026-04-13 09:00 | 2026-04-13 21:00 | S | 0.5
EWIC | EW1 | 500 | 2026-04-13 21:00 | 2026-04-19 23:00 | S | 6.08
Drybridge | IW1 | 17 | 2026-04-14 | 2026-05-01 | S | 17
Lee | LE1 | 15 | 2026-04-20 08:00 | 2026-05-15 20:00 | S | 25.5
Whitebank | DW1 | 61.5 | 2026-04-21 | 2026-04-27 | 26 | 6
Seal Rock | SK3 | 83 | 2026-04-27 06:00 | 2026-05-01 18:00 | S | 4.5
Huntstown | HNC | 342 | 2026-05-01 21:00 | 2026-05-21 21:00 | S | 20
Moneypoint | MP1 | 285 | 2026-05-08 22:00 | 2026-05-24 22:00 | S | 16
Poolbeg | PB6 | 168 | 2026-05-10 | 2026-05-16 20:00 | 84 | 6.83
Poolbeg | PB5 | 148 | 2026-05-10 08:00 | 2026-05-16 20:00 | S | 6.5
Erne | ER2 | 10 | 2026-05-11 08:00 | 2026-05-15 20:00 | S | 4.5
Ardnacrusha | AA1 | 21 | 2026-05-11 08:00 | 2026-05-15 20:00 | S | 4.5
Seal Rock | SK3 | 83 | 2026-05-11 18:00 | 2026-05-14 18:00 | S | 3
Seal Rock | SK4 | 83 | 2026-05-12 | 2026-05-14 12:00 | S | 2.5
Aghada | AT4 | 90 | 2026-05-13 | 2026-05-17 | S | 4
Moneypoint | MP2 | 285 | 2026-05-15 22:00 | 2026-05-31 22:00 | S | 16
Aghada | AT2 | 90 | 2026-05-18 | 2026-05-25 | S | 7
Ardnacrusha | AA3 | 19 | 2026-05-25 08:00 | 2026-05-29 20:00 | S | 4.5
Huntstown | HN2 | 402 | 2026-06-01 21:00 | 2026-06-21 21:00 | S | 20
Liffey | LI1 | 15 | 2026-06-07 08:00 | 2026-06-20 20:00 | S | 13.5
Liffey | LI2 | 15 | 2026-06-07 08:00 | 2026-06-20 20:00 | S | 13.5
Great Island | GI4 | 464 | 2026-06-08 | 2026-06-16 | S | 8
Erne | ER3 | 23 | 2026-06-08 08:00 | 2026-06-12 20:00 | S | 4.5
Ardnacrusha | AA4 | 24 | 2026-06-08 08:00 | 2026-06-12 20:00 | S | 4.5
Lee | LE3 | 8 | 2026-06-08 08:00 | 2026-06-19 20:00 | S | 11.5
Dublin Bay | DB1 | 415 | 2026-06-26 08:00 | 2026-06-30 20:00 | S | 4.5
Edenderry | ED1 | 118 | 2026-07-03 12:00 | 2026-08-04 08:00 | S | 31.83
Seal Rock | SK4 | 83 | 2026-07-13 06:00 | 2026-07-17 18:00 | S | 4.5
Cloniffeen | SI1 | 50 | 2026-07-13 08:00 | 2026-07-13 17:00 | S | 0.33
Cloniffeen | SI2 | 50 | 2026-07-13 08:00 | 2026-07-13 17:00 | S | 0.33
Derrycarney | LU1 | 50 | 2026-07-27 08:00 | 2026-07-28 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2026-07-27 08:00 | 2026-07-28 17:00 | S | 1.33
Poolbeg | PB6 | 168 | 2026-08-30 | 2026-10-10 20:00 | 84 | 41.83
Poolbeg | PB4 | 148 | 2026-08-30 08:00 | 2026-10-10 20:00 | S | 41.5
Whitegate | WG1 | 444 | 2026-09-04 21:00 | 2026-11-02 21:00 | S | 59
Seal Rock | SK3 | 83 | 2026-09-07 06:00 | 2026-09-09 18:00 | S | 2.5
Erne | ER4 | 23 | 2026-09-07 08:00 | 2026-09-11 20:00 | S | 4.5
Edenderry | ED3 | 58 | 2026-09-11 08:00 | 2026-09-11 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2026-09-11 08:00 | 2026-09-11 18:00 | S | 0.42
Moneypoint | MP3 | 285 | 2026-09-18 22:00 | 2026-10-04 22:00 | S | 16
Tynagh | TYC | 404 | 2026-09-28 20:00 | 2026-10-03 20:00 | S | 5
Whitebank | DW1 | 61.5 | 2026-10-05 | 2026-10-09 | 26 | 4
Aghada | AD3 | 19 | 2026-10-07 | 2026-10-11 | S | 4
Whitebank | DW1 | 61.5 | 2026-10-12 | 2026-10-16 | 26 | 4
Inchicore | IH1 | 30 | 2026-10-14 | 2026-10-18 | S | 4
Aghada | AD2 | 449 | 2026-10-19 | 2026-10-24 23:00 | S | 5.92
Seal Rock | SK4 | 83 | 2026-11-16 06:00 | 2026-11-18 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2026-12-26 12:00 | 2027-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan SONI
2026 GENERATION OUTAGE PLAN (SONI)
|  | Month | Jan '2026 |  |  |  |  | Feb '2026 |  |  |  | Mar '2026 |  |  |  |  | Apr '2026 |  |  |  | May '2026 |  |  |  | Jun '2026 |  |  |  |  | Jul '2026 |  |  |  | Aug '2026 |  |  |  |  | Sep '2026 |  |  |  | Oct '2026 |  |  |  | Nov '2026 |  |  |  |  | Dec '2026
|  | Week | 1 '2026 | 2 '2026 | 3 '2026 | 4 '2026 | 5 '2026 | 6 '2026 | 7 '2026 | 8 '2026 | 9 '2026 | 10 '2026 | 11 '2026 | 12 '2026 | 13 '2026 | 14 '2026 | 15 '2026 | 16 '2026 | 17 '2026 | 18 '2026 | 19 '2026 | 20 '2026 | 21 '2026 | 22 '2026 | 23 '2026 | 24 '2026 | 25 '2026 | 26 '2026 | 27 '2026 | 28 '2026 | 29 '2026 | 30 '2026 | 31 '2026 | 32 '2026 | 33 '2026 | 34 '2026 | 35 '2026 | 36 '2026 | 37 '2026 | 38 '2026 | 39 '2026 | 40 '2026 | 41 '2026 | 42 '2026 | 43 '2026 | 44 '2026 | 45 '2026 | 46 '2026 | 47 '2026 | 48 '2026 | 49 '2026 | 50 '2026 | 51 '2026 | 52 '2026 | 53 '2026
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [24 empty] | S
Ballylumford | NIBGT2 | 58
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [33 empty] | S | S | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
Empower | NIEMP | 3
Endeco Technologies | NIECA | 13
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42 | [21 empty] | S
Lisahally | NILPS | 18
Moyle | MOYLE | 450
Powerhouse Generation | NIPH1 | 34

## SONI Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Coolkeeragh | NIC30 | 408 | 2026-03-07 | 2026-03-08 | S | 1
Coolkeeragh | NICGT8 | 53 | 2026-05-11 | 2026-05-15 | S | 4
Coolkeeragh | NIC30 | 408 | 2026-05-23 | 2026-05-25 | S | 2
Kilroot | NIKGT4 | 42 | 2026-05-25 | 2026-05-29 | S | 4
Ballylumford | NIBGT1 | 58 | 2026-06-15 | 2026-06-22 | S | 7
Coolkeeragh | NIC30 | 408 | 2026-07-25 | 2026-07-26 | S | 1
Coolkeeragh | NIC30 | 408 | 2026-08-17 | 2026-09-30 | S | 44
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10

## Outage Plan All Island
2026 GENERATION OUTAGE PLAN (All Island)
|  | Month | Jan '2026 |  |  |  |  | Feb '2026 |  |  |  | Mar '2026 |  |  |  |  | Apr '2026 |  |  |  | May '2026 |  |  |  | Jun '2026 |  |  |  |  | Jul '2026 |  |  |  | Aug '2026 |  |  |  |  | Sep '2026 |  |  |  | Oct '2026 |  |  |  | Nov '2026 |  |  |  |  | Dec '2026
|  | Week | 1 '2026 | 2 '2026 | 3 '2026 | 4 '2026 | 5 '2026 | 6 '2026 | 7 '2026 | 8 '2026 | 9 '2026 | 10 '2026 | 11 '2026 | 12 '2026 | 13 '2026 | 14 '2026 | 15 '2026 | 16 '2026 | 17 '2026 | 18 '2026 | 19 '2026 | 20 '2026 | 21 '2026 | 22 '2026 | 23 '2026 | 24 '2026 | 25 '2026 | 26 '2026 | 27 '2026 | 28 '2026 | 29 '2026 | 30 '2026 | 31 '2026 | 32 '2026 | 33 '2026 | 34 '2026 | 35 '2026 | 36 '2026 | 37 '2026 | 38 '2026 | 39 '2026 | 40 '2026 | 41 '2026 | 42 '2026 | 43 '2026 | 44 '2026 | 45 '2026 | 46 '2026 | 47 '2026 | 48 '2026 | 49 '2026 | 50 '2026 | 51 '2026 | 52 '2026 | 53 '2026
Station | Unit | NPR
AC Automation | NIACA | 8
Activation Energy | NIAEA | 9
Aghada | AD2 | 449 | [10 empty] | S | [31 empty] | S
Aghada | AD3 | 19 | [13 empty] | S | [26 empty] | S
Aghada | AT1 | 90
Aghada | AT2 | 90 | [20 empty] | S
Aghada | AT4 | 90 | [19 empty] | S
Ardnacrusha | AA1 | 21 | [19 empty] | S
Ardnacrusha | AA2 | 22 | [14 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S
Ardnacrusha | AA3 | 19 | [21 empty] | S
Ardnacrusha | AA4 | 24 | [23 empty] | S
Ballylumford | NIB10 | 94
Ballylumford | NIB31 | 249
Ballylumford | NIB32 | 249
Ballylumford | NIBGT1 | 58 | [24 empty] | S
Ballylumford | NIBGT2 | 58
Banoge | OD1 | 9
Cloniffeen | SI1 | 50
Cloniffeen | SI2 | 50
Contour Global | NICG2 | 3
Contour Global | NICGA | 12
Coolkeeragh | NIC30 | 408 | [33 empty] | S | S | S | S | S | S
Coolkeeragh | NICGT8 | 53 | [19 empty] | S
Coolnanoonagh | KZ3 | 2
Coolnanoonagh | KZ4 | 27
Crane | AV1 | 16
Derrycarney | LU1 | 50
Derrycarney | LU2 | 50
Drybridge | IW1 | 17 | [15 empty] | S | S | S
Dublin Bay | DB1 | 415
Edenderry | ED1 | 118 | [27 empty] | S | S | S | S
Edenderry | ED3 | 58
Edenderry | ED5 | 58
Electric Ireland | EI1 | 17
Empower | NIEMP | 3
Endeco Technologies | EC1 | 52
Endeco Technologies | EC2 | 12
Endeco Technologies | EC3 | 5
Endeco Technologies | EC4 | 5
Endeco Technologies | EC5 | 21
Endeco Technologies | NIECA | 13
Enel X | AE1 | 87
Enel X | AE2 | 13
Enel X | AE3 | 14
Enel X | AE4 | 16
Enel X | AE5 | 16
Enel X | EN1 | 16
Enel X | EN2 | 17
Enel X | EN3 | 17
Enel X | EN4 | 16
Enel X | EN5 | 6
Enel X | EN6 | 11
Enel X | EN8 | 24
Enel X | EN9 | 16
Enel X | EX1 | 21
Energy Trading | NIETB | 9
Energy Trading | NIETD | 5
Energy Trading | NIETR | 19
Energy Trading Ireland | ET1 | 5
Erne | ER1 | 10 | [15 empty] | S
Erne | ER2 | 10 | [19 empty] | S
Erne | ER3 | 23 | [23 empty] | S
Erne | ER4 | 23 | [36 empty] | S
EWIC | EW1 | 500 | [15 empty] | S
Gardnershill | GP1 | 8
Golagh | GO2 | 3
Gorman | GF1 | 50
Great Island | GI4 | 464 | [23 empty] | S
Huntstown | HN2 | 402 | [22 empty] | S | S | S
Huntstown | HNC | 342 | [18 empty] | S | S | S
Inchicore | IH1 | 30 | [14 empty] | S | [26 empty] | S
iPower | NIAGU | 74
Kilroot | NIK1 | 256
Kilroot | NIK2 | 258
Kilroot | NIKGT1 | 29
Kilroot | NIKGT2 | 29
Kilroot | NIKGT3 | 42
Kilroot | NIKGT4 | 42 | [21 empty] | S
Kilteel | PN1 | 30
Knockacummer | KC1 | 100
Lee | LE1 | 15 | [16 empty] | S | S | S | S
Lee | LE2 | 4 | [12 empty] | S | S
Lee | LE3 | 8 | [23 empty] | S | S
Liffey | LI1 | 15 | [23 empty] | S | S
Liffey | LI2 | 15 | [23 empty] | S | S
Liffey | LI4 | 4
Liffey | LI5 | 4
Lisahally | NILPS | 18
Lisdrum | LF1 | 60
Moneypoint | MP1 | 285 | [19 empty] | S | S
Moneypoint | MP2 | 285 | [20 empty] | S | S
Moneypoint | MP3 | 285 | [38 empty] | S | S
Moneypoint | MP5 | 1
Moyle | MOYLE | 450
Poolbeg | PB4 | 148 | [35 empty] | S | S | S | S | S | S
Poolbeg | PB5 | 148 | [19 empty] | S
Poolbeg | PB6 | 168
Powerhouse Generation | NIPH1 | 34
Powerhouse Generation | PG1 | 10
Rhode | RP1 | 52
Rhode | RP2 | 52
Seal Rock | SK3 | 83 | [17 empty] | S
Seal Rock | SK4 | 83 | [28 empty] | S
Tawnaghmore | KF2 | 11
Tawnaghmore | TP1 | 52
Tawnaghmore | TP3 | 52
Tobertoreen | XT2 | 11
Turlough Hill | TH1 | 73 | [9 empty] | S | S
Turlough Hill | TH2 | 73 | [9 empty] | S | S
Turlough Hill | TH3 | 73 | [9 empty] | S | S
Turlough Hill | TH4 | 73 | [9 empty] | S | S
Tynagh | TYC | 404 | [39 empty] | S
Uggool | SO1 | 105
Veolia Alternative Energy | DP1 | 5
Veolia Alternative Energy | DP2 | 30
Veolia Alternative Energy | DP3 | 9
VIOTAS | EE1 | 65
VIOTAS | EE2 | 30
VIOTAS | EE3 | 11
VIOTAS | EE4 | 13
VIOTAS | EE5 | 17
VIOTAS | EE6 | 14
VIOTAS | EE7 | 7
VIOTAS | EE8 | 12
VIOTAS | EE9 | 11
Whitebank | DW1 | 62 | [15 empty] | S
Whitegate | WG1 | 444 | [36 empty] | S | S | S | S | S | S | S | S

## All Island Outages
Upcoming Outages including STMOs and Annual Outages
Station | Unit | NPR | Start Date | End Date | Value | Duration
Edenderry | ED1 | 118 | 2025-12-26 12:00 | 2026-01-01 08:00 | S | 5.83
Seal Rock | SK3 | 83 | 2026-01-12 06:00 | 2026-01-14 18:00 | S | 2.5
Turlough Hill | TH1 | 73 | 2026-03-01 06:00 | 2026-03-13 18:00 | S | 12.5
Turlough Hill | TH2 | 73 | 2026-03-01 06:00 | 2026-03-13 18:00 | S | 12.5
Turlough Hill | TH3 | 73 | 2026-03-01 06:00 | 2026-03-13 18:00 | S | 12.5
Turlough Hill | TH4 | 73 | 2026-03-01 06:00 | 2026-03-13 18:00 | S | 12.5
Coolkeeragh | NIC30 | 408 | 2026-03-07 | 2026-03-08 | S | 1
Aghada | AD2 | 449 | 2026-03-09 | 2026-03-14 23:00 | S | 5.92
Seal Rock | SK4 | 83 | 2026-03-09 06:00 | 2026-03-11 18:00 | S | 2.5
Lee | LE2 | 4 | 2026-03-23 08:00 | 2026-04-03 20:00 | S | 11.5
Moneypoint | MP5 | 1 | 2026-04-01 | 2026-04-04 | S | 3
Aghada | AD3 | 19 | 2026-04-01 | 2026-04-07 | S | 6
Whitebank | DW1 | 61.5 | 2026-04-06 | 2026-04-12 | 26 | 6
Ardnacrusha | AA2 | 22 | 2026-04-07 08:00 | 2026-09-15 20:00 | S | 161.5
Inchicore | IH1 | 30 | 2026-04-08 | 2026-04-14 | S | 6
Edenderry | ED1 | 118 | 2026-04-09 17:00 | 2026-04-15 08:00 | S | 5.58
Whitebank | DW1 | 61.5 | 2026-04-11 | 2026-04-22 | S | 11
Erne | ER1 | 10 | 2026-04-13 08:00 | 2026-04-17 20:00 | S | 4.5
EWIC | EW1 | 500 | 2026-04-13 09:00 | 2026-04-13 21:00 | S | 0.5
EWIC | EW1 | 500 | 2026-04-13 21:00 | 2026-04-19 23:00 | S | 6.08
Drybridge | IW1 | 17 | 2026-04-14 | 2026-05-01 | S | 17
Lee | LE1 | 15 | 2026-04-20 08:00 | 2026-05-15 20:00 | S | 25.5
Whitebank | DW1 | 61.5 | 2026-04-21 | 2026-04-27 | 26 | 6
Seal Rock | SK3 | 83 | 2026-04-27 06:00 | 2026-05-01 18:00 | S | 4.5
Huntstown | HNC | 342 | 2026-05-01 21:00 | 2026-05-21 21:00 | S | 20
Moneypoint | MP1 | 285 | 2026-05-08 22:00 | 2026-05-24 22:00 | S | 16
Poolbeg | PB6 | 168 | 2026-05-10 | 2026-05-16 20:00 | 84 | 6.83
Poolbeg | PB5 | 148 | 2026-05-10 08:00 | 2026-05-16 20:00 | S | 6.5
Coolkeeragh | NICGT8 | 53 | 2026-05-11 | 2026-05-15 | S | 4
Erne | ER2 | 10 | 2026-05-11 08:00 | 2026-05-15 20:00 | S | 4.5
Ardnacrusha | AA1 | 21 | 2026-05-11 08:00 | 2026-05-15 20:00 | S | 4.5
Seal Rock | SK3 | 83 | 2026-05-11 18:00 | 2026-05-14 18:00 | S | 3
Seal Rock | SK4 | 83 | 2026-05-12 | 2026-05-14 12:00 | S | 2.5
Aghada | AT4 | 90 | 2026-05-13 | 2026-05-17 | S | 4
Moneypoint | MP2 | 285 | 2026-05-15 22:00 | 2026-05-31 22:00 | S | 16
Aghada | AT2 | 90 | 2026-05-18 | 2026-05-25 | S | 7
Coolkeeragh | NIC30 | 408 | 2026-05-23 | 2026-05-25 | S | 2
Kilroot | NIKGT4 | 42 | 2026-05-25 | 2026-05-29 | S | 4
Ardnacrusha | AA3 | 19 | 2026-05-25 08:00 | 2026-05-29 20:00 | S | 4.5
Huntstown | HN2 | 402 | 2026-06-01 21:00 | 2026-06-21 21:00 | S | 20
Liffey | LI1 | 15 | 2026-06-07 08:00 | 2026-06-20 20:00 | S | 13.5
Liffey | LI2 | 15 | 2026-06-07 08:00 | 2026-06-20 20:00 | S | 13.5
Great Island | GI4 | 464 | 2026-06-08 | 2026-06-16 | S | 8
Erne | ER3 | 23 | 2026-06-08 08:00 | 2026-06-12 20:00 | S | 4.5
Ardnacrusha | AA4 | 24 | 2026-06-08 08:00 | 2026-06-12 20:00 | S | 4.5
Lee | LE3 | 8 | 2026-06-08 08:00 | 2026-06-19 20:00 | S | 11.5
Ballylumford | NIBGT1 | 58 | 2026-06-15 | 2026-06-22 | S | 7
Dublin Bay | DB1 | 415 | 2026-06-26 08:00 | 2026-06-30 20:00 | S | 4.5
Edenderry | ED1 | 118 | 2026-07-03 12:00 | 2026-08-04 08:00 | S | 31.83
Seal Rock | SK4 | 83 | 2026-07-13 06:00 | 2026-07-17 18:00 | S | 4.5
Cloniffeen | SI1 | 50 | 2026-07-13 08:00 | 2026-07-13 17:00 | S | 0.33
Cloniffeen | SI2 | 50 | 2026-07-13 08:00 | 2026-07-13 17:00 | S | 0.33
Coolkeeragh | NIC30 | 408 | 2026-07-25 | 2026-07-26 | S | 1
Derrycarney | LU1 | 50 | 2026-07-27 08:00 | 2026-07-28 17:00 | S | 1.33
Derrycarney | LU2 | 50 | 2026-07-27 08:00 | 2026-07-28 17:00 | S | 1.33
Coolkeeragh | NIC30 | 408 | 2026-08-17 | 2026-09-30 | S | 44
Poolbeg | PB6 | 168 | 2026-08-30 | 2026-10-10 20:00 | 84 | 41.83
Poolbeg | PB4 | 148 | 2026-08-30 08:00 | 2026-10-10 20:00 | S | 41.5
Whitegate | WG1 | 444 | 2026-09-04 21:00 | 2026-11-02 21:00 | S | 59
Seal Rock | SK3 | 83 | 2026-09-07 06:00 | 2026-09-09 18:00 | S | 2.5
Erne | ER4 | 23 | 2026-09-07 08:00 | 2026-09-11 20:00 | S | 4.5
Edenderry | ED3 | 58 | 2026-09-11 08:00 | 2026-09-11 18:00 | S | 0.42
Edenderry | ED5 | 58 | 2026-09-11 08:00 | 2026-09-11 18:00 | S | 0.42
Moneypoint | MP3 | 285 | 2026-09-18 22:00 | 2026-10-04 22:00 | S | 16
Tynagh | TYC | 404 | 2026-09-28 20:00 | 2026-10-03 20:00 | S | 5
Whitebank | DW1 | 61.5 | 2026-10-05 | 2026-10-09 | 26 | 4
Aghada | AD3 | 19 | 2026-10-07 | 2026-10-11 | S | 4
Whitebank | DW1 | 61.5 | 2026-10-12 | 2026-10-16 | 26 | 4
Inchicore | IH1 | 30 | 2026-10-14 | 2026-10-18 | S | 4
Aghada | AD2 | 449 | 2026-10-19 | 2026-10-24 23:00 | S | 5.92
Seal Rock | SK4 | 83 | 2026-11-16 06:00 | 2026-11-18 18:00 | S | 2.5
Edenderry | ED1 | 118 | 2026-12-26 12:00 | 2027-01-01 08:00 | S | 5.83
|  |  | Scheduled Outage | S
|  |  | Forced Outage | F
|  |  | Unit partially available | 10