## Cover Sheet
The Market Operator User Group Action Register is a repository of the actions recorded during the MOUG sessions. The list of actions on the next tab contains all of the actions that have been raised and recorded from the MOUG sessions. An updated list of actions will be published on this website following each MOUG to provide visibility of the process to all stakeholders. The Action Register is crucial in ensuring the issues and feedback raised at the MOUG sessions are addressed and resolved in a timely manner. It also provides all stakeholders with a detailed description of the status of the actions. The list below defines the list of possible statuses for each action: 1. Open - Action has been raised, discussed, assigned to workstream owner or work in progress to be completed. 2. Closed - Action has been delivered and completed or cancelled.
Marker Operator User Group Action Register
Last Updated 27/11/2019

## Main Action Register
Ref No. | Source | Date Raised | Topic | Actions | Status | Update / Resolution
1 | MOUG | 2019-06-20 | CCQT | Test Environment to be made available in advance of planned releases | Closed | 10/09/2019: Participant testing is only required when we are releasing changes that impact the participants. E.g. External facing systems such as the MPI. There are externally facing changes in Release E set for around February 2020, so a test environment will be available for PTs then but not for Release D.
2 | MOUG | 2019-06-20 | SEMOpx | Technical Specifications need to be made available to participants earlier than they are provided at the minute. | Closed | 19/07/2019: ECC have confirmed that they will give members more time to adapt their systems.
3 | MOUG | 2019-06-20 | KIR | Market Message to contain information advising of any amendments to previous KIR. | Closed | 19/07/2019: A date added and date modified column added to the report. A colour coded legend has been added to the header of the report to denote items closed and modified the particular week. Implemented on 28/06/2019.
4 | MOUG | 2019-06-20 | FX Rate | Capacity Payment - exchange rate for NI. Update to be provided on timeline for the change request to be completed. | Closed | 22/10/2019: This is included in Release E which will be released into production at the end of March 2020.
5 | MOUG | 2019-06-20 | SEMOpx | ETS Release - request for step-by-step instructions on processes and a central POC in case of emergency. | Closed | 10/09/2019: Members comments will be taken on board regarding communications for future ETS releases. The Simulation release notice will specify the Client URL; Port and API URL; Port (Full Name). The Production cutover notice will also reiterate the required Client URL; Port and API IRL; Port (Full Name). If members have further suggestions for the structure or content of future release notices, please do not hesitate to submit these to info@semopx.com Regarding the request for a single PoC, we are taking this into consideration but will not be in a position to confirm the content point(s) until closer to the date of the next release. 22/10/2019: We hope that you agree that the release notice issued for ETS V3.3.2 addressed your suggestions, but as always appreciate your continued suggestions for improvement. We considered your request to have a single point of contact in case of emergency, however to ensure that queries regarding ETS releases are addressed by the available technical expert, members should continue to contact MarketOps directly; either via phone selecting option 1 or via email to marketops@ops.semopx.com As with all SEMOpx queries, when raising queries directly with MarketOps, members are asked to copy our Info@semopx.com team to allow us to monitor efficient resolution for you.
6 | MOUG | 2019-06-20 | SEMOpx | M7 Password – If there is a change to security settings can these details be issued via a communication | Closed | 22/10/2019: This was originally communicated on 22/06/2019 and will come in with M7 6.7 release. Please be advised that the release of M7 6.7 is further delayed to end of Quarter 3 2019 as communicated via an updated message on 11/07/2019 and at the MOUG on the 18/07/2019.
7 | MOUG | 2019-06-20 | Resettlement | In-depth logic around templates to be presented to allow participants to understand the process how the resettlement is calculated. | Closed | 19/07/2019: Webinar for participants held on 24/05/2019 covered the subject. Followed up individually with the participant. Not valid for all participants.
8 | MOUG | 2019-06-20 | Settlements | If Settlement Documents are published later the same day as scheduled, payments in/out dates should be adjusted to allow participants process the invoices properly. | Closed | 10/09/2019: If Settlement issued before 4pm we were remaining with the same Payments In and Payments Out date. The T&SC states that after 12pm then the dates for Payments In and Out need to change. We will operate it in line with T&SC going forward.
9 | MOUG | 2019-07-18 | Repricing | Provide a solution and/or update at the next MOUG how participants could see the difference in settlements after re-pricing. Similar to M+4 Forecasts for the week ahead. | Closed | 10/09/2019: We will not be in a position to do forecasts for Repricing. We will cover M+13 and how it will fit with Repricing at the next MOUG (11/09/2019).
10 | MOUG | 2019-07-18 | SEMOpx | Present a process and timeframe for Scalable Complex Orders at the next MOUG | Closed | 22/10/2019: To be communicated when agreed public description is available. The next MOUG (11/09/2019) will provide some information on timeframes and the process which will be followed.
11 | MOUG | 2019-07-18 | OPI | Follow up on EDIL and MPI declarations of availability for DSUs | Closed | 22/10/2019: This was covered as part of a session at the MOUG on 11/09/2019.
12 | MOUG | 2019-07-18 | Query Management | Provide an age breakdown of the query backlog at the next MOUG | Closed | 22/10/2019: This was provided at the MOUG on 11/09/2019.
13 | MOUG | 2019-07-18 | OPI | Host a workshop for participants on the All Island Transmission network and impact of outages | Closed | 22/10/2019: This was covered as part of a session at the MOUG on 11/09/2019.
14 |  | 2019-09-11 | Front Office | Send details for EWIC mailbox | Closed | 22/10/2019: Market Message sent to Participants with Interconnector Contact Information.
15 |  | 2019-09-11 | Settlements | Approach to catch up M+4 to be considered and clarified, should Participants have impact in this decision. | Closed | 22/10/2019: Catch up of M+4 is being planned to re-start on November 25th. Discussion will take place at the MOUG on the proposed plan for this and market participants will have an opportunity to input into that decision.
16 |  | 2019-09-11 | Settlements | Clarification if BALIMB and CRM can be run independently. | Closed | 22/10/2019: Settlements have looked into the possibility of catching up on M+4 CRM separately. But due to metering appearing in only BALIMB report 44, Participants would not be able to shadow settle CRM component as a result of metering changes , it’s not an approach that Settlements can consider as a catch-up option.
17 |  | 2019-09-11 | Recertification | To provide update when available and consider if the scope can be agreed with Participants before commencing. | Open
18 |  | 2019-10-23 | Capacity Market | Q&A session to be organized to walk through the CMP. | Closed | 27/11/2019: Q&A session was held on 14/11/2019.
19 |  | 2019-10-23 | Front Office | Market Message to be issued regarding Helpdesk cover over Christmas period. | Closed | 27/11/2019: Market Message sent to Participants with Helpdesk cover in Christmas period: https://www.sem-o.com/market-messages/message/index.xml?message=1434
20 |  | 2019-10-23 | Front Office | Average age of queries – to be presented at the next MOUG | Closed | 27/11/2019: Will be provided at MOUG on 28/11/2019.
21 |  | 2019-10-23 | Legacy SEM | Will there be adhoc resettlements once M+13 Resettlement be completed? To be communicate via market message. | Closed | 27/11/2019: This was addressed in the FAQ document that was issued on 5th November. There is the option for PT’s to raise a settlement query up until November 29th. There is then an option for PT’s to raise a general dispute up to 6 months after the last settlement of legacy SEM. These were both addressed in the below Q&A. https://www.sem-o.com/market-messages/message/index.xml?message=1353
22 |  | 2019-10-23 | Settlements | Agenda for the Settlements Special Topic Session to be emailed to Participants to allow them to submit what discussion points they may have. | Open

## Status classification (hidden)
Importance (H, M, L): | Status (Project Team): | Expl
H | Open | Comment received, unaddressed
M | Closed | Issue resolved or de-scoped
L