## Slide 1
Market Systems Release Update
Modifications Committee Meeting 67
April 14th 2016

## Slide 2
Approved Scope for this release is as follows:
SEM R2.8.0 will be the final Central Market Systems release under the current 3 year vendor release contract.
SEM R2.8.0 Release
CR Ref | Description | Source
SEM_PC_CR351 | Sort Change for PUMP Eligible Availability | Market Audit
SEM_PC_CR353 | iPlanet (webserver) Upgrade | Technical
SEM_PC_CR354 | Electricity VAT Change | Revenue

## Slide 3
Scope approved Feb 1st
Proof of Concept with vendors Mar 4th
Publication of HLIA Mar 11th
Software delivery Apr 11th
System Integration Test Execution Apr 11th to May 20th
Connectivity Test Apr 25th to Apr 29th
Market Test Execution May 11th to May 20th
Deployment * Jun 17th
* subject to successful completion of all testing.
SEM R2.8.0 – Schedule

## Slide 4
Initial Capacity Settlement delayed on March 9th
  Caused by internal software issue relating to the number of rows that can be inserted to the database at any one time.
  Software patch was issued by our vendor on the evening of March 9th, tested overnight and deployed to Production on March 10th.
Issues during weekend of March 19th / 20th
  UPS failure in Castlereagh House data centre at 1:30 AM on March 19th resulted in a forced outage of the Central Market Systems.
  Service was restored by 4:30 AM.
  Consequential issues encountered over the weekend resulting in
    delays to the publication of the EA1 schedule for Trading Days 20th & 21st March and
    cancellation of a number of EA2 and WD1 MSP and MIUN runs.
  Systems personnel worked through the weekend to address the issues.
Recent Operational Issues

## Slide 5
Questions