## Slide 1
Market Systems Release Update
Modifications Committee Meeting 68
June 9th 2016

## Slide 2
Approved Scope for this release is as follows:
SEM R2.8.0 will be the final Central Market Systems release under the current 3 year vendor release contract.
SEM R2.8.0 Release
CR Ref | Description | Source
SEM_PC_CR351 | Sort Change for PUMP Eligible Availability | Market Audit
SEM_PC_CR353 | iPlanet (webserver) Upgrade | Technical
SEM_PC_CR354 | Electricity VAT Change | Revenue

## Slide 3
Scope approved Feb 1st Complete
Proof of Concept with vendors Mar 4th Complete
Publication of HLIA Mar 11th Complete
Software delivery Apr 11th Complete
System Integration Test Execution Apr 11th to May 20th Complete
Connectivity Test Apr 25th to Apr 29th Complete
Market Test Execution May 11th to May 20th Complete
Deployment * Jun 17th
* subject to successful completion of all testing.
SEM R2.8.0 – Schedule

## Slide 4
Questions