## PED
Item # | Date Raised | Comment | Raised By | Document | Document Section | Response | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
34
35
36
37
39
40
41
42
43
44
45
46
47
48
49
50

## LegalDrafting
Item # | Date Raised | Comment | Raised By | Document | Document Section | Response | Status
1 | 2011-05-03 | The main changes here introduce two new paragraphs which do not apply to the registration of Interconnectors and which are included within the range of "subject to" already there. I don’t think this change is needed. | RAs | TSC | 2.71 | Drafting has been updated to revert to original drafting. | Closed
2 | 2011-05-03 | This is a new paragraph duplicates 2.62A - not required | RAs | TSC | 2.88A | Paragraph 2.62A changed to remove reference to IRCU (2.88A covers this). | Closed
3 | 2011-05-03 | This paragraph refers to the registration of an Interconnector User, which isnt registered. I suggest changing "Interconnector User" to "Interconnector Unit". | RAs | TSC | 2.98A | This clause has been changed to relect the fact that Interconnector Units are registered. | Closed
4 | 2011-05-03 | This change alters the word "such" (a reference back to suspension at the beginning of the paragraph) to "the". I suggest that "such" is more legally robust. The sub-paragraphs set Active Capacity Holdings to zero under suspension. I assume that Active Capacity Holdings are zero (at least for EA1) for any Interconnector Users who have acquired no capacity from the Interconnector User. I could not find where this was set out. | RAs | TSC | 2.100 | Drafting has been updated to revert to using the word "such". | Closed
5 | 2011-05-03 | This refers specifically to each Gate Window Closure. I believe that the words "any Gate Winodw Closure" would be more effective | RAs | TSC | 3.20A | Drafting has been revised as suggested. | Closed
6 | 2011-05-03 | Same point as for 3.20A | RAs | TSC | 3.40 | Drafting has been revised as suggested. | Closed
7 | 2011-05-03 | I think this could refer to "any Gate Window Closure" and the new 3.42K would not then be needed. In addition, the definitions of EA1, EA2 and WD1 are suggested above, I don’t think the refernce to the MSP Software Run is required (incidentally MSP Software Run is not defined so I would suggest the words "run of the MSP Software" | RAs | TSC | 3.42J | Ex Ante One MSP Software Run etc. is explicitly defined in the Glossary and references Appendix N. As part of the FG2 drafting, SEMO will update the references in Appendix N to describe the new runs. The 3.42 clauses need to remain separate, as a VTOD choice cannot be submitted to the WD1 Gate Window. | Closed
8 | 2011-05-03 | I would suggest that this starts with a statement like "A Participant shall not submit a Data Transaction containing a Validation Set Number in respect of any WD1 Gate Window" | RAs | TSC | 3.42L | Drafting has been revised as suggested, other than to include "to any Gate Window" instead of "in respect of any Gate Window". | Closed
9 | 2011-05-03 | I am nervous about the removal of the reference to Trading Day in this paragraph as amended, since data relating to all three Gate Windows also relate to a Trading Day. I would suggest words that refer to the Trading Day and "relevant Gate Window". In addition the term Starting Gate Window Data needs to be in the Glossary. | RAs | TSC | 3.44 | SEMO has amended the clause to relate to the actions to be taken when Starting Gate Window Data should apply in respect of particular Gate Window. The data submitted to a Gate Window is in respect of a Trading Window which is a part of the relevant Trading Day. The definition of Starting Gate Window Data has been added to the Glossary and PED. | Closed
10 | 2011-05-03 | I note the correction of the erroneous paragraph numbering from 3.46 (should be 3.43) to the end of the section. I suggest these should be corrected in the upcoming publication of Version 9 of the Code. | RAs | TSC | 3.43 | As explained at Working Group 8, all changes made in versions of the Code after version 8.0 will be included in the final version to be considered by the Modifications Committee. This particular numbering error has already been addressed in version 9.0 of the T&SC. | Closed
11 | 2011-05-03 | This obliges Participants to submit COD and TOD for all three Gate Windows but I believe that TOD is not submited for WD1. This also changes the refernce to Trading Day (the Trading Window), but I suggest a reference to Trading Day (this is, a specific Trading Day is retained since the data does refer to (a part) of a specific Trading Day. I would also suggest that the words "provisions of paragraph 3.44" might for clarity be changed to "values of Starting Gate Window Data as set out in paragraph 3.44". | RAs | TSC | 4.4 | Forecast Data is Technical Offer Data under the Code and may therefore be submitted to each Gate Window. The drafting reflects this. SEMO believes that the drafting of paragraph 4.4 is correct, as COD/TOD is submitted within a Gate Window for a Trading Window for a particular Trading Day. Reference to COD/TOD being submitted for a Trading Day would be misleading, as for WD1 the data will only relate to the portion of the Trading Day that is within the Trading Window. | Closed
12 | 2011-05-03 | Refers to Offered Modified Quantity and Price, both of which need to be in the Glossary. | RAs | TSC | 4.16 | This has been included in the FG1+FG3 drafting . | Closed
13 | 2011-05-03 | I'm not convinced that any change is needed to this paragraph or to 4.27 | RAs | TSC | 4.26, 4.27 | SEMO believes that the changes to the drafting enhance clarity as, under Intra-Day Trading, there are multiple Gate Windows within which COD/TOD may be submitted. | Closed
14 | 2011-05-03 | I believe that the data referred to is submitted to all Gate Windows so the words "within any Gate Window" are not required. This paragraph also deletes the words "including zero". I accept that this is not required, but I would suggest that it is helpful to remind readers that zero is treated as a positive number. | RAs | TSC | 4.28 | SEMO believes that the inclusion of "within any Gate Window" enhances clarity as, under Intra-Day Trading, there are multiple Gate Windows within which COD/TOD may be submitted. "(including zero)" has been reinstated in the drafting. | Closed
15 | 2011-05-03 | The table reference has been changed. It's not clear why | RAs | TSC | 5.18 | This is a field updating issue with Microsoft Word and is not intended to be a change. This has been resolved in the FG1+FG3 merged drafting. | Closed
16 | 2011-05-03 | Another removal of "(including zero)" | RAs | TSC | 5.35 | Drafting reverted to original. | Closed
17 | 2011-05-03 | This seems to repeat itself. I would suggest "Interconnector Users may submit Commercial Offer Data for each Trading Day to the Market Operator in respect of their Interconnector Units for the corresponding Gate Window" | RAs | TSC | 5.51 | Drafting has been revised as suggested with slight non-material wording difference. | Closed
18 | 2011-05-03 | Since the same restrictions apply to every Gate Window, the references to EA1, EA2 and WD1 are not required; | RAs | TSC | 5.52 | The drafting change to 5.5.2 has been removed. (PED also edited to reflect this.) | Closed
19 | 2011-05-03 | The paragraph refers to "each Trading Day in line 2 so I don't think the additional reference is needed" |  | TSC | 5.174 | Drafting changed to remove reference to "for each Trading Day". Submission of COD is covered elsewhere in the T&SC. | Closed
20 | 2011-05-03 | See comments above. In addition, I do not think that a definition Accession is required. The term is not used capitalised in the Code. The capitalised terms Accession Deed, Accession Fee etc are defined. | RAs | TSC | Glossary | As suggested, the definition of Accession has been removed from the drafting, PED and slides. In addition, the definition of Accession Process has been changed to "means the process set out at paragraphs 2.13 to 2.19.". AP1 sections 3.1.2 and 3.4.5 changes have also been reversed. | Closed
21 | 2011-05-03 | No comment except that there are several changes marked which don’t appear to be changes | RAs | TSC | Appendix H | The highlighted changes are due to resolving row spacing, font sizing and text justification issues within this table. It is suggested that these are included within the drafting to ensure that the issues are resolved in the resulting Code. | Closed
22 | 2011-05-03 | Paragraphs I.2A, I.2B and I.2C refer to "paragraphs I.3 to I.11", which have been removed. Should this reference be to Table I.1 and Table I.2? All three paragraphs say the same thing in relation to different gate Windows, it might be simpler to have one paragraph which refers to "Each Gate Window". | RAs | TSC | Appendix I | Paragraph references (I.3 to I.11) changed to I.2D and I.2E. No change to I.2A to I.2C references to each Gate Window and its associated MSP Software Run. | Closed
23 | 2011-05-03 | Paragraphs I.2A and I.2B say "Each Participant shall submit" COD, should this "shall" be "may"? | RAs | TSC | Appendix I | Additional clause I.2D added to clarify this. | Closed
24 | 2011-05-03 | Paragraphs I.3A and I.3B both refer to I.3 to I.11; should this reference be to Table I.3? | RAs | TSC | Appendix I | Paragraph references (I.3 to I.11) changed to I.3D and I.3E. | Closed
25 | 2011-05-03 | Paragraph I.3D, the numbering of the sub-paragraphs appear to start at 4. When corrected this will impact the table heading in the last column of Table I.3 | RAs | TSC | Appendix I | Numbering is correct and does not need to be changed. | Closed
26 | 2011-05-03 | IN Appendix 1 definitions of BACS and CHAPS refer to the Code where definitions have been added to the Glossary but AP14 has definitions of its own and these need changing to refer to the Code also. | RAs | TSC | AP1 | These are actually contained within AP17, not AP14. AP17 definitions have been changed to refer to the definition within the main body of the Code. New PED_FG1 entries added to reflect these changes. | Closed
27 | 2011-05-03 | In a number of places "Calculation of Modified Interconnector Unit Nominations" is referred to. I would suggest that Appendix 2: should be added to all these references, so that the reader knows where to find it. | RAs | TSC | AP2 | References added where missing (plus resolved field updating issues). PED references updated. | Closed
28 | 2011-05-03 | In the definition of Query Data Window, the end time is shown as "no ent time, although subject to data availability". I don’t understand what this means and whether it is consistent with the Code provisions on raising of Queries. | RAs | TSC | AP4-Section 2.3.5 | The existing nomenclature in the AP is confusing. The non-capitalised Data query is a query of system data. It is not a formal "Data Query" as defined in the T&SC. The Query data window is the period in which a Participant may retrieve the data held in the Isolated Market System, not a formal Data Query as defined in the T&SC. The Query data window has been renamed the System Data retrieval window in AP4 to avoid confusion. | Closed
29 | 2011-05-11 | Need to confirm that SEM-O have the remit to raise changes that are not related to Intra-Day Trading within the scope of MOD_18_10 Working Group | Synergen | n/a | n/a | This was discussed extensively at Working Group #8. Most attendees (e.g. RAs, SEMO, TSOs, Kilroot) have agreed that SEMO's approach is prudent, as long as the PEDs clearly identify those changes that are not as a direct result of IDT. Additionally, there is an established principle of addressing errors / inconsistencies / clarity issues with Modifications as they are identified. | Closed
30 | 2011-05-11 | PED_FG1_32, PED_FG1_33 & PED_FG1_34 These code clauses need to be clear that the range of COD and TOD data is only applicable for the Trading Periods within the Trading Window related to the relevant Gate Window. In particular there can be no retrospective element of bidding at WD1. | Synergen | T&SC | 4.17, 4.20, 4.21, 4.22, 4.23, 4.24, 4.26, 4.27, 4.28, 4.29, 4.30 | Drafting to some clauses changed to clarify that data is submitted within any Gate Window in respect of the corresponding Trading Window in a particular Trading Day." The proposed changes to 4.20/4.26/4.27 are not correct, as VTOD will apply for the entire Optimisation Time Horizon for the relevant Trading Day. Hot Cooling Boundary and Warm Cooling Boundary are consistent across the entire Optimisation Tiome Horizon. WD1 submissions are not permitted. | Closed
31 | 2011-05-11 | PED_FG1_35 isn't required given that Appendix I isn’t new | Synergen | T&SC | 5.9A | This is included to clarify that Appendix I and the provisions of Section 5 for Special Units should be read together in order to fully understand the provisions in respect of COD and TOD. | Closed
32 | 2011-05-11 | PED_FG1_36 isn’t needed should be rejected - the current drafting is useful | Synergen | T&SC | 4.28, 4.30, 4.36, 5.35, 6.58 | (including zero) restored to paragraphs 4.28, 4.30, 4.36, 5.35 and 6.58. PED_FG1_36 has been removed and other PED references renumbered. | Closed
34 | 2011-05-11 | PED_FG1_39 needs to apply to 5.56 as well | Synergen | T&SC | 5.56-5.57 | 5.56 will change further under the scope of FG2 (MSP Software). | Closed
35 | 2011-05-11 | PED_FG1_43 & PED_FG1_45 These code clauses refer to Gate Window rather than Trading Window. | Synergen | T&SC | 5.156, 5.160, 5.174 | Drafting changed to "submitted to a Gate Window in respect of the corresponding Trading Window for 5.156 and 5.160. Drafting changed to remove reference to "for each Trading Day" in 5.174. Submission of COD is covered elsewhere in the T&SC. | Closed
36 | 2011-05-11 | The issue related to the use of Trading Window rather than Gate Window or Trading Day needs further review across all Functional Group drafting | Synergen | All Functional Groups | n/a | SEMO has responded to comments as provided and has reviewed the descriptions in respect of Gate Window/Trading Window/Trading Day. | Closed
37 | 2011-05-17 | sub-paragraph 1 and 2 both relate to the Trading Periods which CMS Data Transactions relate to (not to the time of submission of the data). It is therefore suggested the words “for that Gate Window” should be “for that Trading Window” in each sub-paragraph | RAs | TSC | 3.44 | Drafting changed to Trading Window as suggested. | Closed
39 | 2011-05-17 | the paragraph relates to the submission of Forecast Availability for “any” Gate Window. Since the data submitted for WD1 relates to less than the Trading Day it is suggested that “in respect of the relevant Trading Day” should be “in respect of the relevant Trading Window | RAs | TSC | 4.28 | Drafting changed to "Trading Window for the relevant Trading Day" as suggested. | Closed
40 | 2011-05-17 | the paragraph relates to the submission of Forecast Minimum Output Profile for “any” Gate Window. Since the data submitted for WD1 relates to less than the Trading Day it is suggested that “in respect of the relevant Trading Day” should be “in respect of the relevant Trading Window”. | RAs | TSC | 4.29 | Drafting changed to "Trading Window for the relevant Trading Day" as suggested. | Closed
41 | 2011-05-17 | suggest replacing “given Trading Window” with “particular Trading Window” | RAs | TSC | 5.56 | Drafting changed as suggested. | Closed
42 | 2011-05-17 | both paragraphs relate to the submission of TOD for Trading Periods. Therefore the words “particular Gate Window” should be “particular Trading Window” | RAs | TSC | 5.114, 5.115 | Drafting changed to state that TOD is submitted "to a Gate Window in respect of the corresponding Trading Window for a particular Trading Day ". | Closed
43 | 2011-05-17 | on the basis of a similar consideration to above all three paragraphs should refer to an “associated Trading Window” not “Gate Window”; | RAs | TSC | 5.122, 5.123 & 5.124 | Drafting changed to state that TOD is submitted "by the Gate Window Closure for the associated Trading Window". | Closed
44 | 2011-05-17 | Any Participant submitting Commercial Offer Data in respect of a Demand Side Unit for any Gate Window shall not include any No Load Costs or Start Up Costs in such a submission. | RAs | TSC | 5.159 | Drafting changed as suggested. | Closed
45 | 2011-05-17 | these two paragraphs are doing a similar job in respect of COD to be submitted in respect of a Demand Side Unit. Both originals are a little imprecise because they don’t specify which Participants are being referred to. In addition it is suggested that 5.159 doesn’t need any change, though 5.160 does. I would suggest words such as: | RAs | TSC | 5.159 & 5.160 | Paragraph 5.159 specifically excludes Start Up Costs and No Load Costs for Demand Side Units. Paragraph 5.160 requires submission of a Shut Down Costs for Demand Side Units. Change to 5.160 implemented in the revised drafting to: "Any Participant submitting Commercial Offer Data in respect of a Demand Side Unit to any Gate Window in respect of the corresponding Trading Window shall include a single Shut Down Cost in such a submission." | Closed
46 | 2011-05-17 | Any Participant submitting Commercial Offer Data in respect of a Demand Side Unit for any Gate Window shall include a single Shut Down Cost is such a submission. | RAs | TSC | 5.160 | see #45 | Closed
47 | 2011-05-17 | this paragraph also refers to the submission of COD but the amendments do not recognise that multiple submissions take place. I would suggest that “for each Trading Day” should be “in respect of each Gate Window” and that “for the relevant Trading Day” should be “for the relevant Trading Window” | RAs | TSC | 5.174 | Drafting changed to remove reference to "for each Trading Day". Submission of COD is covered elsewhere in the T&SC. | Closed
48 | 2011-05-23 | Definition of Ex-Ante Two (EA2) Market Schedule - should possibly be "...(MSQuh) for each Trading Period in the Trading Window..." | Tynagh Energy | T&SC | Glossary | The EA1 Market Schedule will be produced for the entire Trading Day. | Closed
49 | 2011-05-23 | Definition of Within Day One (WD1) Market Schedule - should possibly be "...(MSQuh) for each Trading Period in the Trading Window..." | Tynagh Energy | T&SC | Glossary | The EA2 Market Schedule will be produced for the entire Trading Day. | Closed
50 | 2011-05-23 | Definition of Ex-Ante One (EA1) Market Schedule - should possibly be "...(MSQuh) for each Trading Period in the Trading Window..." | Tynagh Energy | T&SC | Glossary | The WD1 Market Schedule will be produced for the entire Trading Day. | Closed
51 | 2011-05-23 | Suggestion: Each Participant shall ensure that the Commercial Offer Data submitted within any Gate Window in a Trading Day, in respect of each of its Generator Units, shall include one No Load Cost which applies to all Trading Periods in the applicable Trading Window. | Tynagh Energy | T&SC | 4.17 | Drafting changed to "Each Participant shall ensure that the Commercial Offer Data submitted within any Gate Window in respect of each of its Generator Units shall include one No Load Cost which is applicable to all Trading Periods in the corresponding Trading Window in a particular Trading Day." | Closed
52 | 2011-05-23 | Suggestion: Each Participant shall ensure that the Technical Offer Data submitted within any Gate Window in a Trading Day, in respect of each of its Generator Units, shall include a Hot Cooling Boundary and a Warm Cooling Boundary, which apply to all Trading Periods in the applicable Trading Window... | Tynagh Energy | T&SC | 4.20 | The proposed change is not correct, as VTOD will apply for the entire Optimisation Time Horizon for the relevant Trading Day. Hot Cooling Boundary and Warm Cooling Boundary are consistent across the entire Optimisation Tiome Horizon. | Closed
53 | 2011-05-23 | Suggestion: Each Participant shall ensure that the Forecast Availability Profile submitted in respect of each of its Generator Units within any Gate Window shall contain the Participant's forecast of average level of Availability, in MW, for the Generator Unit for all Trading Periods in the Optimisation Time Horizon of the applicable Trading Window in the relevant Trading Day. | Tynagh Energy | T&SC | 4.28 | Drafting changed to "Trading Window for the relevant Trading Day". | Closed
54 | 2011-05-23 | Suggestion: The Forecast Minimum Output Profile, submitted within any Gate Window, shall contain the Participant's forecast of the average level of Minimum Output, in MW, for the Generator Unit for all Trading Periods in the Optimisation Time Horizon of the applicable Trading Window in the relevant Trading Day. | Tynagh Energy | T&SC | 4.29 | Drafting changed to "Trading Window for the relevant Trading Day". | Closed
55 | 2011-05-23 | Suggestion: The Forecast Minimum Stable Generation Profile, submitted within any Gate Window, shall contain the Participant's forecast of the average level of Minimum Stable Generation in MW, for the Generator Unit for each Trading Period in the Optimisation Time Horizon of the applicable Trading Window in the relevant Trading Day. | Tynagh Energy | T&SC | 4.30 | Drafting changed to "Trading Window for the relevant Trading Day". | Closed
56 | 2011-05-23 | Typed as 1.2E instead of 1.3E | Tynagh Energy | Appendix I | I.3E | Paragraph numbering issue rectified in drafting. | Closed
57 | 2011-05-30 | It is not clear why it is necessary to include a definition of Accession, when "Accession Process" is already defined. As Accession indicates that a party has ‘completed the Accession Process’ and has ‘become a Party to the Code’ those phrases could be used rather than creating a new definition. In particular, the proposed definition of Accession overlaps with the current definition of ‘Accession Process’ insofar as they both refer to the process – if a definition is to be included it is suggested that it would simply state that Accession is the point at which an Applicant becomes a party to the Framework Agreement and becomes bound by the Code. Note also that there are instances where the term ‘Accession’ has not been capitalised within the text of the TSC, eg Agreed Procedure 1 (thiswill only be necessary if a definition is included). | Endesa | Glossary | Accession Definition | The definition of Accession has been removed from the drafting, PED and slides. In addition, the definition of Accession Process has been changed to "means the process set out at paragraphs 2.13 to 2.19.". AP1 sections 3.1.2 and 3.4.5 changes have also been reversed. | Closed
58 | 2011-05-30 | It is not clear what is meant by ‘Higher Operating Limit’ and ‘Lower Operating Limit’. It seems as though these definitions are superfluous as in reality the limits are set by Availability, Min Gen and the MEC of a unit. | Endesa | Glossary | Higher Operating Limit and Lower Operating Limit Definitions | The inclusion of Lower Operating Limit and Higher Operating Limit is required to provide additional clarity of the upper and lower scheduling limits as applied within the MSP Software (as detailed in Appendix N, drafting to be included within FG2). For Intra-Day, the setting of these limits is more complicated and is based on the Run Type (e.g. for Interconnector Units). In addition, where Accepted PQ Pairs are excluded in the determination of Offered Modified Price Quantity Pairs for Interconnector Units, the Lower Operating Limit is set equal to zero (as per drafting in FG3). | Closed
59 | 2011-05-30 | Endesa Ireland is not satisfied by the definition of ‘Interconnector Unit’ which requires a separate unit for each gate window. This stretches the concept of ‘unit’ too far, which is considered unnecessary and confusing. It would be preferable if participants registered in respect of one Interconnector Unit with a ‘Gate Window Identifier’ as described in Table 9 of AP4 identifying the relevant gate window. This would affect a number of conditions in the Code and Agreed Procedures. Endesa Ireland propose that the ‘Interconnector Unit’ would be designated as a special unit, and that any additional requirements could be captured within special conditions. It is queried what impact the definition currently proposed by SEMO would have on capacity payments and how reporting/invoicing would be handled – this should be fully explained and discussed. | Endesa | Glossary | Interconnector Unit Definition | The issue of there needing to be independent Units for each Gate Window was discussed extensively as part of the Phase 1 Working Group (WGs4-7). In particular, a solution with a single Unit per Partioipant and Interconnector was discarded to allow Participants to bid out of a previous position, which it was agreed would be fixed from each successive MSP Software Run. The systems design and drafting are based on this agreed principle. | Closed
60 | 2011-05-30 | Definitions of ‘Offered Modified Price Quantity Pairs’ and ‘Trading Window’ appear in the PED but not in the revised Glossary itself. The term ‘Offered Modified Price Quantity Pairs’ is not clear as it suggests that the Participant offers modified data, which is not the case. It is presumed that Appendix P will be proposed in another functional group. | Endesa | Glossary | Offered Modified Price Quantity Pairs definition | Appendix P (contained in the drafting for FG3) explains the process by which Accepted Commercial Offer Data for Interconnector Units is modified where insufficient Credit Cover is in place. This Appendix is consistent with the principles as described in the High Level Design. The definition of Offered Modified Price Quantity Pairs has been changed to "means a set of Price Quantity Pairs for Interconnector Units as derived from Accepted Commercial Offer Data in accordance with Appendix P." Definition of Trading Window has been added to the Glossary. | Closed
61 | 2011-05-30 | Endesa Ireland is keen to see how the definition of ‘Trading Window’ sits with the definition of ‘Trading Day’. The term ‘MSP Software Run’ is not defined, although it is capitalised in the definitions of ‘Gate Window’, ‘Gate Window Opening’, ‘Higher Operating Limit’, ‘Lower Operating Limit’. Endesa Ireland proposes that it should be defined and that this definition should specify whether LR or MIPS programming is to be used, as it is felt to be inappropriate to alternate between the methods, particularly if the method changes within day. | Endesa | Glossary | Trading Window, Trading Day Definition | This will be addressed as part of the FG2 drafting, where changes to the provisions relating to the MSP Software will be made. | Closed
62 | 2011-05-30 | Consider amending wording – it currently reads that an Interconnector User must register one and only one Interconnector Unit for each Gate Window. Suggest it should be ‘may’ rather than ‘must’. The obligation is clarifying that there only be one unit, not that there is an obligation to register for every window. See also Endesa Ireland’s view of the definition of Interconnector Unit discussed above. | Endesa | PED, TSC | PED_FG1_19; TSC Section 2.98A | The issue of there needing to be independent Units for each Gate Window was discussed extensively as part of the Phase 1 Working Group (WGs4-7). In particular, a solution with a single Unit per Participant and Interconnector was discarded to allow Participants to bid out of a previous position, which it was agreed would be fixed from each successive MSP Software Run. The systems design and drafting are based on this agreed principle, so has not been changed. | Closed
63 | 2011-05-30 | Numbering seems to be misplaced. | Endesa | TSC | TSC Old Section 3.47 | Whilst the tracked changes version appears as though there is a numbering issue, the non-tracked version is correct. | Closed
64 | 2011-05-30 | The terms ‘Offered Modified Quantity’ and ‘Offered Modified Price’ are not defined, although capitalised in the text. It is not evident what these terms mean, as they suggest that Participants would offer modified quantity and price, which is not the case. | Endesa | TSC | Section 4.16 | Glossary definitions of Offered Modified Price and Offered Modified Quantity have been added. | Closed
65 | 2011-05-30 | Suggest that the proposed ‘Gate Window’ should read 'Trading Window' | Endesa | TSC | Section 5.114, 5115 | Drafting changed to state that TOD is submitted "to a Gate Window in respect of the corresponding Trading Window for a particular Trading Day ". | Closed
66 | 2011-05-30 | It seems that this section should be I.3E Also, Should heading on last column read ‘Other Generator Units, not included in I.3D(8)’. | Endesa | TSC, Appendix I, Section I.2E ‘Technical Offer Data for Generator Units’ |  | Drafting amended as suggested to correct this referencing error. | Closed
67 | 2011-05-30 | The word ‘Account’ is not defined yet has been capitalised in a number of sections, including sections 3.4.4, 2.3.1 | Endesa | AP1 |  | Account ID is a defined term in AP1 Appendix. Section 3.4.4 has been edited ot reflect that it is the Account ID that is in question. | Closed
68 | 2011-05-30 | Typo in text ‘The Market Operator shall reviews...’ | Endesa | Agreed Procedure 1, | Section 3.5.1 | "s" on reviews is deleted in the change marking, so original drafting is ok. | Closed
69 | 2011-05-30 | Suggest that the number ‘2’ should not have been deleted in the second paragraph; seems that it should read ‘which will enable data submission by Type 2 or Type 3 communication.’ | Endesa | Agreed Procedure 1; | Appendix 2 | Drafting amended to correct this error. | Closed
70 | 2011-05-30 | As the proposed footnote to be inserted to the section ‘New Generator Unit Registration’ excludes nonphysical generation units, i.e. Interconnector Units, Interconnector Residual Capacity Units, Interconnector Error Units and Netting Generator Units; the registration requirements for these units should be set out and reference should be made to where the registration requirements for these units can be found. | Endesa | Agreed Procedure 1, | Appendix 3 | This section relates exclusively to the provision of meter-related data to the relevant Meter Data Provider. For non physical Generator Units, the remainder of AP1 shall apply but this data provision cannot apply. | Closed
71 | 2011-05-30 | Suggest that text is a little misleading as COD for one Interconnector Unit for each interconnector may be submitted. Suggest text be amended to read ‘Interconnector Users may submit Commercial Offer Data for one Interconnector Unit for each Interconnector prior to each Gate Window Closure.’ See also Endesa Ireland’s view of the proposed definition of ‘Interconnector Unit’ discussed above. | Endesa | Agreed Procedure 2, | section 3.2.1 | The drafting has been updated as suggested. | Closed
72 | 2011-05-30 | Seems to be a typo – change to ‘and/or one or many occurrences’ | Endesa | Agreed Procedure 4; | Section 2.3.2 | Changed occurrence to occurences as suggested. | Closed
73 | 2011-05-30 | It is not clear in Paragraph 2 why a Participant may not include an External ID as part of the associated message, or why there should be any limitation on what information a Participant may include in a query. | Endesa | Agreed Procedure 4, | Section 2.3.3 | This section relates to a Participant querying the data that is stored within the Market Operator's Isolated Market System. The format of such transactions is established and does not need to change for IDT. If a change is required, a Modification should be raised. | Closed
74 | 2011-05-30 | With respect to ‘Query Data window’, the Start Time of ‘Once Accepted’ is not clear. | Endesa | Agreed Procedure 4, | Section 2.3.4, Table 2 | The use of Query Data is confusing and is being changed for the next iteration of the drafting (FG1+FG3). The Data Query process is a defined process for querying the amounts which are used to derive settlement amounts. This section of AP4 relates to the means by which Participants may retrieve the data (e.g. Registration Data) that is stored in the Market Operator's Isolated Market System. | Closed
75 | 2011-05-30 | Endesa Ireland does not agree with the requirement in a number of elements that registration is approved on the basis of Type 1 Channel communication whereas subsequent changes may only be by Type 2 or 3 channel. It is submitted that all Channels should be acceptable for all purposes, as it is always possible that Participants will experience interruptions in communication systems. See: Application Data, Users Data, Contacts Data, Bank Data, Generator Offer Data, Demand Offer Data. | Endesa | Agreed Procedure 4, | Section 2.3.4, Table 4 | The changes to Agreed Procedure 4 do not change the existing provisions; they intend to correct errors, clarify established procedures and allow for IDT. | Closed
76 | 2011-05-30 | In the provisions for ‘Generator Parameters/Load Parameters’ it is stated that for ‘All Other Data Items’ there must be an Effective Date of the next Trading Day. It is queried whether there is a time by which such information must be submitted, for example if information was submitted at 5am would it be effective for the Trading Day beginning at 6am (i.e. within the same calendar day but a different trading day). | Endesa | Agreed Procedure 4, | Section 2.3.4, Table 4 | Amended text to reflect that Data Items must be submitted before EA1 Gate Window Closure and have an Effective Date of the nect Trading Day. | Closed
77 | 2011-05-30 | For ‘Data Query’, it is queried why ‘Generator Offer Data’ and ‘Interconnector Offer Data’ are treated separately as Interconnector Users are treated as a subset of Generators. On this basis it is proposed that ‘Interconnector Offer Data’ be removed | Endesa | Agreed Procedure 4, | Section 2.3.4, Table 4 | Interconnector Offer Data is a pre-existing concept in the Code, relating to the special provisions in respect of COD for Interconnector Units. Removal of the concept would raise wider issues than those introduced by IDT. This should be raised as a separate Modification if required. | Closed
78 | 2011-05-30 | It is not clear why a generator would have different standing data according to the day of the week and how this change is related to the introduction of Intra-day trading. | Endesa | Agreed Procedure 4, | Section 2.6.3 | The concept of a Day Type is not new for Intra-Day Trading. In reviewing and amending AP4 for IDT, SEMO has added clarification and correction of errors where they have been identified. This section does not introduce any new functionality or requirements. | Closed
79 | 2011-05-30 | It is proposed that, in Step 2, where fax is used for communication, it should also be permitted for email to be used. This should be extended to any other provisions in the Code or Agreed Procedures where the use of fax is provided for. | Endesa | Agreed Procedure 4, | Section 3.2, Table 8 | This is not a change that it required for IDT. If required, this should be raised as a separate Modification. | Closed
80 | 2011-05-30 | ‘Starting Gate Window Data’ is not defined in the glossary of the Code as suggested in this section. | Endesa | Agreed Procedure 4, | Definitions and Abbreviations | Glossary definition for Starting Gate Window Data included within the FG1+FG3 drafting. | Closed

## DesignSlides
Item # | Date Raised | Comment | Raised By | Document | Document Section | Response | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
34
35
36
37
39
40
41
42
43
44
45
46
47
48
49
50